## Instructions
05 — Adoption Measurement & Go-Live Plan
Employee Center Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the go-live communications plan for Employee Center and the KPIs that will be used to measure adoption in the first 90 days. Employee Center adoption is not automatic — it requires deliberate communication, user training, and helpdesk direction. This workbook ensures those activities happen.
Who fills this out | ECS SA provides the framework; Customer ITSM Process Owner and Communications team execute the communications plan.
Sprint window | Sprint 5 Week 2
Estimated effort | 2 hours
Related workbooks | 01 EC Design Decisions · Knowledge Pack — Knowledge KPIs
Success criteria
• | Go-live announcement is drafted and approved.
• | Helpdesk team has been briefed to direct callers to Employee Center.
• | A KB article explaining 'How to use Employee Center' is published.
• | 90-day adoption KPI targets are agreed with IT Director.
• | Monthly adoption review is scheduled.

## Process Decisions
05 — Adoption Measurement & Go-Live Plan — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What are the primary adoption KPIs for Employee Center? | Three KPIs: (1) Self-service submission rate — % of requests submitted via EC vs. phone/email/walk-up. (2) Search-to-submission rate — % of searches that result in a submission without helpdesk contact. (3) Return visit rate — % of users who use EC more than once in 30 days. |  | These three KPIs measure different aspects of adoption: that users know EC exists (self-service rate), that search is working (search-to-submission), and that users found value and returned (return visit). Together they provide a complete adoption picture.
2 | What is a realistic 90-day self-service submission rate target? | 20–30% of total request volume submitted via EC within 90 days of go-live. This is achievable without mandatory enforcement. Targets above 50% in the first 90 days require either mandatory enforcement or an exceptionally well-adopted portal. |  | 20–30% in 90 days is a realistic OOTB target based on mid-market deployments. It assumes: all IT staff directing users to EC, EC link on the intranet homepage, and go-live announcement to all employees.

## Dependencies
05 — Adoption Measurement & Go-Live Plan — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | EC portal fully configured and tested | Required | ECS SA | Sprint 5 Wk 2 | Cannot go live without a complete portal.
2 | KB article: 'How to use Employee Center' published | Required | Customer KM | Sprint 5 Wk 2 | Users need a self-service guide for the self-service portal.

## Configuration Data
05 — Adoption Measurement & Go-Live Plan — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Go-Live Communications Plan
Announcement medium | [Customer: email / intranet / Teams / all-hands]
Announcement author | [Customer: IT Director or CIO — send from leadership] | Leadership-sent announcements have higher open rates.
Announcement send date | [Go-live date]
EC URL to communicate | [Customer: ServiceNow instance URL / custom vanity URL] | If vanity URL, confirm DNS before go-live.
Helpdesk briefing date | [Before go-live — brief IT staff to direct callers to EC]
Intranet homepage link | [Customer: add EC URL to intranet homepage before go-live] | Single highest-impact adoption action.
2. Adoption KPI Targets
Self-service submission rate (90 days) | [Customer: target % — recommended 20-30%]
Search-to-submission rate (90 days) | [Customer: target % — recommended >40%]
Return visit rate (30 days) | [Customer: target % — recommended >60%]
Monthly adoption review owner | [Customer: ITSM Process Owner]
KPI reporting source | Employee Center > Analytics dashboard (OOTB)

## R&R
05 — Adoption Measurement & Go-Live Plan — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Draft go-live announcement | C | R/A | Customer Communications/ITSM PO drafts; ECS SA reviews for accuracy.
Brief helpdesk team on EC and URL | I | R/A | Customer IT Ops Lead briefs helpdesk team.
Add EC link to intranet homepage | I | R/A | Customer intranet/web team.
Publish 'How to use Employee Center' KB article | C | R/A | Customer KM authors; ECS SA reviews template compliance.
Configure OOTB EC analytics dashboard | R/A | I | ECS SA.
Run first 30-day adoption review | C | R/A | Customer ITSM PO runs; ECS SA advises on findings.

## Consultant Guide
05 — Adoption Measurement & Go-Live Plan — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The intranet homepage link
The single highest-ROI adoption action is adding the Employee Center URL to the corporate intranet homepage. It costs nothing, takes 5 minutes of the web team's time, and surfaces the portal to every employee who opens their browser to the intranet. Confirm this is in the customer's go-live plan — not as an aspiration but as a committed action with an owner and a date.
Helpdesk as EC ambassadors
Brief the helpdesk team before go-live with one simple instruction: when a user calls for anything submittable in the catalog, say 'Let me show you how to submit that in Employee Center — it is faster and you can track the status.' One successful EC submission converts a user. The helpdesk team creates more EC adoptions per day than any marketing campaign.

## Adoption vs Re-engineering
05 — Adoption Measurement & Go-Live Plan — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We will train employees to use EC before go-live | Do not invest in training — invest in communications and helpdesk direction. Employee Center requires no training. | Training sessions for a self-service portal are a sign that the portal is not intuitive enough. An OOTB EC portal with good search should require no training — users find it and use it within 2 minutes. If users need training to use the portal, the portal needs redesign, not training. | 'Employee Center is designed to be used without training — like Google or Amazon. If your employees can buy something on Amazon, they can submit an IT request on Employee Center. What they need is to know it exists (go-live announcement) and where to find it (intranet link). Training is for complex tools; EC is designed to be intuitive.' | One-page 'how to use EC' guide (or KB article) is appropriate for the first announcement. No classroom or video training.

## ServiceNow Mapping
05 — Adoption Measurement & Go-Live Plan — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. EC Analytics
EC Usage Analytics | Employee Center > Administration > Analytics | Submission rates, search analytics, popular items — all OOTB.
Deflection Metric | incident.knowledge_accessed | Tracks KB article views before incident submission — measure of EC-driven deflection.