## Instructions
01 — Stockrooms
HAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the stockrooms ServiceNow HAM will track at MVP — physical or logical locations where assets are received, stored, issued from, and held pending disposal. Each stockroom must have a name, tied location, owner, and type. Decisions captured here drive alm_stockroom records and the Stockroom field on alm_hardware.
Who fills this out | Customer-side: HAM Process Owner working with the Stockroom Lead and IT Operations Manager. ECS-side: Solution Architect facilitates; Process Consultant validates against ITAM principles.
When it's due | Process Decisions tab by end of Sprint 0, Week 1. Configuration Data finalized by end of Sprint 0, Week 2. Stockrooms must precede workbooks 04 (Inventory) and 06 (Assignment).
How long it takes | Approximately 2–3 hours of decisions plus 1–2 hours of data capture.
Where the data comes from | Existing inventory tools (Snipe-IT, ManageEngine, etc.), facilities records, IT operations spreadsheets, ServiceNow alm_stockroom export if any.
How to use this workbook | Work through Process Decisions first — the customer's choices drive the values that land in Configuration Data. Use the Adoption vs Re-engineering tab to defend OOTB Stockroom patterns. Once decisions are signed off, ECS lands the configuration in sub-prod and reconciles it back into the Configuration Data tab.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Stockrooms — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Stockroom granularity — single, regional, or per-site? | Per primary office + Pending Disposal stockroom. Single-site customers use one Stockroom + one Pending Disposal. Avoid per-floor or per-room stockrooms at MVP. |  | Stockroom proliferation is the #1 HAM Foundations mistake.
2 | Logical stockrooms (in-transit, repair) — include at MVP? | Yes for In-Transit (one per region) and Pending Disposal (one shared). Defer Repair until Sprint 4 unless RMA volume is significant. |  | In-Transit is essential for asset accountability during shipments.
3 | Stockroom hierarchy — flat or parent/child? | Flat at MVP. Use stockroom 'type' and 'location' for grouping. Parent/child added in HAM Realization Pack only if multi-region governance demands it. |  | Hierarchy adds reporting complexity without ITAM benefit until volume grows.
4 | Stockroom owner role — individual or group? | Individual user_id at MVP, group reference added in Realization Pack. Single owner accelerates decision-making. |  | Group ownership creates accountability gaps at MVP scale.
5 | Capacity / max occupancy tracking? | Out of scope for Foundations. Track in Realization Pack only if procurement burst events are common.
6 | Stockroom-level cost center? | Out of scope for Foundations; financial tracking is a SAM/HAM Realization concern.
7 | Self-service stockroom? (employee-pickup lockers, smart cabinets) | Out of scope for Foundations. Add as integration in Realization Pack only with named device platform.
8 | Stockroom-to-Location mapping precision? | Map to existing cmn_location records from Foundation Data Pack. Do not create new locations from this workbook. |  | Cross-pack dependency: Locations workbook (Foundation 02) must be complete first.
9 | Stockroom audit cadence — track here or in Realization? | Defer to Realization Pack workbook 07 Audits & Reconciliation.
10 | Receiving process — single-step or multi-step? | Single-step at MVP (received → in stock). Multi-step (received → inspected → in stock) deferred. |  | Drives workflow design in workbook 06.
11 | Stockroom-level RBAC — who can move assets? | Stockroom owner + members of Asset Management group from Foundation Data Pack 04. Service Desk has read-only. |  | OOTB ACLs on alm_stockroom; no custom roles.
12 | Active vs inactive stockrooms — handling decommissions? | Use 'active' field (Y/N) on alm_stockroom. Inactive stockrooms cannot receive new assets but historical records preserved.

## Dependencies
Stockrooms — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Foundation Data Pack — Locations (02) imported | In Progress | ECS
2 | Foundation Data Pack — Users (01) imported (for stockroom owners) | In Progress | ECS
3 | Foundation Data Pack — Groups (04) imported (for Asset Management group) | In Progress | ECS
4 | HAM Application activated in target instance (com.snc.itam.hardware) | Not Started | ECS
5 | Stockroom physical-walkthrough complete (count, photos, signage) | Not Started | Customer
6 | Asset Management group named with at least 2 members | Not Started | Customer
7 | Decision: which stockroom is Pending Disposal | Not Started | Customer
8 | Disposal vendor identified (or stub vendor placeholder) | Not Started | Customer

## Configuration Data
Stockrooms — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Stockroom Inventory
Total stockrooms at MVP | 5 | 3 receiving + 1 pending-disposal + 1 in-transit
Naming convention | <SITE>-<TYPE> | e.g., HQ-Receiving, HQ-Pending-Disposal, FieldOps-Truck-East
Active flag default | Y | OOTB
2. Roles & Access
Stockroom owner role | Individual user (sys_user reference) | OOTB
Asset Management group ACL | Full read/write on alm_stockroom and alm_hardware | OOTB
Service Desk ACL on alm_stockroom | Read-only | OOTB
3. Lifecycle Integration
Default stockroom on receive | <SITE>-Receiving | Per workbook 06
Pending-disposal stockroom | HQ-Pending-Disposal | Single shared stockroom
In-transit stockroom — per region | FieldOps-Truck-East, FieldOps-Truck-West
4. Reporting
OOTB Stockroom Inventory dashboard | Enabled | OOTB HAM module dashboard
Custom stockroom widgets | None at MVP

## R&R
Stockrooms — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Stockroom inventory walkthrough | C | R | Customer's Stockroom Lead conducts; ECS provides checklist.
Stockroom decisions workshop | R | C | ECS facilitates; Customer provides decision-makers.
OOTB alm_stockroom configuration | R | I | ECS configures.
Stockroom owner assignment | C | R | Customer assigns; ECS validates user references.
Stockroom data import to sub-prod | R | I | ECS executes; Customer reviews.
UAT — stockroom-related test scenarios | C | R | Customer testers; ECS provides templates.
Production cutover | R | A | ECS executes; Customer signs off.
Post-go-live ongoing stockroom administration | I | R | Customer's HAM Process Owner.

## Consultant Guide
Stockrooms — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Stockroom Foundations
Use OOTB alm_stockroom with a 'type' choice (Stockroom, In-Transit, Pending Disposal, Repair). Do not extend the table at MVP. Stockroom records reference cmn_location (set) and sys_user (owner). Assets are linked to stockrooms via alm_hardware.stockroom.
Implementation Sequence
• Activate ServiceNow HAM Application (com.snc.itam.hardware). Verify alm_stockroom, alm_hardware, alm_consumable tables present.
• Confirm Foundation Data Pack 02 Locations and 01 Users have completed import — stockrooms reference both.
• Add 'type' choice list values to alm_stockroom: Stockroom, In-Transit, Pending Disposal, Repair.
• Configure Data Policy on alm_stockroom: 'name' is mandatory and unique, 'location' is mandatory.
• Configure ACL: Asset Management group (sys_user_group) has CRUD; Service Desk has read.
• Import workbook via Import Set → Transform Map (target alm_stockroom). Validate ref-resolution before transform.
• Smoke test: list view of stockrooms, drill to one, verify owner and location resolved.
Common Pitfalls to Avoid
• Customizing alm_stockroom with extra fields at MVP — add only the type choice.
• Creating new locations via this workbook — locations must come from Foundation Pack 02.
• Assigning a group as owner — OOTB owner is a sys_user reference; force a single named owner.
• Allowing a stockroom without an owner — Data Policy must enforce.
• Mixing physical and logical stockrooms without using the type column — breaks OOTB inventory dashboards.
OOTB Features Used
• alm_stockroom (Stockroom)
• alm_hardware.stockroom (reference)
• Stockroom Inventory dashboard (OOTB HAM)
• Receiving Slip (alm_receiving_slip OOTB)
• Stock Rule (OOTB) — disabled at MVP, enabled in Realization Pack

## Adoption vs Re-engineering
Stockrooms — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We need a stockroom per floor / per closet — that's how we tracked it before." | One stockroom per primary office + Pending Disposal + per-region In-Transit (typically 5–8 total at MVP). | Stockroom proliferation creates phantom inventory: assets get 'lost' between stockrooms because no one runs reconciliation. OOTB design assumes a stockroom is a managed location with a named owner running periodic reconciliation. | "Each stockroom needs a named owner running periodic reconciliation. How many of those owners do you have? Let's match stockroom count to owner count, not to closet count." | Genuine multi-tenant facilities with separate physical security (data centers, secure govt facilities). Even then, prefer location-based filtering before splitting stockrooms.
"Group as stockroom owner so the team shares accountability." | Single sys_user as owner. Group-level access via ACL on Asset Management group. | Group ownership creates a diffusion-of-responsibility problem. ITAM audit findings disproportionately come from group-owned stockrooms because no one signs the count. | "Asset Management group still has full access via ACL. The owner column is the named person who signs the monthly count. Pick the person, then put the rest of the team in the group." | Never — this is a process discipline, not a system limitation.
"We have hierarchical stockrooms — Region → Site → Building." | Flat list at MVP. Use Location reference for hierarchy filtering. | OOTB cmn_location already supports hierarchy. Building hierarchy into alm_stockroom doubles the source of truth. | "cmn_location handles your Region/Site/Building hierarchy. Stockrooms reference Location, so all your hierarchy reporting still works. Adding hierarchy to Stockroom duplicates the data and creates drift." | Genuine federated multi-region governance with separate stockroom approval chains.
"We track stockroom capacity and reorder thresholds in our existing tool." | Out of scope for Foundations. OOTB Stock Rule (alm_stock_rule) added in Realization Pack with named SKUs and target counts. | Capacity tracking without a procurement integration generates noise. Defer to Realization where Procurement workbook (05) wires in the receive/replenish loop. | "Foundations is about visibility and control. Capacity + reorder is the next layer — let's see real receive/issue volumes for one sprint, then design Stock Rules from real data." | Mission-critical spare-parts stockrooms (e.g., dispatch fleet) where reorder lag = downtime.
"Smart-cabinet / kiosk-pickup stockroom — staff scan badges to take an asset." | Out of scope for Foundations. Realization Pack 04 IMAC Workflows includes self-pickup pattern via Service Catalog + Connected vendor integration. | Self-pickup needs a working assignment workflow before it's worth automating. Solve the workflow first, then automate it. | "Get the OOTB Receive → Assign workflow working in Sprint 1. Smart-cabinet integration is a Sprint 4 conversation when we know which device classes warrant the integration cost." | Existing customer-owned smart-cabinet integration is in production already and must be ported.

## ServiceNow Mapping
Stockrooms — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | alm_stockroom
Field mapping
Workbook column | ServiceNow field | Notes
stockroom_name | name | Required, unique.
description | description
location_name | location | Reference to cmn_location, resolved by name lookup.
type | u_stockroom_type | Choice list (Stockroom, In-Transit, Pending Disposal, Repair) — ECS adds choices if missing.
owner_user_id | u_owner | Reference to sys_user, resolved by user_name.
address_line | u_address_line | Free text.
active | active | Y → true, N → false.
notes | u_notes | Free text.
Validation & import notes
• Imported via Import Set + Transform Map.
• Validation script flags unresolved location_name and owner_user_id references before transform runs.
• Data Policy on alm_stockroom enforces 'name' unique and 'location' required.
• ACL: Asset Management group full CRUD; Service Desk read-only; everyone else no access.