## Instructions
03 — Asset Models
HAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Captures the manufacturer + model entries the customer will use to register assets in workbook 04. Each model belongs to one of the in-scope classes from workbook 02. Models drive cmdb_model records and are referenced by every alm_hardware row.
Who fills this out | Customer-side: HAM Process Owner with help from IT Procurement and the Stockroom Lead. ECS-side: Solution Architect validates manufacturer reference resolution and warranty attribute completeness.
When it's due | Process Decisions tab by end of Sprint 0, Week 1. Configuration Data + Data tab finalized by end of Sprint 0, Week 2. Depends on workbook 02 (Asset Classes).
How long it takes | Approximately 2–3 hours.
Where the data comes from | Existing procurement records, vendor catalogs, current asset spreadsheets, ManageEngine/Snipe-IT model exports.
How to use this workbook | Confirm class scope from workbook 02 first. Load only models actively in service or under active procurement. Out-of-warranty / decommissioned models can be loaded later if needed for historic reporting. Use the Adoption vs Re-engineering tab to defend OOTB cmdb_model patterns.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Asset Models — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Model scope at MVP — active only or include historic? | Active and currently-purchased models only. Add historic at first audit cycle if needed. |  | Historic-only models inflate the catalog without operational value.
2 | Manufacturer reference — reuse core_company or extend? | Reuse OOTB core_company. Add manufacturers via the model import; do not pre-populate manually.
3 | Display name standard — manufacturer-led or model-led? | "Manufacturer + Model + (key spec)" — e.g., 'Dell Latitude 7440 (14" / i7)'. Aids agent search.
4 | Warranty tracking — months, days, or end-date? | warranty_months captured here; ECS converts to OOTB warranty_duration in days.
5 | End-of-support date — required or optional? | Required for active classes. Drives Refresh Planning report in Sprint 4.
6 | Model category vs class — same thing? | Yes. Class from workbook 02 maps directly to cmdb_model.model_category.
7 | Allow multiple variants of the same model_number? | No — one model_number per manufacturer. Variants captured as u_ fields or separate display_name suffix.
8 | Track standard purchase price? | Optional at MVP, captured as u_standard_cost. Useful for Refresh Planning ROI.
9 | Refresh planning — track refresh_age_target per model? | Defer to Realization Pack workbook 02 unless a refresh wave is in flight.
10 | Image / icon per model — needed at MVP? | No. OOTB cmdb_model uses class-level icons. Custom imagery deferred.
11 | Vendor support contract reference per model? | Defer to Realization Pack — managed in Procurement workbook 05, not Models.
12 | Custom fields on cmdb_model? | u_model_year, u_end_of_support only. No other extensions at MVP.

## Dependencies
Asset Models — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 02 Asset Classes complete | In Progress | Customer
2 | Foundation Data Pack — core_company / manufacturers loaded | In Progress | ECS
3 | Procurement model list extracted from current ITAM tool | Not Started | Customer
4 | Vendor warranty terms documented per model | Not Started | Customer
5 | End-of-support dates from vendor lifecycle pages | Not Started | Customer
6 | OOTB cmdb_model table available (always present in target instance) | Complete | ECS

## Configuration Data
Asset Models — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Catalog Sizing
Total in-scope models at MVP | ~25 | Across 3 classes
Models per class — typical range | 6–10 | OOTB
2. Required Attributes
Always required | manufacturer, model_number, display_name, model_category | Data Policy on cmdb_model
Required for active models | warranty_months, end_of_support, model_year | Data Policy
3. Naming
Display name format | <Manufacturer> <Model> (<key spec>) | e.g., 'Dell Latitude 7440 (14" / i7)'
Model number format | As provided by manufacturer | Verbatim — no transformation
4. Warranty & Lifecycle
Warranty unit | Months in workbook → days in OOTB | ECS converts at transform
End-of-support source | Vendor public lifecycle pages | Customer captures; ECS does not infer
5. Custom Fields
u_model_year | Required for active models
u_end_of_support | Required for active models
u_standard_cost | Optional | For Refresh Planning ROI in Sprint 4

## R&R
Asset Models — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Model catalog scoping workshop | R | C | ECS facilitates.
Manufacturer name standardization | C | R | Customer reconciles legacy spellings.
Vendor warranty data collection | I | R | Customer's procurement team.
End-of-support data capture | C | R | Customer captures from vendor lifecycle pages.
cmdb_model import | R | I | ECS executes.
Model naming convention sign-off | C | A | Customer's HAM Process Owner.
UAT — model search + asset registration | C | R | Customer testers.
Post-go-live model additions | I | R | Customer's HAM Process Owner.

## Consultant Guide
Asset Models — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Model Foundations
cmdb_model is the master record for every model. Manufacturer references core_company. model_category links to the Asset Class from workbook 02. cmdb_model rows are referenced by alm_hardware.model in every asset record.
Implementation Sequence
• Validate Foundation Pack core_company has required manufacturers; create missing entries on transform.
• Verify model_category records exist (created from workbook 02). If not, halt — workbook 02 must complete first.
• Run validation script: confirm no duplicate manufacturer + model_number combinations.
• Build display_name where left blank: <manufacturer> <model_number>.
• Convert warranty_months to warranty_duration (days = months × 30).
• Import cmdb_model via Import Set + Transform Map.
• Smoke test: drill into one model, confirm manufacturer and model_category resolved, warranty visible.
Common Pitfalls to Avoid
• Loading hundreds of legacy models 'just in case' — they bloat search and contaminate refresh planning.
• Manufacturer name drift ('Dell' vs 'Dell Inc.' vs 'Dell Computer Corp.') — validation script catches but customer must reconcile.
• Warranty stored as days in workbook — keep months for human readability and convert at transform.
• Missing end-of-support — refresh planning depends on this.
• Adding u_ fields beyond u_model_year and u_end_of_support without documented use case.

## Adoption vs Re-engineering
Asset Models — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We need every laptop model we ever owned in the catalog for historic reporting." | Active and currently-purchased models only at MVP. Historic added at first audit cycle if needed. | Historic-only models inflate the catalog 5–10× and clutter agent search. Refresh planning gets distorted by ancient EOL models still in catalog. | "What historic reports do you actually run? If it's annual fleet aging, we cover that with the active catalog plus archived asset history. If it's audit historicals, those are query-time joins, not catalog rows." | Regulated industries with mandatory historic asset cataloguing (medical, defense).
"Custom 'spec sheet' field on every model — RAM, CPU, screen, storage as separate columns." | Spec details captured in display_name and on the asset record (cmdb_ci_computer.cpu_speed, ram, etc.) — not on the model. | Specs vary per build configuration. A 'Latitude 7440' can ship with i5/i7, 8/16/32GB RAM, etc. Locking specs at the model creates lies the moment a different config is purchased. | "Specs go on the asset record because they're per-instance. The model is the family. cmdb_ci_computer has the OOTB fields you need." | Truly identical-build models with no variants (rare in modern hardware).
"Track refresh age target per model so we can color-code the catalog by replacement urgency." | Refresh Planning report uses warranty_end and end_of_support, not a per-model age target. Realization Pack workbook 02 adds u_refresh_target_months if needed. | Per-model refresh targets become stale faster than warranty data. OOTB Refresh Planning uses the lifecycle dates that vendors publish. | "Warranty + end_of_support give you the refresh signal already. Per-model target adds maintenance burden without changing the answer." | Customer has a documented refresh-budget program tied to per-model age.
"Model image / photo on the form so users recognize their device." | Class-level icon at MVP. Per-model image deferred. | Model images require ongoing maintenance and add storage costs without operational ROI. Class icon is sufficient for OOTB workflows. | "Walk me through the operational use case. If it's user pickup confirmation, the asset_tag and serial cover that. We can add per-model images in Realization if a real workflow needs them." | Self-service stockroom kiosks where end users select models visually.

## ServiceNow Mapping
Asset Models — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | cmdb_model
Field mapping
Workbook column | ServiceNow field | Notes
class_name | model_category | Reference to cmdb_model_category from workbook 02.
manufacturer | manufacturer | Reference to core_company; created if missing.
model_number | model_number | Required.
display_name | display_name | Auto-built if blank: '<manufacturer> <model_number>'.
model_year | u_model_year
warranty_months | warranty_duration | Converted: days = months × 30.
end_of_support | u_end_of_support | ISO date.
notes | u_notes | Free text.
Validation & import notes
• Imported via Import Set + Transform Map.
• Validation flags duplicate manufacturer+model_number combos.
• Coalesce on (manufacturer, model_number) to allow re-import / updates.
• Data Policy on cmdb_model: manufacturer + model_number unique.