## Instructions
01 -- PA Scope & Dashboard Inventory
Performance Analytics Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define which OOTB Performance Analytics dashboards to activate, which audiences they serve, and the governance model for ongoing dashboard ownership.
Who fills this out | ECS Consultant leads. Customer IT Director and Process Owners confirm dashboard priorities.
Sprint window | Sprint 6 -- scope confirmed by Week 11
Estimated effort | 2-3 hours with Customer IT Director and Process Owners
Related workbooks | 02 Indicator Library · 03 Dashboard Design · 04 Scorecard Configuration · AP-20 Reporting & Stabilization
Success criteria
• | OOTB dashboard inventory agreed for go-live.
• | Dashboard owners named (one owner per dashboard).
• | Audience confirmed for each dashboard (executive, manager, agent).
• | PA license entitlement confirmed.
• | Review cadence agreed (daily, weekly, monthly per dashboard).

## Process Decisions
01 -- PA Scope & Dashboard Inventory — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which OOTB PA dashboards should be activated at go-live? | Three OOTB dashboards: ITSM Executive Overview, Incident Management, and Service Desk Performance. |  | These three cover the primary audiences (executive, manager, agent team lead) and use OOTB indicators that are already populated by ITSM data. No custom indicators needed for go-live.
2 | Should custom PA indicators be built in Sprint 6? | No custom indicators in 18-week scope. OOTB indicators only. |  | Custom indicators require data collection activation, breakdowns, and threshold configuration -- each adds sprint scope. OOTB indicators are pre-configured and immediately populated.
3 | Who owns each dashboard post-go-live? | One named owner per dashboard. Owner is responsible for monthly review and keeping widgets current. |  | Unowned dashboards become stale within 90 days. Named ownership drives accountability.
4 | Should dashboards be on a fixed refresh schedule? | Yes -- OOTB PA runs on nightly collection jobs. Executive dashboard refreshes daily; Incident and Service Desk dashboards refresh every 4 hours (OOTB default). |  | Real-time refresh is not OOTB for PA indicators. Near-real-time (every 4 hours) is the correct expectation.

## Dependencies
01 -- PA Scope & Dashboard Inventory — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | PA license confirmed (Performance Analytics Premium or included) | Required | Customer | Before Sprint 6 | PA dashboards require license entitlement.
2 | ITSM processes active (incidents, requests, changes) | Required | ECS | Sprint 4 close | PA indicators source from incident, request, and change tables.
3 | Data collection jobs activated | Required | ECS | Sprint 6 Wk 1 | PA data collection must be activated for each indicator to begin populating.

## Configuration Data
01 -- PA Scope & Dashboard Inventory — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. OOTB Dashboard Inventory
ITSM Executive Overview | Activate Sprint 6 Wk 1 | Audience: IT Director / CIO. KPIs: SLA compliance, open incidents by priority, resolution trends.
Incident Management Dashboard | Activate Sprint 6 Wk 1 | Audience: IT Manager, Service Desk Manager. KPIs: volume, MTTR, backlog, first-call resolution.
Service Desk Performance | Activate Sprint 6 Wk 1 | Audience: Service Desk Team Lead. KPIs: agent workload, reassignment rate, resolution by group.
Change Management Dashboard | Activate Sprint 6 Wk 2 (if Change is in scope) | Activate only if Change Management is active in the instance.
Custom dashboards | Defer to Phase 2 | All custom indicator and dashboard builds are post-stabilization scope.
2. Dashboard Ownership
ITSM Executive Overview owner | [Customer: IT Director name] | Must have PA Viewer role minimum
Incident Management Dashboard owner | [Customer: IT Manager name] | Must have PA Viewer role minimum
Service Desk Performance owner | [Customer: Service Desk Manager name] | Must have PA Viewer role minimum
3. Refresh & Collection
Data collection schedule | Nightly for daily indicators; every 4 hours for operational indicators (OOTB) | Do not change collection frequency in 18-week scope
Historical data backfill | OOTB PA collects from activation date forward -- no backfill | Communicate to customer: dashboards will be sparse for first 2-4 weeks

## R&R
01 -- PA Scope & Dashboard Inventory — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Confirm PA license entitlement | I | R/A | Customer IT Director.
Activate OOTB dashboards in instance | R/A | I | ECS Consultant.
Activate data collection jobs | R/A | I | ECS Consultant.
Name dashboard owners | I | R/A | Customer IT Director.
Grant PA Viewer roles to owners | R/A | Provide user list | ECS grants roles; Customer names users.
Communicate 2-4 week data ramp-up to leadership | I | R/A | Customer IT Director sets expectations.

## Consultant Guide
01 -- PA Scope & Dashboard Inventory — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Data ramp-up expectation
PA indicators collect data from the activation date forward. Dashboards will appear sparse or empty for the first 2-4 weeks. Set this expectation explicitly with the IT Director before activating. A dashboard with 2 weeks of data looks broken -- frame it as 'the meter is running, data is accumulating daily.'
Backfill workaround
If the customer needs historical context immediately: OOTB Reports can show historical data from before PA activation. Build an OOTB report for the most important executive metric (e.g., monthly incident volume for the past 6 months) and pin it alongside the PA dashboard. This bridges the ramp-up period.
Dashboard vs. report distinction
PA dashboards show trends and KPIs over time. OOTB Reports show snapshots and lists. Customers often confuse the two. Frame PA as 'the trend story' and OOTB Reports as 'the detail behind it.' Both are needed.

## Adoption vs Re-engineering
01 -- PA Scope & Dashboard Inventory — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Build us a custom executive scorecard with 20 indicators | 3 OOTB dashboards at go-live; custom scorecard in Phase 2. | 20 custom indicators require data collection activation, breakdown configuration, and threshold tuning -- each indicator adds days of scope. | Three OOTB dashboards give the IT Director, Service Desk Manager, and Team Lead exactly what they need on day 1. The data starts accumulating immediately. At the 90-day review, we have real data to design a custom scorecard around what actually matters to your leadership -- not what we guessed would matter before go-live. | Phase 2 -- after 90 days of OOTB data establishes baseline.

## ServiceNow Mapping
01 -- PA Scope & Dashboard Inventory — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Performance Analytics Core
pa_dashboard | PA Dashboard record -- OOTB dashboard configurations | pa_dashboard
pa_indicator | PA Indicator record -- each KPI metric | pa_indicator
pa_collection | Data collection job -- scheduled to run per indicator | pa_collection
PA Viewer role | pa_viewer -- grants read access to PA dashboards | sys_user_role