## Instructions
02 -- Category Classification Configuration
Predictive Intelligence Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB Category Classification PI model to predict incident category and subcategory from the short description field.
Who fills this out | ECS Architect configures. Customer Service Desk Lead reviews prediction accuracy during UAT.
Sprint window | Sprint 4 -- model active and tested by end of Week 8
Estimated effort | 4-6 hours including training run and accuracy review
Related workbooks | 01 PI Scope & Readiness · AP-CAT Service Catalog (category taxonomy)
Success criteria
• | Category Classification model trained and published.
• | Minimum 70% prediction accuracy on test set.
• | OOTB suggestions visible on Incident form for agents.
• | Confidence threshold set to 0.70.
• | Agent UAT completed -- at least 20 test incidents reviewed.

## Process Decisions
02 -- Category Classification Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which fields should PI use as input for category prediction? | Short description only (OOTB default). Do not add description body -- it adds noise and slows training. |  | Short description is the field agents complete first and it contains the most predictive signal. Description body is often templated boilerplate.
2 | Should subcategory prediction be enabled alongside category? | Yes -- enable both category and subcategory prediction in a single PI Solution. |  | OOTB supports hierarchical prediction. Training on both simultaneously is more efficient than two separate models.
3 | What happens when PI confidence is below threshold? | Suppress the suggestion -- do not show low-confidence predictions to agents. |  | Showing low-confidence predictions trains agents to distrust the system. Suppression below threshold maintains signal quality.
4 | How long does model training take? | Initial training: 2-4 hours for 5,000 records. Subsequent weekly retraining: 30-60 minutes. |  | Schedule initial training at off-peak hours. ServiceNow runs ML training jobs asynchronously -- the instance remains available during training.

## Dependencies
02 -- Category Classification Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Category taxonomy frozen (AP-CAT) | Required | ECS | Sprint 3 close | Cannot train on a changing taxonomy.
2 | 1,000+ closed incidents with non-null category | Required | Customer | Sprint 4 Wk 1 | Training data threshold.
3 | PI license active | Required | Customer | Sprint 4 Wk 1 | Cannot activate model without entitlement.

## Configuration Data
02 -- Category Classification Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. ML Solution Configuration
Solution name | ECS_Category_Classifier | Do not use spaces -- ServiceNow ML solution name is a technical identifier
Source table | incident | Train on incident table only
Input field | short_description | Primary predictive input
Output field 1 | category | Primary prediction target
Output field 2 | subcategory | Secondary prediction -- hierarchical
Training filter | state=7 (Closed) AND short_description IS NOT NULL AND category IS NOT NULL | Only clean, closed records used for training
Confidence threshold | 0.70 | Suppress suggestions below this score
Retraining schedule | Weekly -- Sunday 00:00 instance timezone | OOTB default -- do not modify
2. Accuracy Targets
Category accuracy target (go-live) | 70% on held-out test set | ServiceNow auto-splits training data 80/20 train/test
Category accuracy target (30 days) | 75% | With weekly retraining cycles
Subcategory accuracy target (go-live) | 60% | Subcategory is harder to predict -- lower initial threshold acceptable
Auto-apply threshold | 80% category accuracy sustained for 30 days | Customer decision -- ECS recommendation

## R&R
02 -- Category Classification Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Create and configure ML Solution record | R/A | I | ECS Architect.
Run initial model training | R/A | I | ECS runs; Customer IT Manager notified.
Review training accuracy results | R | A | ECS presents; Customer Service Desk Lead approves go-live.
UAT -- review 20 test incident predictions | R | A | ECS and Service Desk Lead jointly review.
Enable suggestions on Incident form | R/A | I | ECS enables; Customer confirms visibility.
Monitor weekly accuracy reports | R (first 4 weeks) | A (ongoing) | Customer PI Admin takes over after sprint close.

## Consultant Guide
02 -- Category Classification Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Training filter discipline
Always filter training data to closed incidents with non-null category AND non-null short_description. Null values in training data corrupt the model. Run the query manually before training to confirm record count and null rate.
Accuracy review with customer
When presenting accuracy results, use plain language: 'For every 10 tickets, PI correctly predicts the category 7 times.' Percentages are abstract -- incidents-per-10 is concrete. This sets honest expectations before agents start using suggestions.
Low accuracy root cause
If accuracy is below 60%: (1) check for categories with fewer than 50 training examples -- merge or exclude them. (2) Check for inconsistent category assignment in historical data -- agents may have used the wrong category. (3) Consider excluding the lowest-frequency categories from prediction scope.

## Adoption vs Re-engineering
02 -- Category Classification Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Agents are ignoring PI suggestions | Monitor acceptance rate in PI Analytics. If below 30%, run accuracy review. | Low acceptance usually means low accuracy -- agents learn quickly when suggestions are wrong. | Low acceptance is data, not a failure. We pull the PI Analytics acceptance rate report and review the most-rejected suggestions. Usually 2-3 category pairs are causing most of the rejections. We adjust the training filter to exclude ambiguous records and the acceptance rate improves within 2 retraining cycles. | If acceptance rate is below 20% after 60 days -- escalate to ServiceNow Support.

## ServiceNow Mapping
02 -- Category Classification Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. ML Solution
ml_solution | PI Solution record -- training config, schedule, status | ml_solution
ml_input_output | Input/output field mapping for the solution | ml_input_output
ml_training_run | Each training execution -- accuracy metrics logged here | ml_training_run
Incident form widget | OOTB PI suggestion widget on incident.category field | incident form layout