## Instructions
03 -- Similar Incident & Problem Intelligence
Predictive Intelligence Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB Similar Incident PI model to surface related past incidents and known errors to agents during incident resolution.
Who fills this out | ECS Architect configures. Customer Service Desk Lead and Problem Manager review during UAT.
Sprint window | Sprint 4 -- model active by end of Week 8
Estimated effort | 3-4 hours including training and UAT
Related workbooks | 01 PI Scope & Readiness · AP-13 Knowledge Management
Success criteria
• | Similar Incident model trained and suggestions visible on Incident form.
• | Similar incident panel shows top 3-5 related incidents OOTB.
• | Known error (Problem) link surfaces in similar incident results.
• | Agent UAT completed -- at least 10 test incidents reviewed.
• | Average time-to-resolution baseline recorded for 30-day comparison.

## Process Decisions
03 -- Similar Incident & Problem Intelligence — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should Similar Incident search across all incidents or just closed? | Closed incidents only (OOTB default). Open incidents may have incorrect diagnoses. |  | Searching open incidents surfaces unresolved records that may lead agents down the wrong path. Closed incidents have confirmed resolutions.
2 | How many similar incidents should be displayed? | Top 5 (OOTB default). Do not increase -- cognitive overload reduces agent usage. |  | Research shows agents engage with the first 3 results most frequently. Showing 5 provides enough options without overwhelming.
3 | Should Similar Incident link to Problem records? | Yes -- enable OOTB known error link. If a related Problem exists, it surfaces above similar incidents. |  | Known errors from Problem Management are higher quality than individual incident resolutions. OOTB links them automatically.
4 | Which fields drive similarity matching? | Short description + description (OOTB semantic similarity). Do not add custom fields. |  | OOTB semantic model uses NLP to match meaning, not just keywords. Custom fields dilute the signal.

## Dependencies
03 -- Similar Incident & Problem Intelligence — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | 1,000+ closed incidents | Required | Customer | Sprint 4 Wk 1 | Same data requirement as Category Classification.
2 | Problem Management active | Recommended | ECS | Sprint 2 close | Known error links only appear if Problem records exist with known error flag set.
3 | KB articles published (AP-13) | Recommended | ECS | Sprint 4 Wk 1 | Similar Incident can also surface KB articles -- requires published articles.

## Configuration Data
03 -- Similar Incident & Problem Intelligence — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Similar Incident ML Solution
Solution name | ECS_Similar_Incident
Source table | incident | Closed incidents only
Similarity fields | short_description, description | OOTB semantic NLP matching
Training filter | state=7 (Closed) AND short_description IS NOT NULL
Results displayed | 5 (OOTB default) | Top 5 by similarity score
Known error surfacing | Enabled -- OOTB Problem Management link | Known errors rank above similar incidents
KB article surfacing | Enabled -- requires published KB articles | Surfaces relevant KB articles alongside incidents
2. Agent Experience
Panel location | Incident form -- right column (OOTB placement) | Do not move or restyle panel
Panel header label | Similar Incidents & Known Errors (OOTB)
Resolution copy action | OOTB -- agent can copy resolution notes from similar incident with one click | Coach agents to use this to reduce typing time

## R&R
03 -- Similar Incident & Problem Intelligence — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Create and configure Similar Incident ML Solution | R/A | I | ECS Architect.
Run model training | R/A | I | ECS runs training job.
UAT -- review similar incident suggestions on test tickets | R | A | ECS + Service Desk Lead jointly.
Enable known error link in Problem Management | R/A | I | ECS enables; Problem Manager confirms.
Record resolution time baseline | R | A | ECS pulls baseline MTTR report before go-live.

## Consultant Guide
03 -- Similar Incident & Problem Intelligence — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Resolution time impact
Similar Incident is the PI feature with the fastest measurable impact. Pull MTTR (mean time to resolve) for the 30 days before go-live. At 30-day post-launch review, compare. Customers typically see 10-15% MTTR reduction from the copy-resolution action alone.
Known error setup
For the known error link to work, Problem records must have the Known Error flag checked and a Workaround field populated. If Problem Management is new, coach the Problem Manager to set these flags as they close root cause analysis.
Low relevance complaints
If agents say suggestions are not relevant, check the training filter. Common cause: incidents with boilerplate short descriptions (e.g., 'User called' or 'Please help') are polluting training data. Add a character-length filter: short_description.length > 15 to exclude one-liners.

## Adoption vs Re-engineering
03 -- Similar Incident & Problem Intelligence — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Agents do not use the similar incident panel | Track panel interaction in PI Analytics. Run 30-day champion exercise. | Low usage usually means agents are not aware the copy-resolution feature exists. | We run a 30-day champion exercise: identify 2-3 agents who use similar incidents most, have them share a before/after story with the team. Peer testimony drives adoption faster than manager instruction. We will have the data from PI Analytics to find the champions. | If usage is below 20% at 60 days -- run a 1-hour team refresher with live demos.

## ServiceNow Mapping
03 -- Similar Incident & Problem Intelligence — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. ML Solution
ml_solution (Similar Incident) | PI Solution record for semantic similarity matching | ml_solution
problem (known error) | Problem record with known_error=true and workaround populated | problem
kb_knowledge | Published KB articles surfaced alongside similar incidents | kb_knowledge