## Instructions
05 -- PI KPIs & Continuous Improvement
Predictive Intelligence Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define the KPIs, review cadence, and continuous improvement process for Predictive Intelligence post-go-live.
Who fills this out | ECS Architect sets up OOTB dashboards. Customer PI Admin owns ongoing monitoring and improvement.
Sprint window | Sprint 5 -- KPI baseline set at go-live; 30/60/90-day review cadence established
Estimated effort | 2 hours for dashboard setup and review cadence agreement
Related workbooks | 01 PI Scope · 02 Category Classification · 03 Similar Incident · 04 Assignment Intelligence · AP-19 Performance Analytics
Success criteria
• | OOTB PI Analytics dashboard accessible to Customer PI Admin.
• | KPI baseline recorded for all three models on go-live day.
• | 30/60/90-day review meetings scheduled.
• | Customer PI Admin trained on pulling and interpreting PI accuracy reports.
• | Continuous improvement process documented and handed over.

## Process Decisions
05 -- PI KPIs & Continuous Improvement — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What are the primary KPIs for Predictive Intelligence? | Category accuracy %, similar incident acceptance rate %, and first-assignment accuracy %. |  | These three metrics directly measure the value of each PI model in operational terms the help desk can understand.
2 | How often should PI performance be reviewed? | 30/60/90-day reviews with ECS during engagement. Monthly self-review by Customer PI Admin post-stabilization. |  | PI models improve continuously with retraining. Quarterly reviews catch model drift early.
3 | What triggers a model retraining review? | Any model dropping below its accuracy target for 2 consecutive weekly retraining cycles. |  | Two cycles rules out noise. A sustained drop indicates data drift or taxonomy change that requires investigation.

## Dependencies
05 -- PI KPIs & Continuous Improvement — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | All three PI models active | Required | ECS | Sprint 5 Wk 1 | Cannot measure KPIs without active models.
2 | PI Analytics access for Customer PI Admin | Required | ECS | Sprint 5 Wk 1 | Admin must have ml_analyst role.
3 | Go-live baseline date recorded | Required | ECS PM | Sprint 4 close | KPI clock starts on model activation date.

## Configuration Data
05 -- PI KPIs & Continuous Improvement — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. KPI Targets
Category Classification accuracy -- go-live | 70% | ServiceNow ML benchmark for OOTB category prediction
Category Classification accuracy -- 90 days | 80% | With 12 weekly retraining cycles
Similar Incident acceptance rate -- 30 days | 40% | % of suggestions agents click to view
Similar Incident acceptance rate -- 90 days | 55% | With agent familiarity and KB article growth
First-assignment accuracy -- go-live | 65% | Baseline improvement from pre-PI rate
First-assignment accuracy -- 90 days | 75% | With weekly retraining and agent correction feedback
2. Review Cadence
30-day review | ECS + Customer PM + PI Admin -- compare all 3 KPIs to targets | ECS schedules before Sprint 5 close
60-day review | Customer PI Admin + IT Manager -- confirm retraining schedule healthy | Customer-led; ECS advisory only
90-day review | ECS + Customer PM -- stabilization assessment; Phase 2 scope | Marks end of ECS PI obligations
Accuracy alert threshold | Any model dropping below 50% for 2 cycles -- ECS review call | ECS available during hypercare period
3. Dashboard Access
PI Analytics location | Predictive Intelligence > Analytics (OOTB) | No custom PA indicators in 18-week scope
Access role | ml_analyst (OOTB) | Customer PI Admin must have this role at go-live

## R&R
05 -- PI KPIs & Continuous Improvement — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Activate PI Analytics dashboard | R/A | Verify access | ECS enables; Customer PI Admin confirms.
Record go-live KPI baseline | R | A | ECS records all three model baselines.
30-day PI review | R | A | ECS presents; Customer PM and IT Manager review.
Monthly accuracy monitoring (ongoing) | N/A | R/A | Customer PI Admin owns post-stabilization.
Model drift investigation | R (during hypercare) | A | ECS investigates during 2-week hypercare window.

## Consultant Guide
05 -- PI KPIs & Continuous Improvement — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Framing success for the customer
Present PI results in business terms: 'Category Classification reduced mis-categorized tickets by 25%. Assignment Intelligence cut first-assignment failures from 35% to 18%.' These numbers resonate with IT leadership far more than raw accuracy percentages.
Model drift early warning
The most common cause of model drift is a taxonomy change (new category added, group renamed) without retraining. Build a checklist: any time the customer changes a category or renames a group, the affected PI model must be retrained. Add this to the Customer PI Admin runbook.
Phase 2 readiness
At the 90-day review, if all three models are above target, introduce Phase 2 PI options: (1) Predictive Fields for additional incident fields, (2) agent-level assignment, (3) PI for change request categorization. Document as Phase 2 scope items with effort estimates.

## Adoption vs Re-engineering
05 -- PI KPIs & Continuous Improvement — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
PI models are trained but nobody uses the suggestions | Monitor acceptance rates. Run champion exercise and refresher training. | Low usage in week 1 is normal -- agents are cautious. Low usage at week 6 needs investigation. | We pull the acceptance rate by agent from PI Analytics. The agents using PI most become our internal advocates. We ask them to share a time the similar incident suggestion saved them 30 minutes -- that story drives more adoption than any policy. | If acceptance below 20% at 60 days -- structured refresher training required.

## ServiceNow Mapping
05 -- PI KPIs & Continuous Improvement — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. PI Analytics
ml_analytics dashboard | OOTB PI Analytics -- accuracy, acceptance rate, suggestion volume by model | ml_analytics
ml_training_run | Training run log -- accuracy metrics per cycle | ml_training_run
ml_analyst role | Grants Customer PI Admin access to PI Analytics dashboard | sys_user_role