## Instructions
02 — Topic Design & NLU Intent Library
Virtual Agent Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define the go-live topic set, NLU intents, sample utterances, and fulfillment actions for each VA topic in Now Assist Studio.
Who fills this out | ECS Consultant drafts topic library. Customer VA Admin reviews utterances and approves conversation scripts during Sprint 5 UAT.
Sprint window | Sprint 5 — topic build and NLU training complete by end of Week 10
Estimated effort | 3-4 hours per topic (design, utterances, configure, test). 6 topics = ~1.5 days.
Related workbooks | 01 VA Scope & Channel Decisions · 03 Handoff & Escalation · AP-CAT Service Catalog · AP-13 Knowledge Management
Success criteria
• | All go-live topics built and published in Now Assist Studio.
• | Each topic has at least 10 NLU training utterances.
• | Every topic passes conversation simulator test with no unhandled fallbacks.
• | Fulfillment actions confirmed (catalog item, incident create, or KB link).
• | UAT sign-off from Customer VA Admin on all topics.

## Process Decisions
02 — Topic Design & NLU Intent Library — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Topic 1: Password Reset | OOTB Forgot Password catalog item as fulfillment — link directly to published catalog item. |  | No custom LDAP reset flow. The catalog item invokes the standard password reset process already in scope.
2 | Topic 2: Incident Create | OOTB incident record producer — VA prefills caller, category, and description. |  | Customer must confirm category/subcategory values match the agreed catalog structure (AP-CAT).
3 | Topic 3: Check Ticket Status | OOTB sys_user open incidents lookup — display last 3 open tickets with state and assignment group. |  | Read-only. No update action. Users can view their incidents without calling the help desk.
4 | Topic 4: IT Equipment Request | OOTB catalog item — Hardware Request — launched from VA panel. |  | Only items published in the Service Catalog at go-live are eligible for VA fulfillment.
5 | Topic 5: HR FAQ Deflection | KB article search → return excerpt and link — no fulfillment workflow. |  | Read-only HR knowledge deflection. HR team must publish and maintain the KB article.
6 | Topic 6: Onboarding Checklist | OOTB KB article link for new employee checklist. |  | HR team owns the article. VA links to it — no custom onboarding workflow in scope.
7 | Topics 7-15 (Phase 2) | Prioritized from 30-day unhandled intent report after go-live. |  | Data-driven expansion. Customer VA Admin pulls top-5 weekly unhandled intents to identify Phase 2 candidates.

## Dependencies
02 — Topic Design & NLU Intent Library — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Published KB articles (Topics 5, 6) | Required | Customer HR + IT | Sprint 5 Wk 1 | KB articles must be published before NLU topic testing — VA links to live articles.
2 | Published catalog items (Topics 1, 4) | Required | ECS | Sprint 5 Wk 1 | Catalog items must be published before VA fulfillment actions can be configured.
3 | Incident category list agreed (Topic 2) | Required | ECS + Customer | Sprint 5 Wk 1 | Category/subcategory list must match the agreed catalog structure (AP-CAT).
4 | Agent Workspace queue active (all topics) | Required | ECS | Sprint 5 Wk 1 | Fallback handoff on all topics requires at least one active IT queue.

## Configuration Data
02 — Topic Design & NLU Intent Library — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. NLU Standards
Utterances per intent — minimum | 10 | ServiceNow recommends 15-20; 10 is minimum viable for sprint
Utterances per intent — target | 20 | Customer VA Admin to add 5-10 utterances from real user language during UAT
NLU confidence threshold | 0.70 | Below threshold → clarification prompt, not auto-fulfillment
Clarification prompt max retries | 2 | After 2 clarification attempts, offer live-agent handoff
NLU training wait time | 2-4 hours after publishing utterances | NLU model retrains asynchronously — allow lead time before testing
2. Topic Build Order
Step 1 | Password Reset (simplest fulfillment — catalog link) | Build simplest topics first to establish NLU baseline
Step 2 | Check Ticket Status (read-only lookup) | No fulfillment action — fast to build
Step 3 | Incident Create (record producer) | Requires category list confirmed
Step 4 | Equipment Request (catalog item launch) | Requires catalog item published
Step 5 | HR FAQ Deflection (KB search) | Requires HR KB article published
Step 6 | Onboarding Checklist (KB link) | Requires onboarding KB article published
3. UAT Criteria
Conversation simulator | 100% of go-live topics must pass with no unhandled fallbacks | Use Now Assist Studio built-in conversation simulator
Live portal test — minimum flows | Password reset (end-to-end), incident create, KB deflection (HR FAQ), unrecognized input → handoff trigger | Customer VA Admin performs live tests in portal
Topic test coverage | All 6 go-live topics signed off by Customer VA Admin before publish

## R&R
02 — Topic Design & NLU Intent Library — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Define topic list and fulfillment actions | R/A | I | ECS Architect leads; Customer PM approves.
Write initial NLU utterances | R/A | I | ECS writes first 10 per intent.
Add domain-specific utterances from user language | I | R/A | Customer VA Admin adds 5-10 per intent during UAT.
Configure conversation flow panels in Studio | R/A | I | ECS configures; Customer reviews flow diagrams.
UAT — conversation simulator testing | R | A | ECS leads; Customer VA Admin signs off.
UAT — live end-to-end portal testing | I | R/A | Customer performs live portal UAT.
Approve go-live topic set | I | R/A | Customer PM sign-off required.

## Consultant Guide
02 — Topic Design & NLU Intent Library — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Build in Studio, not XML
Always build topics using Now Assist Studio UI. Importing topic XML from other instances causes NLU model mismatch errors. Even if the customer has a sandbox with existing topics, rebuild in the production instance using Studio.
Utterance diversity principle
Utterances must vary in phrasing, not just keywords. 'reset my password', 'I forgot my password', 'can't log in', 'locked out' are four distinct surface forms for the same intent. Synonyms and variations are more valuable than repeating the same phrasing.
Three OOTB fulfillment types
Now Assist Studio supports three fulfillment action types OOTB: (1) Open catalog item, (2) Create record (incident/request), (3) Search knowledge base. Do not use scripted actions or REST calls in Sprint 5 — those are Phase 2 patterns.
Unhandled intent report
After go-live, the VA Analytics > Unhandled Intents report shows what users asked that VA could not handle. Pull this weekly for the first 90 days. This is the Phase 2 topic backlog source. Coach the Customer VA Admin to review and flag candidates monthly.

## Adoption vs Re-engineering
02 — Topic Design & NLU Intent Library — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Our users talk differently — the NLU won't work | Add customer-specific utterances during UAT — OOTB NLU adapts. | OOTB NLU is pre-trained on general English business language. Customer utterances added during UAT tune it for local vocabulary. No custom model is needed. | The NLU model learns from examples — that is exactly what the UAT utterance process is for. Your VA Admin adds the phrases your team actually uses, and the model adjusts. We have done this for similar IT environments and seen 70%+ NLU accuracy after UAT tuning. | If NLU accuracy is below 60% at 90 days despite 20 utterances per intent — escalate to ServiceNow Support for NLU model review.
We need the bot to handle 20 topics at go-live | 6-topic MVP; Phase 2 data-driven expansion. | 20 topics with 10 utterances each will have low NLU accuracy. 6 topics with 20 utterances each will outperform on containment. | Quality beats quantity for NLU containment. Six well-trained topics will deflect more tickets than twenty undertrained ones. We build the Phase 2 topic backlog from real unhandled intent data — every topic added after go-live is backed by evidence. | Never — always launch with fewer, better-trained topics.

## ServiceNow Mapping
02 — Topic Design & NLU Intent Library — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Now Assist Studio
va_topic_block | Top-level topic record — one per intent group | va_topic_block
va_panel_choice | Decision panel — presents options to user | va_panel_choice
va_panel_text | Information panel — displays text response | va_panel_text
va_panel_live_agent | Handoff panel — routes to Connect Chat queue | va_panel_live_agent
2. NLU
ml_intent | NLU intent record — stores utterances | ml_intent
ml_solution | NLU solution — links topic to trained intent model | ml_solution
VA Analytics | OOTB dashboard — containment, unhandled intents, handoff rate | sn_va_analytics, va_conversation_log