## Instructions
05 -- VA Go-Live Readiness & Rollout Plan
Virtual Agent Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define the pre-launch UAT checklist, rollout approach, and communication plan for Virtual Agent go-live at the end of Sprint 6.
Who fills this out | ECS PM + Customer PM jointly complete. ECS confirms technical checklist items; Customer confirms comms and change management items.
Sprint window | Sprint 6 -- complete by end of Week 12
Estimated effort | 3-4 hours across ECS PM and Customer PM
Related workbooks | 01 VA Scope & Channel Decisions · 04 VA Analytics & Adoption Measurement · AP-15 Employee Center Go-Live
Success criteria
• | All 6 go-live topics pass UAT (simulator + live portal).
• | Agent Workspace queue active with at least 2 available agents.
• | VA Analytics dashboard accessible to Customer VA Admin.
• | Go-live communication sent to all employees 5 days before launch.
• | IT Director + ECS PM sign-off completed.
• | VA widget published to Employee Center production.

## Process Decisions
05 -- VA Go-Live Readiness & Rollout Plan — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Full launch or phased rollout? | Full employee base at go-live. No phased rollout by department. |  | VA widget is passive -- users choose to engage. No forced adoption risk. Phased rollout by department adds access control configuration with no meaningful risk reduction.
2 | When should go-live communication be sent? | IT leadership email + intranet post 5 business days before go-live. |  | 5 days gives help desk agents time to prepare and gives employees a preview. Same-day announcements reduce adoption in week 1.
3 | Should there be a pilot group? | Optional: 10-person IT team pilot 3 days before full launch. Not required. |  | Useful for customers with strong change management culture. Not required if UAT was thorough.
4 | Who signs off on go-live? | Customer IT Director + ECS PM must both sign UAT completion before widget is published. |  | Dual sign-off prevents premature publication and protects the ECS team if post-launch issues arise.
5 | What is the hypercare scope and duration? | 2 weeks post-go-live. ECS available for utterance tuning and NLU adjustments only. |  | Hypercare covers: utterance additions, NLU threshold adjustment, handoff queue corrections. New topic builds are billable Phase 2 work.

## Dependencies
05 -- VA Go-Live Readiness & Rollout Plan — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Employee Center live (AP-15) | Required | ECS | Before Sprint 6 go-live | VA widget embedded in EC -- EC must be published to production before VA launch.
2 | All 6 topics UAT passed | Required | ECS + Customer | Sprint 6 Wk 1 | Every topic must pass simulator AND live portal test before widget is published.
3 | Agent Workspace queue active | Required | ECS + Customer | Sprint 6 Wk 1 | At least 2 agents must be available during go-live week to handle handoff spikes.
4 | VA Analytics accessible | Required | ECS | Sprint 6 Wk 1 | Customer VA Admin must access analytics on Day 1.
5 | Go-live communication sent | Required | Customer comms team | 5 business days before launch | IT leadership email and intranet post must be sent before widget is published.

## Configuration Data
05 -- VA Go-Live Readiness & Rollout Plan — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Go-Live Schedule
Target go-live date | End of Sprint 6 (Week 12) | Customer to confirm -- must avoid change freeze windows
Communication send date | 5 business days before go-live | Customer IT Director sends email; comms team posts to intranet
Widget activation method | Employee Center page editor -- set VA widget Published flag to True | ECS publishes; Customer PM witnesses
2. Post-Launch Monitoring
ECS monitoring window | Daily VA Analytics review for first 5 business days | ECS flags anomalies to Customer PM within 4 business hours
Hypercare scope | Utterance tuning, NLU threshold adjustment, handoff queue corrections only | New topic builds are billable Phase 2 -- not included in hypercare
Hypercare duration | 2 weeks post-go-live | Beyond 2 weeks is T&M or support contract
30-day review | ECS + Customer PM + VA Admin -- scheduled before Sprint 6 close | Review containment vs. 15% target; agree Phase 2 backlog
3. UAT Sign-Off Checklist
Topic 1 Password Reset -- simulator pass | [ECS to initial] | No unhandled fallback in simulator
Topic 2 Incident Create -- simulator pass | [ECS to initial]
Topic 3 Check Status -- simulator pass | [ECS to initial]
Topic 4 Equipment Request -- simulator pass | [ECS to initial]
Topic 5 HR FAQ -- simulator pass | [ECS to initial]
Topic 6 Onboarding -- simulator pass | [ECS to initial]
Live portal -- password reset end-to-end | [Customer VA Admin to initial] | Must complete fulfillment in portal
Live portal -- handoff trigger confirmed | [Customer VA Admin to initial] | Unrecognized input triggers handoff offer
Agent Workspace receipt confirmed | [Customer agent to initial] | Agent receives VA transcript in Connect Chat
IT Director sign-off | [Customer IT Director signature]
ECS PM sign-off | [ECS PM signature]

## R&R
05 -- VA Go-Live Readiness & Rollout Plan — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Complete UAT sign-off checklist | R | A | ECS confirms technical; Customer IT Director signs.
Draft go-live communication | Review + edit | R/A | Customer comms team drafts; ECS reviews for accuracy.
Send IT leadership email | N/A | R/A | Customer IT Director sends.
Publish VA widget to EC production | R/A | Witness | ECS publishes; Customer PM witnesses.
Monitor analytics -- Days 1-5 | R/A | N/A | ECS daily review during hypercare.
Schedule 30-day review | R | A | ECS PM schedules before Sprint 6 close.

## Consultant Guide
05 -- VA Go-Live Readiness & Rollout Plan — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
UAT pass criteria
All 6 topics must complete end-to-end in the conversation simulator with no unhandled fallbacks. Minimum live portal tests: password reset (full fulfillment), incident create, KB deflection (HR FAQ), and unrecognized input to handoff trigger. These 4 live flows represent the highest-volume VA interaction patterns.
Widget publish risk
Publishing the VA widget is instant and affects all portal users. There is no staging preview for portal users. Do a final simulator test immediately before publishing. If possible, publish on a Tuesday or Wednesday morning (lower traffic) so the team can respond to early feedback.
Hypercare scope protection
Be explicit before go-live: hypercare covers tuning existing topics (utterances, thresholds, queue names). Building new topics is Phase 2 billable work. Log any new topic requests to the Phase 2 backlog during hypercare.
Communication content guide
The go-live email must include: (1) what VA does and does not do, (2) portal link, (3) the 6 topics it handles, (4) how to reach a live agent. Avoid overselling. Users who feel VA was oversold become hostile; users who feel it was accurately described become advocates.

## Adoption vs Re-engineering
05 -- VA Go-Live Readiness & Rollout Plan — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Launch to one department first | Full employee base on Day 1 -- VA widget is passive. | No meaningful risk difference between phased and full launch for a passive widget. Phased rollout adds access control configuration and slows adoption data collection. | The VA widget is like a help button in the portal corner -- no one is forced to use it. Full launch gives us real adoption data from day 1 across all user types. A phased rollout means we only see one department vocabulary and miss the patterns that drive Phase 2 topics. | Never for VA -- phased rollout adds configuration without meaningful risk reduction.
Delay go-live until we have 20 topics | 6 well-trained topics at go-live; expand via Phase 2. | 20 under-trained topics will produce lower containment than 6 well-trained ones. Go-live quality is about utterance coverage, not topic count. | More topics is not better if the training data is thin. Six topics with 20 utterances each will outperform twenty topics with 8 utterances each on every containment metric. We go live with what is proven and grow the library from unhandled intent data. | Never -- always prioritize topic quality over quantity at go-live.

## ServiceNow Mapping
05 -- VA Go-Live Readiness & Rollout Plan — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Go-Live Actions
Employee Center page editor | VA widget publication -- set Published flag to activate in portal | sp_page, sp_widget
VA Analytics baseline | Record first session date as go-live baseline | sn_va_analytics
2. Change Management (Optional)
Change Request | Customer may require RFC for VA widget activation -- coordinate with CAB if applicable | change_request