## Go-Live Readiness
CONNECTION - GO-LIVE READINESS CHECKLIST (go/no-go gate, Week 16)
Every Gate=Yes criterion must be Met (or have an agreed plan) before go-live. The EM compiles; the Product Owner and Executive Sponsor authorize.
# | Category | Readiness Criterion | Owner | Status | Gate (blocking?) | Evidence / Notes
1 | Configuration | All in-scope configuration stories Done and demo-accepted by the Product Owner | Solution Architect | Not Started | Yes
2 | Configuration | No open P1/P2 configuration defects | Solution Architect | Not Started | Yes
3 | Data | Foundation data loaded and validated; CMDB Health meets the agreed baseline | CMDB SME | Not Started | Yes
4 | Data | Knowledge baseline content seeded and published | Knowledge Manager | Not Started | No
5 | Integrations | AD/SSO, SCCM, Intune, and email validated in production-like environment | Integration Engineer | Not Started | Yes
6 | Integrations | Vonage CTI / Interactions validated (inbound call -> Interaction -> Incident/Request) | CTI Engineer | Not Started | Yes
7 | Testing | SIT complete with integration touchpoints validated | Technical Consultant | Not Started | Yes
8 | Testing | UAT executed; pass rate meets the agreed threshold; P1/P2 defects resolved or have an agreed plan | UAT Lead | Not Started | Yes
9 | Training & KT | Admin KT (4 sessions) delivered; Administrator Guide handed over | Solution Architect | Not Started | Yes
10 | Training & KT | Train-the-Trainer sessions delivered per process area | Process Consultant | Not Started | No
11 | Training & KT | Knowledge Transfer Package assembled and accepted | Solution Architect | Not Started | No
12 | Cutover | Cutover Runbook reviewed and approved; rollback plan ready | Solution Architect | Not Started | Yes
13 | Cutover | Cutover window scheduled and communicated; freeze in effect | Engagement Manager | Not Started | Yes
14 | Support | Hypercare support model agreed; ECS L2+ coverage confirmed for the window | Engagement Manager | Not Started | Yes
15 | Support | Connection Service Desk ready for L0-L1 intake; escalation contacts confirmed | Connection PM | Not Started | Yes
16 | Governance | All open deviations in the Triage Log dispositioned; no blocking PCRs open | Engagement Manager | Not Started | Yes
17 | Governance | Risk register has no open go-live blockers (or each has a mitigation) | Engagement Manager | Not Started | Yes
18 | Sign-offs | Product Owner acceptance of the configured platform | Product Owner | Not Started | Yes
19 | Sign-offs | Executive Sponsor go-live authorization (signed) | Executive Sponsor | Not Started | Yes
SUMMARY
Total criteria | 19
Met | 0
Blocking gates | 16
Blocking gates Met | 0
Blocking gates NOT met | 16
GO / NO-GO: GO only when all blocking gates are Met.