## Rollout Guide
CONNECTION - STAGED DOCUMENT ROLLOUT (JUST-IN-TIME)
Release each drop when its phase approaches - orientation first, then workshop material ~1 week ahead of each stage, then testing and handoff. Keeps Connection engaged and prepared without overwhelming anyone. Regenerate via _tools/build_staged_rollout.py (after the library export).
Drop | When to Send | File | Why It's In This Drop | Released On | Sent To / Notes
Drop 01 Initial Package - Now — with / just ahead of the Sprint 0 kickoff - Orientation: what the project is, how it will run, who does what, and what Connection owns. Enough to engage leadership without overwhelming anyone.
Drop 01 | Now | Connection_Client_Onboarding_Guide.docx | Start here — what to expect, the 18-week journey, governance in plain terms
Drop 01 | Now | Connection_Document_Roadmap.docx | The five-drop document roadmap — what arrives when, and why staged (JIT by design)
Drop 01 | Now | Connection_Communication_Plan.docx | Every touchpoint, owner, and cadence — plus the contact roster to complete at kickoff
Drop 01 | Now | Customer_Governance_Charter.docx | The operating model and two-key decision rights
Drop 01 | Now | Connection_Kickoff_Deck.pptx | The kickoff presentation — share after the session as the standing reference
Drop 01 | Now | Connection_Onboarding_Checklist.xlsx | The Sprint 0 plan — 19 readiness tasks with owners (ECS / Connection / Joint)
Drop 01 | Now | Connection_18Week_Project_Plan.xlsx | The overall project plan — Sprints 0-8 across four stages, Go-Live Week 16
Drop 01 | Now | Connection_Customer_Dependency_Tracker.xlsx | Connection-owned obligations (data, access, decisions) with timing and impact-if-late
Drop 01 | Now | Connection_SOW_Deliverables_Matrix.xlsx | The deliverable checklist — every SOW-committed deliverable and its status
Drop 02 Foundation and Data - Stage 1 — Sprints 1-2 (Weeks 3-6), release ~1 week before the first workshops - Platform foundation and data-model workshops plus the data-collection packs Connection fills. Pre-reads go out ahead of each session so no one walks in cold.
Drop 02 | Stage 1 | Connection_WP_01_Platform_Foundation_CLIENT.docx | Pre-read — Platform Foundation workshop
Drop 02 | Stage 1 | Connection_WP_12_CSDM_CLIENT.docx | Pre-read — CSDM workshop
Drop 02 | Stage 1 | Connection_WP_13_CMDB_CLIENT.docx | Pre-read — CMDB workshop
Drop 02 | Stage 1 | Connection_WP_14_Discovery_CLIENT.docx | Pre-read — Discovery workshop
Drop 02 | Stage 1 | Connection_WP_15_Service_Graph_Connectors_CLIENT.docx | Pre-read — Service Graph Connectors workshop
Drop 02 | Stage 1 | Post_Workshop/Connection_Platform_Foundation_Workshop.pptx | Workshop deck — release AFTER the session
Drop 02 | Stage 1 | Post_Workshop/Connection_CSDM_Workshop.pptx | Workshop deck — release AFTER the session
Drop 02 | Stage 1 | Post_Workshop/Connection_CMDB_Workshop.pptx | Workshop deck — release AFTER the session
Drop 02 | Stage 1 | Post_Workshop/Connection_Discovery_Workshop.pptx | Workshop deck — release AFTER the session
Drop 02 | Stage 1 | Post_Workshop/Connection_Service_Graph_Connectors_Workshop.pptx | Workshop deck — release AFTER the session
Drop 02 | Stage 1 | Post_Workshop/Connection_Integrations_Workshop.pptx | Workshop deck — AD/SSO, SCCM, Intune — release AFTER the session
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/00_README_Foundation_Data_Pack.docx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/01_users.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/02_locations.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/03_departments.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/04_groups.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/05_group_members.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/06_assignment_rules.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/07_schedules.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | Foundation_Accelerator_Pack/08_slas.xlsx | Data pack — users, locations, groups, SLAs (Connection fills)
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/00_README_CMDB_CSDM_Pack.docx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/01_csdm_service_taxonomy.xlsx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/02_ci_class_selection.xlsx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/03_business_service_definitions.xlsx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/04_technical_services_and_apps.xlsx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/05_service_ci_relationships.xlsx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | CMDB_CSDM_Accelerator_Pack/06_cmdb_governance_baseline.xlsx | Data pack — service taxonomy, CI classes, relationships
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/00_README_Discovery_Pack.docx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/01_discovery_scope.xlsx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/02_mid_server_config.xlsx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/03_credential_management.xlsx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/04_discovery_schedules.xlsx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/05_sgc_configuration.xlsx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Discovery_Accelerator_Pack/06_ire_reconciliation.xlsx | Data pack — discovery scope, MID servers, credentials
Drop 02 | Stage 1 | Integration_Accelerator_Pack/00_README_Integration_Pack.docx | Data pack — AD/SSO, SCCM, Intune, Vonage CTI
Drop 02 | Stage 1 | Integration_Accelerator_Pack/01_active_directory.xlsx | Data pack — AD/SSO, SCCM, Intune, Vonage CTI
Drop 02 | Stage 1 | Integration_Accelerator_Pack/02_single_sign_on.xlsx | Data pack — AD/SSO, SCCM, Intune, Vonage CTI
Drop 02 | Stage 1 | Integration_Accelerator_Pack/03_sccm.xlsx | Data pack — AD/SSO, SCCM, Intune, Vonage CTI
Drop 02 | Stage 1 | Integration_Accelerator_Pack/04_intune.xlsx | Data pack — AD/SSO, SCCM, Intune, Vonage CTI
Drop 02 | Stage 1 | Integration_Accelerator_Pack/05_vonage_cti_interactions.xlsx | Data pack — AD/SSO, SCCM, Intune, Vonage CTI
Drop 02 | Stage 1 | Connection_RACI_Matrix.xlsx | Who owns what, by deliverable — baseline for the working rhythm
Drop 03 ITSM Core - Stage 2 — Sprints 3-4 (Weeks 7-10), release ~1 week before the ITSM workshops - The ITSM Core build: Incident, Major Incident, Problem, Change, and Service Catalog workshops with their pre-reads and process-decision packs.
Drop 03 | Stage 2 | Connection_WP_02_Incident_Management_CLIENT.docx | Pre-read — Incident Management workshop
Drop 03 | Stage 2 | Connection_WP_03_Major_Incident_Management_CLIENT.docx | Pre-read — Major Incident Management workshop
Drop 03 | Stage 2 | Connection_WP_04_Problem_Management_CLIENT.docx | Pre-read — Problem Management workshop
Drop 03 | Stage 2 | Connection_WP_05_Change_Management_CLIENT.docx | Pre-read — Change Management workshop
Drop 03 | Stage 2 | Connection_WP_06_Service_Catalog_Request_CLIENT.docx | Pre-read — Service Catalog & Request workshop
Drop 03 | Stage 2 | Post_Workshop/Connection_Incident_Workshop.pptx | Workshop deck — release AFTER the session
Drop 03 | Stage 2 | Post_Workshop/Connection_Major_Incident_Workshop.pptx | Workshop deck — release AFTER the session
Drop 03 | Stage 2 | Post_Workshop/Connection_Problem_Workshop.pptx | Workshop deck — release AFTER the session
Drop 03 | Stage 2 | Post_Workshop/Connection_Change_Workshop.pptx | Workshop deck — modernized Change + CAB Workbench — release AFTER the session
Drop 03 | Stage 2 | Post_Workshop/Connection_Service_Catalog_Workshop.pptx | Workshop deck — release AFTER the session
Drop 03 | Stage 2 | Post_Workshop/Connection_Interactions_Vonage_CTI_Workshop.pptx | Workshop deck — inbound voice via Vonage CTI — release AFTER the session
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/00_README_ITSM_Process_Pack.docx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/01_incident_management.xlsx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/02_major_incident_management.xlsx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/03_problem_management.xlsx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/04_change_management.xlsx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/05_service_request_management.xlsx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | ITSM_Accelerator_Pack/06_knowledge_management.xlsx | Process pack — incident, MIM, problem, change, request, knowledge decisions
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/00_README_Service_Catalog_Pack.docx | Data pack — category rationalization, item inventory, approvals
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/01_category_rationalization.xlsx | Data pack — category rationalization, item inventory, approvals
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/02_catalog_item_inventory.xlsx | Data pack — category rationalization, item inventory, approvals
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/03_item_template_standards.xlsx | Data pack — category rationalization, item inventory, approvals
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/04_fulfillment_workflow_decisions.xlsx | Data pack — category rationalization, item inventory, approvals
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/05_approval_matrix.xlsx | Data pack — category rationalization, item inventory, approvals
Drop 03 | Stage 2 | Service_Catalog_Accelerator_Pack/06_catalog_item_config_data.xlsx | Data pack — category rationalization, item inventory, approvals
Drop 04 Employee Experience and Analytics - Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops - The employee-experience and analytics build: Employee Center, Virtual Agent, Knowledge, Predictive Intelligence, Performance Analytics, and HAM foundations.
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Connection_WP_07_Knowledge_Management_CLIENT.docx | Pre-read — Knowledge Management workshop
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Connection_WP_08_Employee_Center_CLIENT.docx | Pre-read — Employee Center workshop
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Connection_WP_09_Virtual_Agent_CLIENT.docx | Pre-read — Virtual Agent workshop
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Connection_WP_10_Predictive_Intelligence_CLIENT.docx | Pre-read — Predictive Intelligence workshop
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Connection_WP_16_Hardware_Asset_Management_CLIENT.docx | Pre-read — HAM foundations workshop
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Post_Workshop/Connection_Knowledge_Workshop.pptx | Workshop deck — release AFTER the session
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Post_Workshop/Connection_Employee_Center_Workshop.pptx | Workshop deck — release AFTER the session
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Post_Workshop/Connection_Virtual_Agent_Workshop.pptx | Workshop deck — 5 baseline topics + AI Search — release AFTER the session
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Post_Workshop/Connection_Predictive_Intelligence_Workshop.pptx | Workshop deck — release AFTER the session
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Post_Workshop/Connection_Performance_Analytics_Workshop.pptx | Workshop deck — release AFTER the session
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Post_Workshop/Connection_HAM_Workshop.pptx | Workshop deck — stockrooms + HAM foundations — release AFTER the session
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/00_README_Knowledge_Pack.docx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/01_kb_structure.xlsx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/02_article_template_standards.xlsx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/03_access_controls.xlsx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/04_article_workflow.xlsx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/05_search_optimization.xlsx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Knowledge_Accelerator_Pack/06_knowledge_kpis.xlsx | Data pack — KB structure, article standards, workflow
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Employee_Center_Accelerator_Pack/00_README_Employee_Center_Pack.docx | Data pack — portal design, taxonomy, search
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Employee_Center_Accelerator_Pack/01_ec_portal_design.xlsx | Data pack — portal design, taxonomy, search
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Employee_Center_Accelerator_Pack/02_topic_taxonomy.xlsx | Data pack — portal design, taxonomy, search
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Employee_Center_Accelerator_Pack/03_homepage_layout.xlsx | Data pack — portal design, taxonomy, search
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Employee_Center_Accelerator_Pack/04_search_configuration.xlsx | Data pack — portal design, taxonomy, search
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Employee_Center_Accelerator_Pack/05_adoption_measurement.xlsx | Data pack — portal design, taxonomy, search
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Virtual_Agent_Accelerator_Pack/00_README_Virtual_Agent_Pack.docx | Data pack — topic design, handoff, go-live readiness
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Virtual_Agent_Accelerator_Pack/01_va_scope_channel.xlsx | Data pack — topic design, handoff, go-live readiness
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Virtual_Agent_Accelerator_Pack/02_topic_design_nlu.xlsx | Data pack — topic design, handoff, go-live readiness
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Virtual_Agent_Accelerator_Pack/03_handoff_escalation.xlsx | Data pack — topic design, handoff, go-live readiness
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Virtual_Agent_Accelerator_Pack/04_va_analytics.xlsx | Data pack — topic design, handoff, go-live readiness
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Virtual_Agent_Accelerator_Pack/05_golive_readiness.xlsx | Data pack — topic design, handoff, go-live readiness
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Predictive_Intelligence_Accelerator_Pack/00_README_Predictive_Intelligence_Pack.docx | Data pack — scope, classification, assignment intelligence
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Predictive_Intelligence_Accelerator_Pack/01_pi_scope_readiness.xlsx | Data pack — scope, classification, assignment intelligence
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Predictive_Intelligence_Accelerator_Pack/02_category_classification.xlsx | Data pack — scope, classification, assignment intelligence
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Predictive_Intelligence_Accelerator_Pack/03_similar_incident.xlsx | Data pack — scope, classification, assignment intelligence
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Predictive_Intelligence_Accelerator_Pack/04_assignment_intelligence.xlsx | Data pack — scope, classification, assignment intelligence
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Predictive_Intelligence_Accelerator_Pack/05_pi_kpis.xlsx | Data pack — scope, classification, assignment intelligence
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Performance_Analytics_Accelerator_Pack/00_README_Performance_Analytics_Pack.docx | Data pack — dashboards, indicators, scorecards
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Performance_Analytics_Accelerator_Pack/01_pa_scope_dashboard_inventory.xlsx | Data pack — dashboards, indicators, scorecards
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Performance_Analytics_Accelerator_Pack/02_ootb_indicator_library.xlsx | Data pack — dashboards, indicators, scorecards
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Performance_Analytics_Accelerator_Pack/03_dashboard_design.xlsx | Data pack — dashboards, indicators, scorecards
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Performance_Analytics_Accelerator_Pack/04_scorecard_configuration.xlsx | Data pack — dashboards, indicators, scorecards
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | Performance_Analytics_Accelerator_Pack/05_pa_governance.xlsx | Data pack — dashboards, indicators, scorecards
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/00_README_HAM_Foundations_Pack.docx | Data pack — stockrooms, asset classes, lifecycle
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/01_stockrooms.xlsx | Data pack — stockrooms, asset classes, lifecycle
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/02_asset_classes_baseline.xlsx | Data pack — stockrooms, asset classes, lifecycle
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/03_asset_models.xlsx | Data pack — stockrooms, asset classes, lifecycle
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/04_initial_inventory.xlsx | Data pack — stockrooms, asset classes, lifecycle
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/05_lifecycle_states_baseline.xlsx | Data pack — stockrooms, asset classes, lifecycle
Drop 04 | Sprints 5-6 (Weeks 11-14), release ~1 week before the experience workshops | ITAM_HAM_Foundations_Accelerator_Pack/06_assignment_and_receiving.xlsx | Data pack — stockrooms, asset classes, lifecycle
Drop 05 Testing GoLive and Handoff - Stage 3-4 — Sprints 6-8 (Weeks 13-18), release as UAT scheduling begins - Everything Connection needs to test, approve go-live, and take ownership: UAT material, the gated go/no-go checklist, cutover plan, and knowledge-transfer package.
Drop 05 | Stage 3-4 | Connection_UAT_Guidebook_for_End_Users.docx | How to test, step by step — written for first-time testers
Drop 05 | Stage 3-4 | Connection_UAT_End_to_End_Test_Scripts.xlsx | 18 end-to-end scripts across 10 suites, traced to stories, with defect log
Drop 05 | Stage 3-4 | Connection_Go_Live_Readiness_Checklist.xlsx | The gated go/no-go criteria reviewed jointly before cutover
Drop 05 | Stage 3-4 | Connection_Cutover_Runbook.docx | Cutover sequence, validation points, rollback plan
Drop 05 | Stage 3-4 | Connection_Administrator_Guide_and_KT.docx | Run the platform — admin reference + 4-session KT plan
Drop 05 | Stage 3-4 | Connection_Train_the_Trainer_Toolkit.docx | Enable Connection trainers ahead of go-live
Drop 05 | Stage 3-4 | Connection_Operational_Handoff_Pack.docx | Ownership, support model, and escalation after Hypercare