## Sprint Capacity
CONNECTION - SPRINT PLAN & CAPACITY MODEL
Load = story points planned per sprint (config + delivery backlog). Set Capacity (pts) per sprint from team velocity; the model flags over-loaded sprints. Adjust scope/sequence before a sprint goes red.
Sprint | Stage | Config Load (pts) | Delivery Load (pts) | Total Load (pts) | Capacity (pts) | Load vs Capacity | Status
Sprint 0 | Stage 1 | 0 | 24 |  | 15
Sprint 1 | Stage 1 | 53 | 4 |  | 30
Sprint 2 | Stage 1 | 42 | 10 |  | 30
Sprint 3 | Stage 2 | 78 | 4 |  | 30
Sprint 4 | Stage 2 | 81 | 9 |  | 30
Sprint 5 | Stage 2 | 68 | 6 |  | 30
Sprint 6 | Stage 3 | 33 | 14 |  | 30
Sprint 7 | Stage 3 | 0 | 26 |  | 30
Sprint 8 | Stage 4 | 0 | 11 |  | 15
Ongoing / All | All | 0 | 23 |  | 0
TOTAL
Capacity (blue) is editable: set from team size x velocity. OVER = load exceeds capacity (rebalance); TIGHT = >85%.