EVERFORTH CONSULTING SERVICES

Statement of Work — Reference Language

Scope Classification Definitions: Defect · Enhancement · Missed Requirement

# 1. Purpose

This document establishes agreed-upon contractual definitions for three categories of scope-related findings that may arise during the delivery of a ServiceNow Out-of-the-Box (OOTB) engagement. The intent is to create a shared, unambiguous framework that protects both Everforth Consulting Services (ECS) and the Customer from misaligned expectations, scope creep, and delivery disputes.

These definitions are intended to be incorporated by reference into the project Statement of Work (SOW) and apply to all sprints, workstreams, and deliverables within the engagement.

# 2. Guiding Principles

The following principles underpin how scope classification decisions are made:

- Approved design documentation — including Sprint Workbooks, Design Decision Records, and Configuration Worksheets — serves as the binding record of what was agreed and in scope.

- The OOTB-first commitment means ECS will not introduce custom code to resolve scope gaps unless a formal change order is approved.

- Classification decisions are made jointly by the ECS Delivery Manager and the Customer Sponsor, with escalation to the ECS Practice Manager when parties cannot agree.

- No classification decision should be used to shield either party from accountability for honest documentation failures during scoping.

# 3. Definitions

| 3.1 DEFECT |  |
| --- | --- |
| Definition A Defect is any condition in which a delivered configuration or feature does not perform as documented in the approved design documentation, or where a standard ServiceNow OOTB capability fails to operate as described in ServiceNow’s published platform documentation, with no customer-specific configuration as the root cause. |  |
| Qualifying Criteria | - The behavior contradicts an explicit, approved design decision or sprint workbook entry. - The OOTB platform feature operates contrary to ServiceNow’s published documentation for the current licensed instance version. - The issue is reproducible and not caused by customer environment factors (e.g., network, browser, unsupported integration). - No approved change to scope or design has altered the expected behavior. |
| Examples | - An assignment rule documented in the Sprint 2 Workbook does not fire for the agreed triggering condition. - A Virtual Agent topic approved in the design returns an error on a standard conversation path. - An SLA definition, configured per approved design, fails to apply to the correct record type. - A Predictive Intelligence model trained on agreed data fields produces no predictions after go-live. |
| ECS Responsibility | ECS will remediate confirmed Defects at no additional cost to the Customer. Remediation timelines will be governed by the severity classification in the project’s escalation and issue management process. |
| Customer Responsibility | The Customer must submit a documented defect report with reproducible steps. ECS reserves the right to reclassify a reported Defect as an Enhancement or Missed Requirement if investigation reveals the expectation was not documented in approved design artifacts. |
| Not a Defect if… | - The customer’s expectation was never documented in approved design artifacts. - The request reflects a preference change from an approved decision. - The behavior is a result of an OOTB platform limitation acknowledged during design. |

| 3.2 ENHANCEMENT |  |
| --- | --- |
| Definition An Enhancement is any request to add, expand, or modify functionality, configuration, or behavior that was not included in the agreed-upon project scope, as defined by the executed SOW, approved Sprint Workbooks, and accepted Design Decision Records. Enhancements represent new value beyond the contracted engagement. |  |
| Qualifying Criteria | - The requested feature, field, workflow step, automation, or report was not described or implied in the SOW or design documentation. - The Customer or stakeholder has changed their mind on a previously approved design decision. - A new integration, data source, or system dependency is introduced after scoping. - The request increases the complexity, effort, or duration of a workstream beyond what was planned. |
| Examples | - After approving a three-state incident lifecycle, the customer requests a fourth “Pending Vendor” state. - A new approval workflow is requested for a catalog item that was scoped without approvals. - The customer requests integration with a third-party ITSM tool not mentioned in the SOW. - Additional Virtual Agent topics are requested beyond the agreed topic count or list. - A custom report or dashboard is requested that was not included in the reporting scope. |
| ECS Responsibility | ECS will evaluate the Enhancement request, provide an estimate of effort and cost, and present a formal Change Order for Customer approval. Work will not begin until a signed Change Order is in place. |
| Customer Responsibility | The Customer Sponsor must formally request the Enhancement in writing. Verbal requests or informal communications do not initiate the Enhancement process. The Customer acknowledges that Enhancement requests may impact project timeline and budget. |
| Not an Enhancement if… | - The request corrects a Defect against agreed design documentation. - The request addresses a functional need that was clearly implied by the SOW scope but accidentally omitted from documentation (see Missed Requirement). |

| 3.3 MISSED REQUIREMENT |  |
| --- | --- |
| Definition A Missed Requirement is a functional need that was not captured during the scoping, discovery, or Sprint 0 process, is not represented in the executed SOW or approved design documentation, and is identified after delivery has begun. Unlike an Enhancement, a Missed Requirement reflects an omission rather than a change in desire — the Customer needed this outcome from the beginning but it was not surfaced or documented. |  |
| Qualifying Criteria | - The requirement is core to a process that was in-scope but the specific need was not documented. - Neither ECS nor the Customer raised the requirement during discovery, workshops, or Sprint 0. - The requirement does not reflect a new desire or preference change, but an oversight by either or both parties. - Delivery of the agreed scope without this requirement would leave the process functionally incomplete. |
| Examples | - An incident assignment group was in scope but the escalation path to a secondary group was never discussed or documented. - A catalog item was scoped for fulfillment but the notification to the fulfiller was not documented and not configured. - The CMDB class model was approved but a critical CI relationship type was not included in any discovery conversation. |
| Accountability Framework | Missed Requirements are evaluated on a case-by-case basis using the following factors: - Discovery ownership: Was the requirement within ECS’s responsibility to surface, or the Customer’s? - Documentation gap: Did ECS’s design artifacts fail to capture something that was discussed? - Materiality: Is this a minor omission or a significant functional gap? - Timing: At what point in the delivery cycle was this identified? ECS and the Customer Sponsor will jointly determine the appropriate resolution path, which may include absorbing the work, negotiating a partial Change Order, or prioritizing the requirement in a future sprint or engagement phase. |
| ECS Responsibility | ECS acknowledges that thorough discovery and documentation is a core delivery obligation. Where a Missed Requirement is attributable to an ECS-side documentation failure, ECS will work in good faith to resolve the gap with minimal or no cost impact to the Customer, subject to scope materiality. |
| Customer Responsibility | The Customer is responsible for ensuring that subject matter experts participate in discovery and Sprint 0 activities and that key stakeholders review and approve design documentation. Missed Requirements that arise from lack of Customer participation in scoping activities may be treated as Enhancements. |
| Not a Missed Req. if… | - The requirement was raised and explicitly descoped during discovery. - The requirement reflects a new capability the Customer has decided they want (see Enhancement). - The requirement was documented but the configuration has a defect (see Defect). |

# 4. Scope Classification Decision Matrix

The following matrix provides guidance on how to classify common scenarios. When a scenario falls into a gray area, the ECS Delivery Manager and Customer Sponsor should review the qualifying criteria in Section 3 and escalate if alignment cannot be reached.

| Scenario | Defect | Enhancement | Missed Req. |
| --- | --- | --- | --- |
| Documented design is not working as agreed | ✓ Yes | — | — |
| OOTB ServiceNow feature behaves unexpectedly vs. platform docs | ✓ Yes | — | — |
| Customer wants additional fields, workflow steps, or automation not in scope | — | ✓ Yes | — |
| Customer requests a new integration not in the SOW | — | ✓ Yes | — |
| A functional need was never raised in discovery or Sprint 0 | — | — | ✓ Yes |
| Scope document omitted a process the customer assumed was included | — | — | ✓ Yes |
| Customer changes their mind on an approved design decision | — | ✓ Yes | — |
| An OOTB limitation prevents agreed outcome — workaround required | Case-by-case | Possible | Possible |

# 5. Classification & Escalation Process

## Step 1 — Submission

Either party may raise a scope classification question at any time by submitting a written description of the finding to the ECS Delivery Manager. Verbal or informal submissions do not initiate the formal process.

## Step 2 — Initial Assessment (5 Business Days)

The ECS Delivery Manager will review the submission against approved design documentation and issue an initial classification within five (5) business days. The classification will specify the rationale and reference the relevant design artifacts.

## Step 3 — Customer Review

The Customer Sponsor has five (5) business days to accept, dispute, or request a joint working session on the classification. Silence after five business days constitutes acceptance.

## Step 4 — Escalation

If the parties cannot reach agreement, the matter is escalated to the ECS Practice Manager and the Customer’s designated executive sponsor within three (3) business days. A resolution will be sought within ten (10) business days of escalation.

## Step 5 — Documentation

All classification decisions are documented in the project Issue Log and, where applicable, reflected in a formal Change Order or design amendment. Classifications that result in no-cost remediation are documented as Defect resolutions in the sprint workbook.

# 6. Recommended SOW Incorporation Language

The following paragraph is recommended for inclusion in the project SOW under a “Scope Management” or “Change Control” section:

Scope Classification. The parties agree that all scope-related findings during delivery will be classified as one of the following: (a) a Defect, meaning a delivered configuration that does not perform as documented in approved design artifacts or that contradicts ServiceNow’s published platform documentation; (b) an Enhancement, meaning a request to add or modify functionality not described in this SOW or in approved design documentation; or (c) a Missed Requirement, meaning a functional need not captured during discovery or Sprint 0 that was not surfaced by either party. Defects will be remediated by ECS at no additional charge. Enhancements require a signed Change Order prior to commencement of work. Missed Requirements will be evaluated jointly by the parties on a case-by-case basis according to the Scope Classification Definitions document incorporated herein by reference.

# 7. Document Control

| Document Title | Scope Classification Definitions — SOW Reference Language |
| --- | --- |
| Version | 1.0 — Draft for Review |
| Owner | ECS Practice Management |
| Status | Internal Review |
| Last Updated | May 2025 |
| Next Review | Prior to each engagement SOW execution |