CLIENT · STATEMENT OF WORK

ServiceNow Architecture Services

Statement of Work

High Availability Environment Rebuild — Electric Boat / General Dynamics

ECS Federal · ServiceNow Practice

Audience: Unisys · Electric Boat (General Dynamics)

Companion to: Unisys – Electric Boat ServiceNow Support Services SOW (O&M)

Document ID: SOW-EB-001     ·     Version: 1.0     ·     Status: Draft

Internal Use Only · Confidential

# 1.  Executive Overview

Everforth ECS Federal ((ECS)) is engaged as a subcontractor to Unisys in support of Unisys's prime contract with Electric Boat (EB), a subsidiary of General Dynamics. As part of that engagement, Electric Boat operates an on-premise installation of ServiceNow that Unisys is contractually obligated to manage and maintain.

The current ServiceNow environment lacks sufficient compute capacity—processing power and RAM—and has no reliability redundancy across its environment tiers. This creates operational risk and, under the terms of Unisys's contract renewal with Electric Boat, now creates a contractual compliance risk: EB's renewed contract requires 99.99% uptime (fewer than 53 minutes of downtime per year across all tiers).

This Statement of Work defines the services ECS will perform to design, build, and migrate Electric Boat's ServiceNow environment to a new, high-availability architecture across all tiers (PROD, UAT, and DEV), spanning two data centers with global load balancing, RaptorDB Professional database infrastructure, and automated database failover. Post-migration operational support is governed under a separate Unisys–Electric Boat ServiceNow Support Services agreement and is explicitly outside the scope of this engagement.

# 2.  Requested Architecture

The following architecture has been specified by Unisys and Electric Boat to meet the 99.99% uptime contractual requirement. ECS will deliver against these specifications across three environment tiers.

## PROD Environment

Expand application node hosts by two (2) in PROD

Final configuration: two (2) application servers in DataCenter 1 and two (2) application servers in DataCenter 2, providing both single-site and cross-site high availability

Leverage Global Server Load Balancing (GSLB) on F5s for application nodes

GSLB provides a VIP in each data center, managing traffic in an active/passive fashion to deliver single-site and cross-site high availability

Migrate MariaDB to RaptorDB, targeting RaptorDB Professional

Database placement: Primary, Replica, and Witness servers in DataCenter 1; two (2) Replica servers in DataCenter 2 — providing both single-site and cross-site HA

Leverage GSLB on F5s for database tier

Implement automated high availability for databases beyond simple replication, per ServiceNow KB2407699 — using repmgr or Patroni (Distributed Configuration Store)

Two (2) Predictive Intelligence Servers — listed as an optional line item

## UAT Environment

Expand application node hosts by one (1) in UAT

Final configuration: two (2) application servers in DataCenter 1 and two (2) application servers in DataCenter 2

Leverage GSLB on F5s for application nodes — active/passive VIP per data center

Provides cross-site high availability

Migrate MariaDB to RaptorDB, targeting RaptorDB Professional

Database placement: Primary and Witness servers in DataCenter 1; one (1) Replica server in DataCenter 2

Leverage GSLB on F5s for database tier

Implement automated high availability for databases per ServiceNow KB2407699 (repmgr or Patroni)

Two (2) Predictive Intelligence Servers

## DEV Environment

Migrate MariaDB to RaptorDB, targeting RaptorDB Professional

Database placement: Primary server in DataCenter 1. No replicas.

Two (2) Predictive Intelligence Servers — optional line item

## Architectural Overview

The combined architecture delivers three tiers of availability protection: in-site high availability within each data center, cross-site high availability across DataCenter 1 and DataCenter 2, and cold/warm-site disaster recovery capability. F5 GSLB is the traffic management layer for both application and database tiers. RaptorDB Professional with repmgr or Patroni provides automated database failover that exceeds the capability of simple replication, satisfying the uptime requirement without reliance on manual intervention.

Target Uptime SLA: 99.99% — fewer than 53 minutes of unplanned downtime per year. This is a contractual commitment between Unisys and Electric Boat. This architecture is designed to meet that requirement.

# 3.  Scope of Services

ECS will provide the following services under this Statement of Work. All work will be performed remotely unless travel is explicitly requested and approved in writing by Unisys.

## Architecture Design and Documentation

Document the current-state ServiceNow architecture across all environment tiers

Design the target-state high availability architecture in alignment with the specifications in Section 2

Produce architecture diagrams and supporting documentation for Unisys and EB review and approval prior to build

Identify and document required infrastructure dependencies (F5, server provisioning, network)

## Environment Build — DEV, UAT, PROD

Build new ServiceNow environments in the specified sequence: DEV first, UAT second, PROD last

Configure RaptorDB Professional across all tiers per the architecture specification

Coordinate with EB infrastructure teams on F5 GSLB configuration

Configure repmgr or Patroni for automated database high availability per ServiceNow KB2407699 guidance

Configure application node distribution across DataCenter 1 and DataCenter 2

Install and configure Predictive Intelligence servers (optional — if authorized)

## Testing

Unit and integration testing throughout the build of each environment tier

Failover testing — simulated single-site and cross-site failure scenarios

Performance validation — confirm resource capacity meets current load and projected growth

Coordinate User Acceptance Testing (UAT) with EB stakeholders prior to PROD migration

## Migration

Develop and document a migration plan for each environment tier

Execute migration from legacy environment to new architecture

Coordinate Change Advisory Board (CAB) approval through Unisys and EB change management process prior to PROD migration execution

Validate post-migration system health across all tiers

Confirm go-live readiness with Unisys and EB stakeholders

## Project Management and Communication

Provide weekly status reports to Unisys

Maintain a project schedule and issue/risk log

Facilitate regular coordination calls with Unisys and EB stakeholders

Manage ECS internal team coordination, task assignment, and quality assurance throughout the engagement

## Out of Scope

Ongoing operational support and managed services — governed under the separate Unisys–Electric Boat ServiceNow Support Services agreement

ServiceNow platform licensing — Electric Boat's responsibility as the licensed customer

Physical infrastructure provisioning (servers, networking equipment, data center facilities) — Electric Boat's responsibility

Travel costs — excluded unless requested and approved in writing by Unisys

Customization or functional configuration of ServiceNow modules beyond the architecture scope

# 4.  Project Approach and Timeline

This engagement is planned for fourteen (14) weeks, with a ceiling of sixteen (16) weeks to accommodate infrastructure provisioning dependencies outside ECS's control. The sequencing prioritizes DEV first to validate the build approach before applying it to UAT and PROD.

## Month 1 — Discovery, Architecture, and Preparation (Weeks 1–4)

Conduct project kickoff with Unisys and EB stakeholders

Identify and confirm SME contacts, points of contact, and escalation paths

Document current-state architecture across PROD, UAT, and DEV

Design and document target-state architecture; obtain Unisys and EB approval

Verify and validate access to all required environments and infrastructure

Coordinate with EB to confirm server provisioning timelines and F5 access

Initiate the Unisys/EB Change Management process for planned environment work

Prepare detailed build runbooks for each environment tier

## Month 2 — Environment Build (Weeks 5–10)

Build DEV environment first: RaptorDB migration, PI server configuration, validation

Build UAT environment: app node expansion, RaptorDB, GSLB configuration, F5 coordination

Conduct integration and failover testing in DEV and UAT

Coordinate UAT sign-off with EB stakeholders

Begin PROD environment build in parallel with UAT validation

Ongoing status reporting and stakeholder coordination throughout

## Month 3 — PROD Finalization, Migration, and Go-Live (Weeks 11–14)

Finalize PROD environment build and testing

Conduct PROD failover and performance validation

Develop and review detailed migration plan with Unisys and EB

Obtain CAB approval for production migration through Unisys/EB change process

Execute production migration during approved change window

Validate post-migration system health and confirm 99.99% uptime architecture is operational

Conduct project closeout with Unisys and EB; transfer documentation package

# 5.  Roles and Responsibilities

## Everforth ECS Federal

ECS is responsible for delivery of all services defined in Section 3, including:

All architecture design, build, testing, and migration activities

Project management, scheduling, status reporting, and internal team coordination

Documentation of architecture, migration plans, and test results

Coordination with Unisys on change management, escalations, and contract-level decisions

Technical quality assurance across all environment tiers

## Unisys

As the prime contractor, Unisys is responsible for:

Contract and relationship management with Electric Boat — ECS escalates to Unisys for all customer-level decisions and approvals

Coordination of EB stakeholder and SME availability for architecture review, testing, and go-live

Escalation of issues requiring EB action (infrastructure provisioning, change approvals, access requests)

Review and approval of ECS status reports, architecture documentation, and migration plans

Contractual coordination of the Unisys/EB change management process

## Electric Boat / General Dynamics

Electric Boat is responsible for infrastructure ownership and organizational coordination, including:

Timely provisioning of servers, network infrastructure, and data center resources required to support the build timeline

F5 configuration support — EB infrastructure teams own the F5 appliances and must coordinate GSLB configuration with ECS

SME availability for architecture review, UAT sign-off, and migration go-live approval

CAB process — Electric Boat's change advisory process governs all PROD environment changes

ServiceNow platform licensing and license management

# 6.  Project Resources

ECS will staff the following roles for the duration of this engagement. All resources are remote unless otherwise agreed.

| Role | Responsibilities |
| --- | --- |
| Engagement Manager | Project management, scheduling, stakeholder communication, status reporting, risk and issue management, ECS team coordination |
| Business Analyst(s) | Architecture documentation, testing coordination, requirements capture, migration plan documentation, general BA support |
| Platform Architect | Lead architect responsible for target-state design, build execution, RaptorDB and GSLB configuration, failover design and validation |
| Developer | General configuration support, build assistance, peer testing, post-migration validation support |

# 7.  Dependencies

The following dependencies are outside ECS's direct control and represent the primary schedule risk for this engagement. ECS will flag these early and track them throughout.

Infrastructure provisioning timeline — server provisioning and data center readiness are owned by Electric Boat. Delays in provisioning will directly impact the build schedule.

F5 GSLB configuration — Electric Boat's infrastructure team must be available and responsive to support F5 configuration in both data centers.

SME availability — EB subject matter experts must be available for architecture review, UAT validation, and go-live approval windows. Scheduling conflicts will delay milestones.

Change Advisory Board (CAB) process — PROD migration requires CAB approval through Unisys and EB's change management process. CAB cadence and lead times are EB-controlled.

Access and credentials — ECS requires timely access to all environment tiers, infrastructure management systems, and relevant tooling. Delayed access provisioning will impact the Month 1 preparation phase.

Unisys coordination — as the prime, Unisys must be available to facilitate EB communication and escalate decisions in a timely manner.

# 8.  Assumptions

This Statement of Work is based on the following assumptions:

Electric Boat maintains supported ServiceNow versions on all environment tiers throughout the engagement.

All work will be performed remotely. Travel is not included in the pricing below. If travel is required, it will be mutually agreed in writing and billed as a pass-through expense at cost.

EB-owned infrastructure (servers, data center facilities, F5 appliances, networking) will be provisioned and accessible within the timelines required to support the build schedule.

Unisys will coordinate EB stakeholder and SME availability; ECS does not have a direct contractual relationship with Electric Boat.

Pricing is based on T&M at a blended rate. Hours are estimated; actual hours billed will reflect work performed.

Post-environment operational support (monitoring, break/fix, managed services) is explicitly out of scope and is governed by the separate Unisys–Electric Boat ServiceNow Support Services agreement.

ServiceNow licensing, including any incremental licenses required for RaptorDB Professional or Predictive Intelligence, is Electric Boat's responsibility.

The Predictive Intelligence Server component in each environment tier is treated as an optional scope item and priced separately. Inclusion requires written authorization from Unisys.

ECS's scope is limited to the architecture, build, and migration work defined in this SOW. Functional configuration changes, module implementations, or enhancements to ServiceNow capabilities are out of scope.

# 9.  Pricing

## Pricing Structure

This engagement is priced as a Time and Materials (T&M) contract. ECS will bill at a blended hourly rate for all resources assigned to this engagement. Actual hours billed will reflect work performed; the estimate below represents the projected total for the fourteen (14) week base engagement.

| Description | Detail |
| --- | --- |
| Contract Type | Time and Materials (T&M) |
| Blended Hourly Rate | $215.00 per hour |
| Estimated Total Hours | 2,325 hours |
| Estimated Total Cost | $499,875 |
| Base Engagement Duration | 14 weeks (16-week ceiling) |
| Travel | Excluded — billed as pass-through if required and approved |

The estimated total reflects ECS's projection for the full engagement across all four roles (Engagement Manager, Business Analyst, Platform Architect, Developer) over fourteen weeks. Hours may be reallocated across roles as needed to respond to schedule conditions, provided the blended rate and total hours remain within the ceiling.

Not-to-Exceed Authorization: Unless otherwise agreed in writing, ECS will not exceed $499,875 without prior written approval from Unisys. ECS will notify Unisys when cumulative billings reach 80% of the authorized ceiling.

# 10.  Payment Terms

Invoicing. Everforth ECS shall invoice Unisys monthly in advance. Payment terms are net thirty (30) days from invoice date. Late payments shall accrue interest at the lesser of 1.5% per month or the maximum rate permitted by law.

Suspension for Non-Payment. Everforth ECS may suspend services upon ten (10) business days’ written notice for any invoiced amount more than thirty (30) days past due. SLAs shall be suspended during any period of non-payment. Such suspension shall not constitute a breach by Everforth ECS.

Annual Adjustment. If the engagement is extended beyond the initial twelve (12) month term, fees shall be subject to an annual adjustment equal to the greater of (i) three percent (3%) or (ii) the change in the U.S. Bureau of Labor Statistics Employment Cost Index for Information Sector workers for the trailing twelve months.

Taxes. Fees are exclusive of all applicable taxes other than taxes on Everforth ECS’s net income.

# 11.  Summary

This Statement of Work defines the scope, approach, responsibilities, and commercial terms under which Everforth ECS Federal will deliver ServiceNow architecture services to support Unisys's contractual obligations to Electric Boat / General Dynamics.

ECS will design and build a high-availability ServiceNow environment across three tiers (DEV, UAT, PROD) spanning two data centers, migrating from the current MariaDB installation to RaptorDB Professional with automated failover, deploying application node redundancy, and implementing F5 Global Server Load Balancing. The result will be an architecture capable of meeting Electric Boat's 99.99% uptime contractual requirement.

Post-migration operational support is explicitly out of scope and is governed by the separate Unisys–Electric Boat ServiceNow Support Services agreement.

This document is a draft Statement of Work provided for discussion and review. It does not constitute a binding commitment. All terms, including pricing, are subject to revision until a mutually executed SOW is in place. In the event of conflict between this document and any executed agreement, the executed agreement shall control.