INTERNAL PLAYBOOK

ServiceNow OOTB-First

Delivery Playbook

How we deliver OOTB-first ServiceNow engagements with discipline, measurement, and repeatability

ECS Federal  ·  ServiceNow Practice

Audience: Engagement Managers, Solution Architect, Process Consultant, Practice Management

Internal Use Only · Confidential

# Purpose of This Playbook

This playbook codifies how the ECS Federal ServiceNow practice delivers OOTB-first engagements. It exists for two reasons. First, to give every engagement team — Engagement Manager, Solution Architect, Process Consultant, developers — a common operating model so we deliver the same way every time, regardless of who is on the team. Second, to give practice management a trust-but-verify framework: a small, consistent set of metrics and check-ins that surface engagement health early enough to act, without micromanaging the team running the work.

The discipline this playbook describes is what makes OOTB-first economically viable. Without it, OOTB engagements collapse into custom-build engagements at the same price — which is how practices lose money on this model. With it, each engagement compounds into the next: reusable artifacts, shared decision patterns, and a customer base that has experienced the discipline and refers more like it.

How to use this document. Engagement Managers use Sections 1 and 4 to set up the engagement and manage the customer. Solution Architect and Process Consultant use Sections 2 and 3 to run workshops and enforce the discipline. Practice management uses Section 5 to monitor engagement health. Section 6 is the institutional memory that makes the next engagement easier than the last.

# 1.  Engagement Setup

Engagement setup is the highest-leverage phase of the entire program. Decisions made in Sprint 0 — team composition, customer dependency readiness, decision rights — are the difference between an engagement that ships clean and one that absorbs scope creep silently. The four artifacts in this section are non-negotiable: every engagement uses them, every time.

## 1.1  Sprint 0 Customer Readiness Checklist

By the end of Sprint 0, every item below must be confirmed. Any unchecked item at end of Sprint 0 triggers a dependency-slip conversation with the Project Sponsor (see Section 4.1).

### Foundation Data and SMEs

☐  Foundation Data Accelerator workbook completed by Connection (users, locations, groups, assignment rules, SLAs)

☐  Named SME for each in-scope process (Incident, Request, Change, Knowledge, Catalog, etc.) with calendar availability committed

☐  Named decision-makers for each in-scope process with decision authority confirmed in writing

☐  Project Sponsor identified, with calendar availability for Customization Council and bi-weekly Sponsor sync

### Environment and Access

☐  ServiceNow instance provisioned (sub-prod and prod) with admin access for ECS team

☐  Source-system access confirmed: AD/Entra ID, SCCM, Intune (with credentials and MID server placement validated)

☐  Network/firewall access for ECS team (VPN, allow-list, jump hosts as required)

☐  Communication channels established (Teams or Slack workspace, shared document repository, defect tracker)

### Existing Configuration Inventory

☐  Service Catalog inventory exported (item list, workflow types, approval chains, fulfillment groups)

☐  Knowledge base export with article counts by category, age, and last-updated date

☐  CMDB export with current CI counts by class and current relationship density

☐  Integration inventory: list of all current integrations with counter-system owners named

### Process Foundations

☐  CSDM 5.0 reference model selected (industry / company-size match) and pre-loaded for Sprint 1 workshops

☐  ECS Accelerator Pack distributed and walkthrough completed with Connection PM

☐  Backlog tooling stood up (in ServiceNow Agile or external) with story template defined

☐  Definition of Done published and acknowledged by Connection Product Owner

## 1.2  Team Roles and Decision Rights

Every engagement team has the same five roles. The decision rights matrix below ends "who owns this?" debates before they start.

### Roles

| Role | Responsibility | Loading |
| --- | --- | --- |
| Engagement Manager | Customer relationship, scope/budget, escalation, Customization Council chair, PCR authority | 0.25–0.5 FTE |
| Solution Architect | Architecture, OOTB-first decisions, customization recommendations, technical sign-off, code/config review | 1.0 FTE |
| Process Consultant | Workshop facilitation, requirements-to-stories, sprint cadence, customer day-to-day | 1.0 FTE |
| Developer / Configuration Specialist | Configuration, integration build, story-level test, peer code review | 1.0 FTE |
| CSDM / Data Architect | Data model decisions, CSDM mapping, CMDB design, Service taxonomy | 0.5 FTE |
| Junior Developer (as needed) | Catalog item build, KM article curation, defect remediation | 0.5 FTE |

### Decision Rights

| Decision | Recommends | Decides |
| --- | --- | --- |
| OOTB vs Customization (Rule of Three pass/fail) | Solution Architect | Customization Council |
| Sprint scope and acceptance criteria | Process Consultant | Engagement Manager + Product Owner |
| Story-level Definition of Done | Solution Architect | Solution Architect |
| Sprint sign-off (Definition of Done met for sprint) | Process Consultant | Connection Product Owner |
| PCR raise | Engagement Manager | Engagement Manager (notified to Practice Management) |
| Architecture / data model decisions | CSDM Architect + Solution Architect | Solution Architect |
| Hypercare extension (paid) | Engagement Manager | Practice Management + Customer Sponsor |

## 1.3  Customization Council Charter

Purpose. Gate every Customization Request to maintain OOTB-first discipline. Every customization that enters the build must have been seen, evaluated, and approved by the Council. No exceptions, no "just this one," no decisions in hallway conversations.

Members. Solution Architect (ECS, voting), Engagement Manager (ECS, voting), Project Sponsor (Customer, voting), CSDM Architect (ECS, advisory), Customer-side ServiceNow Architect if available (advisory).

Cadence. Weekly, 30 minutes, only Customization Requests on the agenda. If no requests are pending, meeting is canceled. Standing slot avoids re-scheduling friction when requests do come up.

Quorum. Solution Architect and Engagement Manager minimum. Project Sponsor or designated alternate must be present for any approval — no async approvals.

Decision threshold. Cumulative cap of 5 approved customizations across Phase 1. Crossing 6 triggers a PCR conversation; the customer must agree the engagement is moving outside the original OOTB envelope and either (a) descope something to compensate, (b) accept a PCR, or (c) reverse the most recent approvals.

Output. Every Customization Request — approved, rejected, or deferred — is logged in the Governance Triage Log within 24 hours of the meeting. Entries include business need, OOTB alternative considered, Council decision, rationale, and downstream impact.

## 1.4  PCR Trigger Reference

The SOW contains contractual PCR triggers. Below is the operational reference: when each fires, what the conversation looks like, who raises it.

| Trigger | When it fires | Conversation framing |
| --- | --- | --- |
| Custom scripting / protected baseline modification | Customization Council approves a request that requires Script Includes or modifies protected objects | "This crosses the OOTB envelope. We can do it, but it needs a PCR for scope and upgrade-impact assessment." |
| Custom tables outside CSDM | Council approves a custom table for an in-scope process where a standard CI class exists | "Structural deviation from CSDM. PCR for the table and the downstream upgrade implications." |
| Customer dependency missed by Sprint 0/1 | Any item on the 1.1 checklist still unchecked at end of Sprint 1 | "We're at risk of [specific outcome]. PCR for timeline extension or descope to recover." |
| Customer SME unavailable for in-scope integration | Integration-workstream work blocked >5 business days on customer SME availability | "Integration build is blocked. PCR for timeline if we can't get [SME] this week." |
| Third-party integration not in original SOW | Customer requests a new integration mid-engagement | "Out of original scope. We can do it as a PCR or defer to backlog." |
| Customization count >5 | Cumulative approved customizations cross 6 in a single Phase 1 | "We're outside the OOTB envelope. PCR or reverse the most recent approvals." |

# 2.  Workshop Operating Model

Workshops are how the OOTB-first principle gets enforced in practice. They are the moment when a process owner with ten years of legacy customization either accepts the OOTB pattern or doesn't. Done well, the workshop ends with a signed-off user story headed straight to the active sprint. Done badly, it ends with a list of "things to think about" that come back as customization requests two weeks later. The pattern in this section is what makes the difference.

## 2.1  The Five-Tier Workshop Framework

| Tier | What it covers | Sign-off output |
| --- | --- | --- |
| Accelerator Pack | Foundation data: users, groups, locations, assignment rules, catalog taxonomy, reference datasets | Validated workbook ready for build |
| CSDM | Service taxonomy, design domains, lifecycle stages, CI relationship standards, normalized class hierarchy | Signed-off CSDM-aligned data model |
| Reporting | OOTB Performance Analytics, dashboards, standard reports against business objectives | Confirmed list of OOTB reports + identified gaps for backlog |
| Process OOTB Alignment | End-to-end demonstration of each in-scope process (Incident, Request, Change, etc.) against OOTB | Signed-off user stories for the process |
| Integration | Integration patterns, data contracts, OOTB Spoke / IntegrationHub usage | Documented integration design + data contract |

## 2.2  Standard Facilitation Pattern

Every workshop runs the same six-beat pattern. Total duration: 90 minutes for routine workshops, 120 minutes for CSDM and Process OOTB Alignment.

### The Six Beats

- Pre-work (1 week before): Customer SMEs receive the OOTB demo materials and a pre-workshop questionnaire. Decisions are pre-warmed, not introduced cold.

- Open (5 minutes): Re-state the OOTB-first frame, the workshop's specific goal, and the named decisions required. Set the expectation that decisions will be made in the room.

- Demo (20–30 minutes): The platform shows the work first. Use customer data wherever possible — never Lorem ipsum. Demo against real Connection scenarios.

- Decisions (30–45 minutes): Focused conversation on the narrow set of decisions. Capture decisions live in the workshop notes. No "we'll get back to you" — if a decision genuinely needs more thought, name the decision-maker and the date by which it returns.

- Sign-off (10 minutes): Explicit sign-off on the decisions made, named in workshop notes. Sign-off authority is the named process owner from Section 1.1.

- Backlog and PCR (5 minutes): Items deferred to backlog are captured with rationale. Items that triggered a PCR conversation are flagged for the Engagement Manager.

## 2.3  Decision-Forcing Techniques

These are the tactical moves that prevent workshops from spiraling into open-ended discussions.

- Show, don't tell. Demo OOTB doing the work. Let the customer feel it. Talking about OOTB is less convincing than seeing it.

- Customer data, not Lorem ipsum. Always run demos against the customer's actual data. "Oh, this is OUR data" is the moment OOTB starts to feel real to the customer.

- Two options, both OOTB. When a customer pushes back on an OOTB pattern, offer two OOTB alternatives and force a choice between them. Never frame it as OOTB vs custom — frame it as Option A vs Option B, both OOTB.

- What's the business outcome? When a customer demands a specific implementation, redirect to the outcome. "Help me understand the outcome you need — let's see what OOTB gives us against that outcome."

- Defer to backlog, don't argue. For nice-to-haves that aren't blocking go-live, capture in backlog without committing. Backlog items don't require OOTB-vs-custom debate today.

- Name the customization explicitly. If something genuinely needs to be a customization, say so out loud and route it to the Council. Don't accidentally build a customization without flagging it.

## 2.4  "But Our Old Platform Did X" — Rebuttal Patterns

These are the conversations that happen in every workshop. Use the language patterns below to redirect without making the customer feel dismissed.

### "Our old workflow had 7 approval steps"

"Let's look at what each step prevented. If OOTB delivers the same control with fewer steps, that's a win for everyone. If a specific step prevents something OOTB doesn't, that's a candidate for the Customization Council. Let's walk through the steps."

### "We've always used custom Script Includes for this"

"Show me what the script does — what's the business behavior? We'll see if Flow Designer or a Decision Table can do the same thing OOTB. If they can, we save the maintenance burden of the script. If they can't, we'll bring it to the Council."

### "Our users won't accept the new portal"

"Adoption is real. Let's pilot the OOTB Employee Center with a small group in Sprint 5 and measure feedback before we commit to changing it. If the data shows real adoption pain, we have time to react. If it doesn't, we've saved the customization cost."

### "We need this customization or [bad thing] will happen"

"Let's document the bad thing. If it's a material business impact, it absolutely goes to the Council. If it's a preference or a workaround for something OOTB handles differently, it goes to backlog. Walk me through the bad thing."

### "That's not how we do it here"

"Got it. The OOTB pattern works for hundreds of organizations — let's not assume it can't work for Connection. Walk me through what's specific about Connection that the OOTB pattern doesn't account for. If there's a real gap, that's the Council. If it's process inertia, the OOTB pattern is the rebuild we're paying for."

### "Just make it work like the old system"

"That's the trap we're rebuilding away from. The old system has the technical debt that's blocking AI and modern features. Let me show you what OOTB does — if it gives us the same business outcome, we're better off. If it doesn't, that's a Council conversation."

## 2.5  Sign-off Criteria Per Workshop Type

Every workshop ends with a defined sign-off output. If the sign-off doesn't happen, the workshop didn't end successfully — it got rescheduled.

| Workshop Type | Sign-off Required |
| --- | --- |
| Accelerator Pack | Workbook completed and validated; named owner per data section; no open data-quality issues |
| CSDM | Service taxonomy documented (Business / Technical / Application Services); CI relationship standards agreed; design-domain ownership assigned; deviations from OOTB CSDM 5.0 logged with rationale |
| Reporting | List of OOTB reports/dashboards confirmed as meeting business need; gaps identified and routed to backlog or Council |
| Process OOTB Alignment | Signed-off user stories for the process; named approver; deltas (if any) routed to Council; backlog items captured |
| Integration | Integration design documented (source, target, frequency, payload); data contract signed by both sides; OOTB Spoke or IntegrationHub pattern selected |

# 3.  Discipline Mechanisms

The discipline mechanisms are the operational rails that keep OOTB-first from collapsing under daily pressure. Each one is a checkpoint that the team uses to enforce the principle without requiring Engagement Manager intervention every time.

## 3.1  Customization Request Flow

Every potential customization follows the same path. Solution Architect enforce this; Engagement Managers back the Solution Architect's judgment.

- Workshop or sprint surfaces a potential customization (a request that may not fit the Rule of Three).

- Solution Architect evaluates against the Rule of Three: can it be met by Configuration, UI Policy, or Flow Designer?

- If YES → standard user story, no Customization Request needed. Story enters the active sprint.

- If NO → Solution Architect creates a Customization Request and logs it in the Governance Triage Log within 24 hours.

- Solution Architect drafts an impact assessment: business need, OOTB alternatives considered, scope estimate, budget impact, upgrade impact.

- Customization Council reviews at the next weekly meeting (or sooner if blocking).

- Council decision: Approved / Rejected / Deferred to backlog.

- If Approved AND cumulative count is now >5 → Engagement Manager initiates PCR conversation before scope is added.

- Outcome documented in the Governance Triage Log with rationale and downstream impact.

## 3.2  Definition of Done Enforcement

The SOW's Definition of Done is contractual. The operational gates below are how the team enforces it on every story.

### Contractual DoD (from the SOW)

- All acceptance criteria in the user story have been met and validated by the Product Owner.

- The configuration adheres to the Rule of Three (Configuration, UI Policy, or Flow Designer) unless a Customization has been approved by the Project Sponsor.

- The configuration is documented in the relevant design artifact.

### Operational Gates (team-level)

- Update set documented and named per the engagement's update-set convention.

- Code/configuration peer-reviewed by the Solution Architect or a designated reviewer.

- Unit or smoke test executed and passing.

- Integration touchpoints exercised in sub-prod (if the story touches integrations).

- No P1 defects open against the story.

- Demo recorded for the customer's Sprint Review.

## 3.3  Sprint Cadence

The two-week sprint cadence is identical across every engagement. Customers get used to it. Team members rotate between engagements without re-learning the rhythm.

| When | Ceremony | Duration | Attendees |
| --- | --- | --- | --- |
| Mon Week 1, Day 1 | Sprint Planning | 2 hours | Full team + Connection Product Owner |
| Daily | Standup | 15 minutes | Full team (Connection optional) |
| Wed Week 1 | Backlog Refinement | 1 hour | Solution Architect + Process Consultant + Product Owner |
| Wed Week 2 | Customization Council | 30 minutes (if requests pending) | Council members |
| Fri Week 2 | Customer Showcase | 30 minutes | Full team + Customer stakeholders |
| Fri Week 2 | Sprint Review & Sign-off | 1 hour | Full team + Product Owner + named approvers |
| Fri Week 2 | Sprint Retro | 30 minutes (ECS-internal) | Full team |

## 3.4  Governance Triage Log

The Governance Triage Log is the single source of truth for OOTB compliance. Every Customization Request, every "Skipped Record" risk, every fired PCR trigger, every sponsor-approved deviation lives here. Reviewed weekly by the Engagement Manager.

### Log Entry Template

| Field | Definition |
| --- | --- |
| Date | Date the entry was logged |
| Requester | Name and role of the person raising the request |
| Workstream | Which in-scope area (ITSM Core, CSDM, Catalog, Integration, etc.) |
| Business Need | What outcome the customer is trying to achieve |
| OOTB Alternative Considered | What OOTB capability was evaluated; why it does/does not meet the need |
| Council Decision | Approved / Rejected / Deferred to backlog |
| Rationale | Why the Council made the decision (one or two sentences) |
| Downstream Impact | Scope/budget/upgrade implications; PCR triggered (Y/N) |
| Status | Open / In Build / Closed |

# 4.  Customer Engagement Patterns

This section is the playbook for the customer-facing conversations that decide engagement health. Most engagements that fail don't fail on technical execution — they fail because hard conversations were avoided or had too late.

## 4.1  Dependency-Slip Escalation Playbook

When a customer-side dependency slips, escalation follows a deterministic timeline. Not punitive — focused on getting the engagement back on track before the calendar damage is irrecoverable.

### The Timeline

- Day +1 (slip identified): Solution Architect or Process Consultant raises in standup; logs in the dependency tracker; sends a same-day note to the Connection PM with the impact.

- Day +3: Engagement Manager has a soft conversation with the Connection PM. Frame: "We're tracking a slip on [X]. Here's the impact if it doesn't land by [date]. What can we do together?"

- Day +5: Engagement Manager has a formal conversation with the Project Sponsor. Three options framed (see 4.2 below).

- Day +7: PCR formally raised if the dependency hasn't been recovered or descoped.

### Day +5 Sponsor Conversation Script

"[Sponsor name], I want to flag a dependency we need to resolve together. [Specific dependency] was due by [date] and we're now [N] days past. The impact is [specific calendar / scope outcome]. We have three options: (1) get [dependency] back on track this week, (2) descope [specific item] from Phase 1 to compensate, or (3) raise a PCR for timeline extension. Which works for you?"

Notice the structure: state the fact, name the impact, present three concrete options. Don't lead with "we need a PCR" — that's option three of three. Most Sponsors will pick option one and unblock the dependency. PCR is the safety net, not the opening offer.

## 4.2  PCR Conversation Template

PCRs are not punitive — they are how we deliver on time. The framing matters: it's a conversation about delivery, not about money.

### Standard Frame

- State the goal: "We want to deliver [specific scope] by [date]."

- State the dependency: "[Specific input] is needed by [date] for that to happen."

- State the gap: "We're at [current date] without [input]."

- Present options: "Option 1: get on track this week. Option 2: descope X. Option 3: PCR for [time/budget]."

- Ask for direction: "Which works for you? We need a decision by [date] to keep the engagement on schedule."

Done early — within a week of the dependency slip — the conversation usually doesn't even produce a PCR. The customer gets the dependency back on track because they hear the impact while it's still fixable. Done late, the conversation costs everyone.

## 4.3  Sponsor and Stakeholder Cadence

| Cadence | Audience | Format | Purpose |
| --- | --- | --- | --- |
| Bi-weekly Sponsor Sync | Project Sponsor + Engagement Manager | 30 minutes, agenda-driven | Decisions, risks, PCR triggers (NOT status updates — status goes in the written report) |
| Monthly Steering Committee | Sponsor + senior stakeholders + Engagement Manager + Solution Architect | 60 minutes, structured review | Phase progress, risks, upcoming gates, customization log review |
| Weekly Written Status | All stakeholders | Short, scannable, RYG | Schedule status, completed work, planned work, risks, decisions needed |
| Sprint Showcase | Working stakeholders | 30 minutes, live demo | Demonstrating what was built — this drives adoption confidence |

## 4.4  Workshop Language Patterns

Specific phrases the team uses to maintain discipline without being adversarial. These should feel like the team's natural voice, not a script — but having them documented means new team members start consistent.

"Let's see what OOTB does first."

"What's the business outcome we're after?"

"If we can't meet that with OOTB, it's a Council conversation."

"I'll capture that in the backlog so we can prioritize against everything else."

"Help me understand why the OOTB pattern doesn't work for this case."

"Walk me through the impact if we don't customize this."

"Two OOTB options for you — which one fits Connection better?"

"That's a sponsor-level decision. Want me to schedule a Council conversation?"

# 5.  Measurement and Trust-but-Verify

This section is the practice management layer. It exists so engagement health is visible from outside the engagement, so management can support without micromanaging, and so problems surface early enough to act.

## 5.1  Weekly Project Health Metrics

Every Engagement Manager reports the following metrics weekly to practice management. The thresholds below define Red / Yellow / Green status.

| Metric | Definition | Green | Yellow | Red |
| --- | --- | --- | --- | --- |
| Customization Count (cumulative) | Approved customizations this Phase | ≤3 | 4–5 | ≥6 |
| OOTB Adoption Rate | % of stories built without customization | ≥90% | 80–89% | <80% |
| Sprint Velocity (3-sprint avg) | Story points completed vs. planned | ≥90% | 75–89% | <75% |
| Defect Trend (open P1+P2) | Count, week-over-week | Decreasing | Flat | Increasing |
| Dependency Slip Count | Customer dependencies missed by sprint | 0 | 1–2 | ≥3 |
| PCR Triggers Fired (cumulative) | PCR-trigger events logged | 0–1 | 2–3 | ≥4 |
| Workshop Sign-off Rate | % of workshops with same-day sign-off | ≥90% | 75–89% | <75% |
| Customer Satisfaction (sprint review) | 1–10 score from sprint review feedback | ≥8 | 6–7 | ≤5 |

## 5.2  Engagement Health Status

Engagement is RED if any of: two or more red metrics; customization count ≥6 mid-Phase; three or more dependency slips; velocity <75% for three consecutive sprints.

Engagement is YELLOW if: two or more yellow metrics, or one metric trending toward red, or one one-time event of concern (e.g., a Sponsor reversal of a Solution Architect recommendation).

Engagement is GREEN otherwise.

Reporting cadence: Engagement Managers send the weekly metrics report to practice management every Friday by close of business. Yellow or Red status triggers a Monday 1:1 with practice management to plan the response.

## 5.3  Mandatory Escalation Triggers

These events trigger same-day escalation to practice management, regardless of weekly cadence:

- First Customization Council vote where the ECS Solution Architect is overridden by the Project Sponsor.

- First time a PCR trigger fires (not the PCR being raised — the trigger event).

- First time velocity drops below 75% for a single sprint.

- Any explicit Sponsor pushback on the OOTB-first principle (e.g., "we don't agree with this approach").

- Any dependency slip beyond Day +5 without resolution.

- Any team member raising a concern about engagement viability in a retro.

- Any indication the Customer is considering changing the project Sponsor or the engagement scope.

## 5.4  Practice Management Health Check Questions

These are the questions practice management uses in weekly 1:1s with the Engagement Manager. They are designed to surface issues that don't show up in the metrics — open-ended, not scored.

- "Did the Solution Architect say no to anything this week? What was the customer's reaction?"

- "Which workshop felt the hardest? Why?"

- "Is anyone on the team starting to cave on customization conversations?"

- "What's the Sponsor saying privately, off the agenda?"

- "What's the next dependency at risk?"

- "What's showing up in retros that isn't in the weekly metrics?"

- "Is there a customer stakeholder going quiet on you?"

- "Anything you've absorbed this week that you should have raised as a PCR?"

That last question is the one that surfaces the silent scope creep. Most Engagement Managers will hesitate to admit they absorbed something — make it explicit and safe to raise.

## 5.5  Customer-Side Health Signals

Beyond the project metrics, watch for these customer-side signals. Any one of them is a yellow flag worth investigating in the next Sponsor conversation.

- Project Sponsor stops attending bi-weekly syncs (or sends a delegate without explanation).

- SME responsiveness drops in the second half of sprints (Mondays great, Thursdays silent).

- Workshop attendance shifts to substitutes instead of the named SMEs from the Sprint 0 checklist.

- "We need to think about it" responses on decisions that have been on the table for more than one workshop.

- Multiple back-channel conversations between customer stakeholders about scope changes (visible because two different people raise the same scope question).

- Customer asking for additional reporting / status detail not previously requested (often signals doubts brewing).

- Customer asking how the engagement compares to other Phase 1 implementations (often signals second-guessing the approach).

# 6.  Knowledge Capture and Continuous Improvement

Each engagement makes the next one cheaper to deliver. This section is how that compounding actually happens — what we capture, where it lives, and how we use it.

## 6.1  Lessons-Learned Template

End of every Phase 1 (and end of every major Phase 2/3 milestone), the engagement team captures the following — within two weeks of close-out, while it's fresh.

### What Went Right

Three to five things the team would do again. Specific, not generic. "The CSDM workshop in Sprint 1 used a pre-loaded reference model that cut decision time in half" — not "good teamwork."

### What Went Wrong

Three to five things the team would change. Same specificity. "Catalog item discovery didn't start until Sprint 3, which compressed Sprints 4–5" — not "could have planned better."

### Decision Postmortem

Walk through the three or four most consequential decisions of the engagement. For each: what did we decide, what did we learn, would we decide it the same way again?

### Playbook Changes

Specific recommended changes to this playbook based on what was learned. These feed the quarterly playbook review.

### Artifact Library Additions

New reusable artifacts (CSDM models, accelerator workbooks, demo scripts, integration patterns) that should be added to the practice library for the next engagement.

## 6.2  Reusable Artifact Library

Maintained centrally by the practice. Every engagement contributes; every engagement starts by pulling from it.

| Artifact Type | Description | Maintained By |
| --- | --- | --- |
| CSDM 5.0 Reference Models | Pre-populated CSDM models by industry and company size for use as a starting point in CSDM workshops | CSDM Architects (rotating ownership) |
| ECS Accelerator Packs | Workbooks for foundation data, indexed by workstream | Engagement Managers contribute, Practice Lead curates |
| Catalog Item Templates | Pre-built catalog item designs by category (HR-style, IT-style, Facilities-style) following OOTB patterns | Senior Developers |
| Workshop Facilitation Decks | Standard decks for each of the five workshop tiers, with placeholder slides for customer-specific content | Process Consultant |
| PCR Conversation Scripts | Templates and recorded examples for each PCR trigger type | Engagement Managers |
| Dependency Tracker Template | Pre-formatted dependency tracker with the standard data fields and timeline triggers | Practice Lead |
| Weekly Status Report Template | RYG status template with the standard sections and metric callouts | Practice Lead |
| Governance Triage Log Template | Pre-formatted Governance Triage Log with the standard fields | Practice Lead |
| Sprint Ceremony Templates | Sprint Planning, Backlog Refinement, Sprint Review, Retro templates | Process Consultant |
| Demo Scripts | Reusable demo scripts for Process OOTB Alignment workshops by process type (INC, REQ, CHG, CAB, etc.) | Solution Architect |

## 6.3  Cross-Engagement Pattern Library

After three or more engagements, recurring patterns emerge. The pattern library captures them so subsequent engagements don't re-discover them.

- Common objection patterns and rebuttals: Specific "but our old platform did X" objections we've seen, and the OOTB rebuttals that worked.

- Common Sponsor concerns: Patterns of concern from Project Sponsors and how the Engagement Manager addressed them — written as decision tree, not narrative.

- Common dependency slips: Which customer dependencies tend to slip in which industries; recovery patterns that worked.

- Common customizations that came up: Customization Requests we've seen across multiple engagements; how the Council decided each time and what the long-term outcome was.

- Common adoption patterns: How customer adoption tends to evolve through Phase 1 and into Hypercare; warning signs and intervention patterns.

The pattern library is reviewed quarterly by senior Engagement Managers. New patterns are added; old patterns are validated against recent experience and updated or retired.

## 6.4  Quarterly Playbook Review

This playbook is a living document. Once per quarter, the practice convenes a 90-minute review with all senior Engagement Managers and Solution Architect.

### Review Agenda

- Lessons-learned reports from engagements closed in the quarter — what should change in the playbook?

- Pattern library additions and retirements.

- Metric threshold review — are the Red/Yellow/Green thresholds in Section 5.1 still appropriate? Have we calibrated against the right baseline?

- Workshop language pattern review — what new objections have surfaced? What rebuttals worked?

- Artifact library curation — what new artifacts get added? What artifacts haven't been used and should be retired?

- Forward-looking: what's coming in the next ServiceNow release that this playbook needs to anticipate?

### Output

Updated playbook published within two weeks of the review, distributed to the practice with a one-page change summary.

# Closing Note

This playbook is the discipline that makes OOTB-first economically viable for ECS and operationally credible for our customers. Every section exists because a real engagement either succeeded by following it or struggled by ignoring it.

Practice management's job is to back the team when they apply this discipline — including in the moments when the customer pushes back. The Solution Architect who refuses an unjustified customization, the Engagement Manager who raises a PCR on Day +5 instead of absorbing the slip, the Process Consultant who defers a request to backlog instead of building it quietly: these are the behaviors that win the next engagement, not just this one.

Trust the team. Verify with the metrics. Back the discipline.