INTERNAL OPERATING GUIDE

Governance Operating

Guide

How ECS delivers OOTB-first governance: templates, mechanics, two-key SLAs, education and risk containment

ECS Federal  ·  ServiceNow Practice

Audience: Engagement Managers, Solution Architects, Practice Lead, Engagement Managers

Internal Use Only · Confidential

# How to Use This Guide

This Guide is the internal companion to the client-facing Phase 1 Governance Charter. The Charter describes what we do with the customer; this Guide describes how we do it operationally — the templates, SLAs, decision mechanics, education program, and risk-containment levers that make the framework work in practice.

Read order:

- Engagement Managers: Sections 1, 4, 5, 6 — operating model, two-key mechanics, risk containment, escalation.

- Solution Architects: Sections 1, 2, 3 — operating model, deviation lifecycle, recommendation templates.

- Practice Lead / Engagement Managers: Sections 1, 4, 5 — two-key role and SLA, contract risk model, escalation triggers.

- All roles: Section 7 (Education) — what each role learns and when.

# 1.  The Operating Model

## 1.1  The Principle

Lead with OOTB; deviate only when business outcomes require it. Make customization the exception, not the default. The principle is the same one stated in the Client Charter — internal alignment is necessary because the team enforces it daily, often when it would be easier not to.

## 1.2  The Five Levers

OOTB-first depends on five operational levers that the team uses every day. Without all five, the principle erodes.

| Lever | Purpose | Owner |
| --- | --- | --- |
| Rule of Three | Triage filter: Configuration / UI Policy / Flow Designer first. | Solution Architect |
| Deviation Lifecycle | Standard six-stage process for any deviation from OOTB. | Solution Architect + Engagement Manager |
| Two-Key Decision | Dual approval (Sponsor business need + ECS Practice technical path). | Practice Lead + Sponsor |
| Governance Triage Log | Single source of truth for all OOTB-compliance decisions. | Engagement Manager |
| PCR Triggers | Contractual safety valves; raised early, not absorbed. | Engagement Manager |

# 2.  The Deviation Lifecycle — Operational Detail

The lifecycle in the Client Charter is the public face. The version below adds the internal mechanics: who does what, against what SLA, with what artifact.

| Stage | SLA | Tools / Artifacts |
| --- | --- | --- |
| 1. Surface | Logged within 24 hours of being raised. | Governance Triage Log entry created. |
| 2. Triage | Solution Architect classifies within 24 hours. | Rule of Three checklist; Triage Log updated with classification. |
| 3. Document | Solution Architect drafts impact assessment within 48 hours of classification. | OOTB Alternative Analysis + Business Outcome Alignment + Contract Risk Assessment templates (see Section 3). |
| 4. Recommend | Recommendation included in impact assessment. | Recommendation logged in Triage Log. |
| 5. Decide | Two-key decision within 48 hours of impact assessment publication. | Council meeting (if required) or async two-key process. |
| 6. Route | Outcome routed within 24 hours of decision. | Sprint backlog (if approved), product backlog (if deferred), or PCR document (if PCR-triggered). |

Total wall-clock time from surface to decision: 5 business days max. If a decision is needed faster (because it is blocking active sprint work), the Solution Architect flags it as urgent and the SLAs compress to 24-hour total.

# 3.  Recommendation Templates

Every Customization Request comes with three completed templates. The Solution Architect writes them; the first two are shared with the customer; the third is internal-only.

## 3.1  OOTB Alternative Analysis (Shared)

Demonstrates the team has genuinely considered OOTB before recommending a deviation.

| Field | Description | Example |
| --- | --- | --- |
| Request | What the customer asked for, in their words. | "We need a 7-step approval workflow for change requests with conditional routing based on requester level." |
| OOTB Capability Reviewed | Which OOTB feature was evaluated. | Standard Change Approval Policy + Risk Assessment workflow + CAB Workbench. |
| What OOTB Does | Plain-language description of the OOTB capability. | OOTB delivers risk-scored approvals (Standard, Normal, Emergency) with optional CAB review for non-Standard. Approval routing uses Approval Definitions tied to assignment groups. |
| What OOTB Does Not Do | Specific gap relative to the request. | OOTB does not natively support requester-level-based routing; a requester-level field would need to feed an Approval Definition. |
| Configuration Path Considered | Did Configuration / UI Policy / Flow Designer close the gap? | Yes — a Decision Table can route based on a requester-level reference field; a Flow Designer flow can update the Approval Definition selection. No custom code required. |
| Recommendation | Build OOTB / Configure / Defer / Council. | Configure — no deviation needed. Build using Decision Table + Flow Designer in Sprint 4. |

## 3.2  Business Outcome Alignment (Shared)

Forces the recommendation to be evaluated against the customer's actual outcome, not against the implementation request.

| Field | Description | Example |
| --- | --- | --- |
| Stated Outcome | The business outcome the customer is trying to achieve. | Reduce average change-approval cycle time from 5 days to 2 days while maintaining audit trail. |
| Implicit Outcome (if different) | The outcome behind the request that the customer may not have stated. | Speed up change approvals because IT changes are blocking business projects. |
| How OOTB Serves the Outcome | The OOTB capability's contribution to the outcome. | Standard Change Approval Policy auto-approves low-risk changes (40-50% of CHGs) instantly; Risk Assessment routes the rest based on calculated risk score; CAB Workbench eliminates manual CAB scheduling overhead. Net: average cycle time projected to drop to <2 days for low-risk, ~3 days for medium-risk. |
| How the Requested Approach Serves the Outcome | Whether the customer's specific request actually serves the underlying outcome better than OOTB. | The 7-step workflow encodes existing process — but does not actually reduce cycle time. It preserves the legacy approach. Cycle time would improve more by adopting risk-based approvals than by replicating the legacy workflow. |
| Recommendation | Recommendation framed against business outcome. | Adopt OOTB Standard Change Approval Policy. Frame the conversation with the Sponsor as: "Your outcome is faster cycle time; OOTB delivers it; the legacy 7-step workflow does not." |

## 3.3  Contract Risk Assessment (Internal Only)

The internal-only template that protects the engagement. The Solution Architect completes this for every Customization Request before the two-key decision.

| Field | Description | Example |
| --- | --- | --- |
| PCR Trigger Status | Does this fire any of the six SOW PCR triggers? | No — fits within Rule of Three (Decision Table + Flow Designer). No PCR trigger. |
| Cumulative Customization Count | Including this request if approved. | Currently 2 of 5 approved. This would not be a customization. |
| Upgrade-Safety Impact | Specific upgrade impact assessment. | None — uses OOTB Decision Tables which are upgrade-safe by design. |
| Cross-Workstream Impact | Does this affect other in-scope workstreams? | No — Change is self-contained for this request. |
| Maintenance Burden | Long-term maintenance implication for Connection. | Low — Decision Tables and Flow Designer flows are configured, not coded. |
| Estimated Build Cost (sprint days) | Internal estimate for sprint planning. | 1.5 sprint days (1 day build, 0.5 day test). |
| Risk if Approved | What can go wrong if this is approved. | Low. Decision Table updates may need to be made if Connection's level-routing rules change. |
| Risk if Deferred | What can go wrong if this is deferred. | Medium. Sponsor may push back if the Standard Change Approval Policy change feels unfamiliar — pre-brief recommended. |

# 4.  The Two-Key Decision Mechanics

## 4.1  Roles

| Key | Who | Approves | What They Look For |
| --- | --- | --- | --- |
| First Key — Business Need | Connection Project Sponsor (or named delegate) | Whether the deviation addresses a genuine business need. | Material business outcome, not preference. Worth the maintenance burden. Aligned with current priorities. |
| Second Key — Technical Path | ECS Practice Lead (Practice Lead or designated Engagement Manager — outside the engagement's daily team) | Whether OOTB genuinely cannot meet the need and the proposed approach is the right path. | OOTB alternatives genuinely exhausted. Approach upgrade-safe. No downstream impact missed. |

## 4.2  When Tim or the EM Takes the Second Key

- Engagement Manager (EM) handles by default. Routine Customization Requests within scope, no PCR trigger, cumulative count below 4.

- Tim (Practice Lead) takes the second key on: (a) any request where the Sponsor's body language suggests pushback, (b) any structural deviation (custom table, protected baseline modification), (c) any request that would push cumulative customization count to 4 or above, (d) any request the EM flags for senior review.

## 4.3  SLAs

| Step | SLA | Owner |
| --- | --- | --- |
| Solution Architect submits impact assessment to Sponsor and Practice Lead | Same day as completion (within 48 hrs of triage). | Solution Architect |
| Sponsor decision (first key) | Within 24 hours of submission. | Sponsor |
| Practice Lead decision (second key) | Within 24 hours of Sponsor decision. | Practice Lead |
| Outcome logged in Triage Log | Within 24 hours of two-key decision. | Engagement Manager |

## 4.4  When the Two Keys Disagree

Disagreement is expected occasionally and is not a failure mode. The reconciliation path:

- If Sponsor approves but Practice rejects → Solution Architect drafts a revised approach (e.g., narrower scope, different OOTB pattern). Re-submitted within 48 hrs.

- If Sponsor rejects but Practice approves → request is rejected (the deviation is not built). Logged with Sponsor rationale.

- If both reject → request is rejected; Engagement Manager has follow-up conversation with Sponsor to understand business need and route to backlog or descope conversation.

## 4.5  When the Practice Lead Should Override the Solution Architect

The Practice Lead's job is to back the Solution Architect's recommendation 90%+ of the time. The 10% where the Practice overrides should:

- Have a clear, documented rationale.

- Include a learning conversation with the Solution Architect, not a reversal in front of the customer.

- Update either the Solution Architect's understanding (coaching) or the recommendation templates (process improvement).

If the Practice Lead is overriding more than 10% of the time, the Solution Architect needs coaching, not the recommendations need overriding.

# 5.  Risk Containment

## 5.1  Cumulative Customization Counter

| Cumulative Count | Status | Required Action |
| --- | --- | --- |
| 0–3 approved | Green | Standard process. Two-key decisions only. |
| 4–5 approved | Yellow | Engagement Manager notifies Practice Lead weekly. Review trajectory. |
| 6 or more approved | Red | Mandatory PCR conversation with Sponsor. Three options framed: descope, accept PCR, reverse most recent approvals. |

## 5.2  PCR Triggers (from the SOW)

Six contractual triggers. Each one fires immediate Engagement Manager awareness; the script for raising each is in the SOW Section 2.3.

- Custom scripting / protected baseline modification.

- Custom tables outside CSDM.

- Customer dependency missed by Sprint 0/1.

- Customer SME unavailable for in-scope integration work.

- Third-party integration not in original SOW.

- Cumulative customization count exceeds 5.

## 5.3  Definition of Done — Internal Gates

In addition to the contractual DoD, every story passes through internal operational gates before sprint sign-off:

- Update set documented and named per the engagement's update-set convention.

- Code/configuration peer-reviewed by the Solution Architect or designated reviewer.

- Unit or smoke test executed and passing.

- Integration touchpoints exercised in sub-prod (if the story touches integrations).

- No P1 defects open against the story.

- Demo recorded for the customer's Sprint Review.

## 5.4  Engagement Health Metrics — Weekly Report

Engagement Managers send the following weekly to Practice Management:

| Metric | Green | Yellow | Red |
| --- | --- | --- | --- |
| Customization Count (cumulative) | ≤3 | 4–5 | ≥6 |
| OOTB Adoption Rate | ≥90% | 80–89% | <80% |
| Sprint Velocity (3-sprint avg) | ≥90% | 75–89% | <75% |
| Defect Trend (open P1+P2) | Decreasing | Flat | Increasing |
| Dependency Slip Count | 0 | 1–2 | ≥3 |
| PCR Triggers Fired (cumulative) | 0–1 | 2–3 | ≥4 |
| Workshop Sign-off Rate | ≥90% | 75–89% | <75% |
| Customer Satisfaction (sprint review) | ≥8 | 6–7 | ≤5 |

## 5.5  Mandatory Escalation Triggers

Same-day escalation to Practice Management, regardless of weekly cadence:

- First Council vote where the ECS Solution Architect is overridden by the Sponsor.

- First time a PCR trigger fires (the trigger event, not the PCR being raised).

- First time velocity drops below 75% for a single sprint.

- Any explicit Sponsor pushback on the OOTB-first principle.

- Any dependency slip beyond Day +5 without resolution.

- Any team member raising engagement viability concerns in retro.

# 6.  Customer-Facing Posture

How the team talks about governance with the customer matters as much as how it operates internally. The framing below is consistent across all customer touchpoints.

## 6.1  How to Frame the Two-Key Model

"Customization decisions go through both your Sponsor and our Practice Lead. Your Sponsor confirms the business need; our Practice confirms the technical path is right. It's how we make sure customizations are genuinely needed and built to be upgrade-safe — protecting your investment in this platform long-term."

## 6.2  How to Talk About 'No'

"Let's walk the decision framework together. We're not saying no — we're checking whether OOTB delivers the outcome, whether configuration can close the gap, and whether the deviation is worth the long-term burden. Most of the time we end at 'yes, configured this way.'"

## 6.3  How to Raise a PCR

"We want to deliver [scope] by [date]. [Specific dependency or scope item] is needed for that. Three options: (1) get it back on track, (2) descope X, or (3) PCR for [time/budget]. Which works for you?"

## 6.4  How to Defer to Backlog

"That's a good thought — let me capture it in the backlog so we can prioritize against everything else. Phase 2 is when the items in this backlog get built, with sponsor input on what makes the cut."

# 7.  Education Program

## 7.1  Client Education Track

| When | Activity | Duration | Outcome |
| --- | --- | --- | --- |
| Sprint 0 | Governance Onboarding session — walk through the Charter end-to-end with Sponsor and named stakeholders. | 60 minutes | Client understands the framework and signs the Charter. |
| Before each workshop | Workshop Pre-Brief — covers OOTB pattern about to be demonstrated and decisions in scope. | 15 minutes | Decisions are pre-warmed; workshop time is decision time, not introduction time. |
| Monthly | Triage Log Review — Sponsor sees what's been raised, decided, deferred, escalated. | 30 minutes (within Sponsor sync) | Trust through transparency. |
| End of Phase 1 | Lessons-learned debrief and Charter refresh for Phase 2. | 90 minutes | Phase 2 starts with shared understanding. |

## 7.2  Team Education Track

| When | Activity | Duration | Outcome |
| --- | --- | --- | --- |
| New Solution Architect onboarding | Walkthrough of operating model, templates, decision tree, two-key mechanics. Shadow one Council before solo. | 90 minutes + shadow | Solution Architect can run the framework solo. |
| New Process Consultant onboarding | Workshop facilitation pattern, rebuttal scripts, sign-off criteria. Co-facilitate one workshop with peer review. | 90 minutes + co-facilitate | Facilitator runs OOTB-first workshops consistently. |
| All-team monthly pattern share | Cross-engagement learning — what's coming up, what's working, what isn't. | 30 minutes | Practice learns, not just delivers. |
| Quarterly Practice Review | Lessons learned review; metric calibration; Charter and Operating Guide updates. | 90 minutes | Frameworks stay current. |

# 8.  Quick Reference — Day-One Cheat Sheet

For the team member who needs the framework on a single page.

### If you hear a deviation request:

- Apply Rule of Three. If Configuration / UI Policy / Flow Designer can do it → no deviation.

- If true deviation → log in Triage Log within 24 hrs.

- Solution Architect writes 3 templates within 48 hrs (OOTB Alternative, Business Outcome, Contract Risk).

- Two-key decision within 48 hrs (Sponsor + Practice Lead).

- Route: build / backlog / PCR. Log decision.

### If a customer dependency slips:

- Day +1: Solution Architect/Process Consultant raises in standup, logs in tracker, notifies Connection PM.

- Day +3: Engagement Manager has soft conversation with Connection PM.

- Day +5: Engagement Manager has formal Sponsor conversation, three options framed.

- Day +7: PCR formally raised if not resolved.

### If you hit a yellow or red metric:

- Notify Practice Management same day.

- Monday 1:1 with Practice Management to plan response.

- Document mitigation in Triage Log.

### If you're not sure whether to escalate:

"Ask: "Will I regret this in two weeks if I don't raise it now?" If yes, raise it now."