## Instructions
02 — Asset Classes (Baseline)
HAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the asset classes the customer will track at MVP. Foundations deliberately keeps the list small — typically 3–5 classes (e.g., Laptop, Monitor, Mobile Phone). Each class corresponds to an alm_hardware extension table (cmdb_ci_computer, cmdb_ci_display, cmdb_ci_mobile_device).
Who fills this out | Customer-side: HAM Process Owner. ECS-side: Solution Architect validates class count and CMDB extension match.
When it's due | Process Decisions and Configuration Data finalized by end of Sprint 0, Week 1. Workbook 03 (Models) and 04 (Inventory) cannot start until classes are confirmed.
How long it takes | Approximately 1.5–2 hours.
Where the data comes from | Strategy decisions from Sprint 0 HAM workshop. Existing class lists from Snipe-IT / ManageEngine / spreadsheet inventories.
How to use this workbook | Use the OOTB classes ECS recommends. Resist the temptation to add classes 'because we used to track them.' If a class doesn't have an active receive-issue-retire process, defer it to Realization Pack workbook 02.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Asset Classes (Baseline) — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How many asset classes at MVP? | 3–5 classes — Laptop, Monitor, Mobile Phone is the typical baseline. |  | More classes ≠ more value. More classes = more stale data.
2 | Track laptops and desktops as separate classes or one Computer class? | One class (cmdb_ci_computer) with form_factor field. Splits add taxonomy without operational value.
3 | Mobile phones in scope at Foundations? | Only if MDM is already in place and there's an active issue/return process. Otherwise defer.
4 | Peripherals (mice, cables, headphones) in scope? | Out of scope for Foundations. Track as Consumables in Realization Pack workbook 02 with bulk-receive pattern.
5 | Servers/network gear in scope? | Out of scope for Foundations — managed by Discovery and CSDM, not HAM. Realization Pack workbook 02 includes if customer chooses.
6 | Use OOTB cmdb_ci_* classes or extend? | Use OOTB classes only. No custom CI classes at MVP.
7 | Class-level required fields? | asset_tag, serial_number, model. Owner/assigned_to required only when state = In use. |  | Drives Data Policy in workbook 05.
8 | Asset tag format — class-prefixed or unified? | Class-prefixed (IT-LAP-####, IT-MON-####). Easier visual scanning during audits.
9 | Asset tag generator — manual or auto? | Auto-generated via OOTB Number Maintenance per class.
10 | Volume estimate per class — used for sizing? | Capture realistic estimates. Drives ECS effort estimates for import and reconciliation.
11 | Track-by-serial vs track-by-tag? | Both. Serial is the manufacturer truth; tag is the operational handle.
12 | Decommissioned classes — retain historic records? | Yes, retained as inactive. No deletion of historic alm_hardware.

## Dependencies
Asset Classes (Baseline) — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | HAM Application activated | Not Started | ECS
2 | CMDB CI classes available (cmdb_ci_computer, cmdb_ci_display, cmdb_ci_mobile_device) | Complete | ECS
3 | Number Maintenance (sys_number) records for each class | Not Started | ECS
4 | Customer signoff: which classes are in scope at MVP | Not Started | Customer
5 | Realistic volume estimate per class | Not Started | Customer

## Configuration Data
Asset Classes (Baseline) — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. In-Scope Classes (MVP)
Class 1 | Laptop → cmdb_ci_computer | Volume estimate: 350
Class 2 | Monitor → cmdb_ci_display | Volume estimate: 420
Class 3 | Mobile Phone → cmdb_ci_mobile_device | Volume estimate: 75
2. Asset Tag Configuration
Tag prefix per class | IT-LAP, IT-MON, IT-MOB | Class-scoped
Tag number format | 5-digit zero-padded | OOTB Number Maintenance
Auto-generation | Enabled | OOTB
3. Required Fields per Class
Always required | asset_tag, serial_number, model | Data Policy
Required when state = In use | assigned_to | Data Policy from workbook 05
Required when state = In stock | stockroom | Data Policy from workbook 05
4. Class Extensions
Custom fields added | None at MVP | Use OOTB fields only
Custom CI classes | None | Use cmdb_ci_* directly

## R&R
Asset Classes (Baseline) — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Class scope decision workshop | R | C | ECS facilitates; Customer decides.
OOTB CI class validation | R | I | ECS confirms target tables.
Number Maintenance configuration | R | I | ECS configures.
Asset tag prefix decisions | C | R | Customer's HAM Process Owner.
Volume estimates per class | I | R | Customer's IT Operations.
Data Policy configuration | R | C | ECS configures based on workbook 05.
UAT — class-related test scenarios | C | R | Customer tests.
Post-go-live class additions | C | R | Customer's HAM Process Owner submits change request.

## Consultant Guide
Asset Classes (Baseline) — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Class Foundations
ServiceNow HAM uses CMDB CI classes (cmdb_ci_computer, cmdb_ci_display, cmdb_ci_mobile_device, cmdb_ci_printer, cmdb_ci_peripheral) extended by alm_hardware. The class hierarchy is OOTB; do not create custom classes for end-user devices at MVP.
Implementation Sequence
• Confirm HAM Application is activated.
• Verify each in-scope CI class exists and is not customized in target instance.
• Configure Number Maintenance per class with the agreed prefix and 5-digit zero-pad.
• Configure Data Policy on alm_hardware: asset_tag unique, serial_number required (if class.track_serial = true), model required.
• Configure UI Policy: assigned_to visible+required when install_status = 'In use'; stockroom visible+required when install_status = 'In stock'.
• Validate against Adoption vs Re-engineering tab before agreeing to any class extension.
Common Pitfalls to Avoid
• Splitting Computer into Laptop / Desktop classes — use form_factor field instead.
• Adding peripherals as a tracked class without active receive process — they will become stale within 30 days.
• Custom CI classes for devices ServiceNow already models — every custom class is upgrade burden.
• Skipping Number Maintenance and asking the customer to assign tags manually — guaranteed duplicates.
• Adding u_ fields without an active customer use case — see Adoption vs Re-engineering tab.

## Adoption vs Re-engineering
Asset Classes (Baseline) — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We have 14 classes in our legacy tool and need them all in ServiceNow." | 3–5 classes at MVP; expand by class in Realization Pack as receive/issue process matures. | Class proliferation produces stale data because each class needs an owner running reconciliation. Most legacy 'classes' are taxonomy without operational process behind them. | "Walk me through the receive-and-issue process for each class. For ones where you can't name the process owner, those are taxonomy, not classes — they belong as fields, not extension tables." | Truly distinct device economies (e.g., medical-grade equipment with FDA tracking) where the receive/issue process and audit cadence are genuinely different.
"Custom CI class for our specialized engineering laptops — they have different attributes." | cmdb_ci_computer with u_ fields for genuinely distinct attributes; or model_category to group within the class. | Custom CI classes create upgrade burden and break OOTB CMDB Health and Discovery patterns. | "Which fields differ? If it's 3–5 fields, they go on cmdb_ci_computer as u_ columns. If it's a fundamentally different device, we'll talk about a class extension after demonstrating the OOTB pattern doesn't fit." | Devices that genuinely need a different table because of distinct lifecycle, distinct tagging discipline, or compliance audit requirements (very rare).
"Custom asset tag format with embedded location and department codes." | Numeric auto-generated tag with class prefix (IT-LAP-00001). Location and department live as references on the asset, not in the tag string. | Encoded tags lock decisions in immutably. When an asset moves location/dept, the tag becomes a lie — and renumbering is forbidden in audit-grade ITAM. | "What happens when an asset moves to a different location? The tag becomes wrong but you can't renumber. The location reference field handles this with audit history. Same for department." | Compliance regimes that mandate physical-stamp tag formats (e.g., DoD asset tags). Even then, drive the requirement to the format spec only — don't embed dynamic data.
"Track every cable and adapter as a hardware asset." | Consumables (alm_consumable) with bulk receive/issue, not individual hardware records. Realization Pack workbook 02. | Serial-tracked records of fungible consumables generate massive noise without ROI. Consumables track quantity by SKU, not individual instance. | "Cables and adapters are consumables — bulk-tracked by SKU and stockroom. Tracking individual cables creates 10× the records with zero ITAM benefit. Realization workbook 02 sets up the consumable pattern." | High-value cables (e.g., specialized lab/medical interconnects worth $500+) where each unit warrants serial tracking.

## ServiceNow Mapping
Asset Classes (Baseline) — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | cmdb_model_category, alm_hardware (and CI class extensions: cmdb_ci_computer, cmdb_ci_display, cmdb_ci_mobile_device)
Field mapping
Workbook column | ServiceNow field | Notes
class_name | model_category.name | Resolved against cmdb_model_category.
servicenow_class | sys_class_name | Validated against live CMDB hierarchy.
description | u_class_description
track_serial | u_track_serial | Drives Data Policy.
track_assignment | u_track_assignment | Drives UI Policy.
track_lifecycle | u_track_lifecycle | If N, install_status frozen at 'In stock'.
expected_volume_mvp | — | Reference only — drives ECS effort estimate, not stored.
Validation & import notes
• Each class becomes a Model Category linked to its CI class.
• Number Maintenance per class drives auto-generated asset_tag.
• Data Policy and UI Policy on alm_hardware reference the class via model_category.