## Instructions
06 — Assignment & Receiving
HAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the workflows that move assets through the baseline lifecycle: Receive (new → In stock), Assign (In stock → In use), Return (In use → Returned), and Retire (any → Retired). Each event is configured as a Flow Designer flow on alm_hardware. Approval is applied only to Retire at MVP.
Who fills this out | Customer-side: HAM Process Owner with the IT Service Manager. Service Desk Manager consulted on Assign/Return ergonomics. ECS-side: Process Consultant for workflow design; Solution Architect for Flow Designer configuration.
When it's due | Process Decisions tab Week 1 of Sprint 0; flows configured in Sprint 1 once states (workbook 05) are live.
How long it takes | Approximately 3 hours of workflow decisions plus 1 hour of UAT scenario design.
Where the data comes from | Existing IT operations runbooks, Service Desk SOPs, audit and security policies (especially for retire flow).
How to use this workbook | Workflows are the operational expression of the lifecycle defined in workbook 05. Make decisions about ownership, approvals, and notifications here; ECS configures Flow Designer flows that match.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Assignment & Receiving — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Who can perform Receive? | Asset Management group + Stockroom owner (stockroom-scoped).
2 | Who can perform Assign? | Service Desk group + Asset Management. Self-service deferred to Realization.
3 | Who can perform Return? | Service Desk group + Asset Management. End-user submits via Employee Center request that triggers Service Desk.
4 | Who can perform Retire? | Asset Management only. Service Desk cannot retire.
5 | Approval on Receive? | None. Receive is operational.
6 | Approval on Assign? | None. Assignment is operational.
7 | Approval on Return? | None. Return is operational.
8 | Approval on Retire? | Yes — HAM Process Owner approves. Audit-grade ITAM rule.
9 | Notification on Receive? | Stockroom owner email.
10 | Notification on Assign? | Assigned user email + their manager (as Foundation Pack Users 01).
11 | Notification on Return? | Stockroom owner email + originally-assigned user email confirmation.
12 | Notification on Retire? | Stockroom owner + Asset Management group + Internal Audit.
13 | Receive form — barcode scan or manual entry? | OOTB Asset List + Receiving Slip (alm_receiving_slip). Barcode optional via mobile.
14 | Assign trigger — direct edit, request, or scan? | Direct edit by Service Desk at issue time. Self-service request added in Realization.
15 | Return trigger — Employee Center request or manual? | Employee Center catalog item 'Return IT Equipment' triggers a fulfillment task on Service Desk.
16 | Retire trigger — manual or rule-based? | Manual at MVP. Rule-based (warranty + age threshold) added in Realization workbook 06.
17 | Failed-flow handling — retry, escalate, or dead-letter? | OOTB Flow retry (3 attempts, 5-min back-off). Failures escalate to Asset Management group inbox.
18 | State-change audit additional to OOTB? | None at MVP — OOTB sys_audit sufficient.

## Dependencies
Assignment & Receiving — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 05 Lifecycle States configured | Not Started | ECS
2 | Foundation Data Pack — Groups (Asset Management, Service Desk) imported | Complete | ECS
3 | Foundation Data Pack — Users imported | Complete | ECS
4 | OOTB Flow Designer activated | Complete | ECS
5 | OOTB notifications activated | Complete | ECS
6 | Employee Center catalog — 'Return IT Equipment' item | Not Started | ECS
7 | sysapproval_approver group for HAM Process Owner approval | Not Started | ECS
8 | Audit team email distribution list | Not Started | Customer

## Configuration Data
Assignment & Receiving — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Workflow Inventory
Receive flow | alm_hardware.install_status: New → In stock | Triggered by new alm_hardware insert
Assign flow | In stock → In use | Triggered by Service Desk action
Return flow | In use → Returned | Triggered by EC catalog item or Service Desk
Retire flow | Any → Retired | Manual trigger; approval required
2. Approvals
Receive approval | None
Assign approval | None
Return approval | None
Retire approval | HAM Process Owner | OOTB sysapproval_approver
3. Notifications
Receive notification | Stockroom owner
Assign notification | Assigned user + their manager
Return notification | Stockroom owner + originally-assigned user
Retire notification | Stockroom owner + Asset Management group + Internal Audit DL
4. Triggers & Trigger Sources
Receive source | alm_receiving_slip OR direct alm_hardware insert | OOTB
Assign source | Service Desk direct edit
Return source | Employee Center catalog item
Retire source | Service Desk Workspace action
5. Failure Handling
Retry policy | 3 attempts, 5-min back-off | OOTB Flow retry
Escalation | Asset Management group inbox

## R&R
Assignment & Receiving — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Workflow design workshop | R | C | ECS facilitates.
Flow Designer flow configuration | R | I | ECS configures.
Approval group / approver mapping | C | R | Customer assigns.
Notification template wording | R | C | ECS provides OOTB; Customer reviews.
Employee Center catalog item creation | R | C | ECS configures; Customer reviews UX.
UAT scenarios design | C | R | Customer testers.
UAT execution | I | R | Customer executes.
Production cutover | R | A | ECS executes; Customer signs off.
Post-go-live workflow tweaks | C | R | Customer's HAM Process Owner submits change.

## Consultant Guide
Assignment & Receiving — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Workflow Foundations
Flow Designer flows on alm_hardware drive each lifecycle event. OOTB notifications via sys_notification. Approvals via sysapproval_approver. Employee Center catalog items via sc_cat_item. No custom Business Rules, no custom Script Includes, no custom approval engine.
Implementation Sequence
• Confirm Flow Designer is activated and Flow Definitions can target alm_hardware.
• Build Receive flow: trigger on alm_hardware insert with install_status=New → set to In stock → notify stockroom owner.
• Build Assign flow: trigger on install_status change to In use → notify assigned_to + manager → log activity.
• Build Return flow: trigger on install_status change to Returned → notify stockroom owner + previously-assigned user → create wipe/inspect task.
• Build Retire flow: manual trigger from Service Desk Workspace → approval activity (HAM Process Owner) → on approval set Retired + stockroom = Pending Disposal → notify Stockroom + Asset Management + Internal Audit.
• Configure Employee Center catalog item 'Return IT Equipment': fulfillment task to Service Desk; on close, triggers Return flow.
• Configure ACLs: Asset Management group can run all flows; Service Desk can run Receive/Assign/Return only; everyone else blocked.
• Test failure path: simulate retire approval rejection — confirm asset stays in original state with rejection reason logged.
Common Pitfalls to Avoid
• Custom Business Rules to enforce state transitions — UI Policy from workbook 05 already does this.
• Approval on every flow — kills throughput. Approval only on Retire.
• Notification spam — limit to actors with operational need. Audit DL for Retire only.
• Custom approval engine — OOTB sysapproval_approver handles this.
• Employee Center catalog item with custom workflow — reuse standard Fulfillment task pattern.

## Adoption vs Re-engineering
Assignment & Receiving — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"Manager approval required before any asset is assigned to their report." | None at MVP. Approval discipline applied to Retire only. | Manager approval on every assignment creates throughput problems and trains managers to rubber-stamp. The risk it mitigates (incorrect assignment) is rare and easily corrected. | "Walk me through the last 12 months of incorrect assignments. If it's <2% of assignments, approval gates create more cost than they prevent. Audit log handles the rest." | Regulated industries where manager approval is mandated (e.g., classified equipment, federal financial).
"Custom emails for every state change with HTML branding." | OOTB notification templates with customer brand applied via OOTB header/footer. | Custom HTML email templates are upgrade burden and frequently break in mobile clients. OOTB templates handle the cases. | "OOTB notifications already include brand header/footer. Wording can be customized. Walk me through the specific use case requiring custom HTML — usually it's a wording change, not a layout change." | Consumer-facing notifications with strict brand guidelines.
"Bulk-assign all New Hire laptops via a single approval at the start of each week." | Per-asset assign at issue time. Bulk pattern available via Service Catalog request 'Onboard New Hires (batch)' in Realization. | Bulk-assign without per-asset confirmation creates assignments to people who haven't started, never started, or got reassigned. Per-asset at issue keeps the data right. | "Bulk assign works for the first hour and then breaks the moment one new hire delays. Per-asset at issue keeps assignments accurate. The 'batch onboard' pattern in Realization gives you the planning view without the data corruption." | Boot-camp scenarios where a class of new hires arrives identically (rare in modern enterprises).
"Dedicated Loaner workflow with auto-return logic." | Loaner is In use + u_loan_until. Auto-return reminders via OOTB scheduled job. Realization Pack workbook 04. | Dedicated Loaner workflow duplicates Assign and Return. Use a date field + reminder job — same operational outcome, less code. | "Loaner is just Assign with a return-by date. The reminder job pings the user and Service Desk. Dedicated workflow is more code without more value." | Loaner-as-service business model (e.g., equipment rental).
"Custom approval matrix that routes to different approvers based on asset value." | Single HAM Process Owner approval at MVP. Tiered approvers (by value, class, or stockroom) added in Realization Pack. | Tiered approvals at MVP means workflow changes for every threshold tweak. Single approver gets the gate working; tiering happens once volume/risk patterns are known. | "Get the gate working with one approver first. After 3 sprints of real data, we can tier intelligently. Pre-tiering is a guess." | Multi-divisional companies where divisions cannot be cross-approved.

## ServiceNow Mapping
Assignment & Receiving — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | alm_hardware (Flow Designer flows on this table)
Field mapping
Workbook column | ServiceNow field | Notes
event | Flow name | Flow Designer.
from_state | Trigger condition | install_status pre-condition.
to_state | State action | install_status set.
performed_by_role | ACL | Restricts who can execute.
requires_approval | Approval activity | If Y, sysapproval_approver insertion.
approver_role | Approval group | Assigned to sys_user_group.
notification_to | Email notification | Comma-separated targets resolved at runtime.
Validation & import notes
• Each event becomes one Flow Designer flow on alm_hardware.
• ACLs restrict who can trigger; OOTB sysapproval_approver handles approvals.
• Notifications use OOTB sys_notification with brand header/footer.
• Employee Center catalog item 'Return IT Equipment' triggers the Return flow on close of fulfillment task.