## Instructions
01 — Stockroom Strategy
HAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Extends the baseline stockrooms from the Foundations Pack into a full multi-stockroom strategy: hierarchy, transfers between stockrooms, in-transit handling for shipping and field operations, repair/RMA stockrooms, capacity rules, and stockroom-level RBAC. Drives full alm_stockroom configuration and adds Stock Rules (alm_stock_rule).
Who fills this out | Customer-side: HAM Process Owner with Stockroom Lead, IT Operations Manager, and Facilities. ECS-side: Process Consultant designs the strategy; Solution Architect configures alm_stockroom extensions and Stock Rules.
When it's due | Process Decisions tab by end of Sprint 2, Week 1. Configuration finalized end of Sprint 2, Week 2. Depends on Foundations Pack workbook 01 being live in production.
How long it takes | Approximately 4–6 hours of strategy decisions plus 2 hours per added stockroom.
Where the data comes from | Foundations Pack workbook 01 baseline; facilities records; field-operations inventory; existing repair/RMA processes; vendor-direct shipping arrangements.
How to use this workbook | Start from the live Foundations stockroom inventory. Each new stockroom must have a named owner, a documented use case, and a fit to one of the OOTB stockroom types (Stockroom, In-Transit, Pending Disposal, Repair). Use Adoption vs Re-engineering tab to defend disciplined stockroom counts.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Stockroom Strategy — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Final stockroom count after Realization? | Total ≤ 12 for most enterprises. Hierarchy via Region → Site cmn_location, not stockroom parent/child. |  | Discipline against per-floor proliferation.
2 | In-Transit stockroom strategy — per shipment lane or per region? | Per region (East, West, etc.). Per-shipment-lane is operational noise.
3 | Repair/RMA stockroom — single shared or per-vendor? | Single shared 'Pending Repair' + per-vendor sub-state via u_repair_vendor field.
4 | Pending Disposal — single corporate or per-region? | Single corporate at Realization (consolidates disposal vendor relationships and certificates).
5 | Transfers between stockrooms — track as events? | Yes. Add 'Transfer' as an event type in workbook 04 IMAC Workflows.
6 | Stock Rules (reorder thresholds) — enable? | Yes for consumables (alm_consumable). Optional for hardware.
7 | Capacity tracking per stockroom? | Yes for hub stockrooms (Receiving, Pending Disposal). Skip for transit.
8 | Field-truck stockrooms — track? | Yes if field operations is in scope. Type = In-Transit, location = vehicle ID.
9 | Stockroom-level cost center? | Yes. Drives Refresh Planning ROI segmentation.
10 | Stockroom hierarchy — true parent/child or location-based? | Location-based via cmn_location. No parent/child on alm_stockroom.
11 | Inactive stockroom retention period? | Indefinite. Inactive ≠ deleted. Historic records preserved.
12 | Stockroom merge — allowed when stockrooms consolidate? | Yes via UI Action 'Merge Stockrooms' that re-points alm_hardware. ECS provides script.
13 | Smart-cabinet / kiosk integration? | Optional. Realization workbook 04 includes self-pickup catalog item pattern.
14 | Stockroom-level audit cadence varies? | Yes. Define per-stockroom audit_frequency (Monthly/Quarterly/Annual) in workbook 07.

## Dependencies
Stockroom Strategy — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Foundations Pack 01 Stockrooms live in production | Complete | Joint
2 | alm_stockroom extensions agreed | In Progress | ECS
3 | Stockroom Lead has assigned owners for every new stockroom | Not Started | Customer
4 | Disposal vendor consolidation decision | Not Started | Customer
5 | Repair vendor list for u_repair_vendor field | Not Started | Customer
6 | Field-operations vehicle inventory (if applicable) | Not Started | Customer
7 | OOTB Stock Rule plugin activated | Not Started | ECS
8 | Cost center mapping confirmed (from Foundation Data Pack 03) | In Progress | Customer

## Configuration Data
Stockroom Strategy — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Stockroom Inventory (Realization)
Total stockrooms after Realization | ~10 | Baseline + 5 added
Receiving stockrooms | 3 (HQ-Receiving, EastHub-Receiving, WestHub-Receiving)
In-Transit stockrooms | FieldOps-Truck-East, FieldOps-Truck-West
Pending Repair stockroom | HQ-Pending-Repair | u_repair_vendor list
Pending Disposal stockroom | HQ-Pending-Disposal | Single corporate
2. Stock Rules (alm_stock_rule)
Consumables — reorder threshold | Min 20%, target 60% of capacity | OOTB
Hardware — reorder threshold | Disabled at MVP | Re-evaluate after first sprint of consumable rules
3. Transfer Workflow
Transfer event | Defined in workbook 04 IMAC Workflows
Transfer approval | Stockroom-source owner approval | sysapproval_approver
4. RBAC
Stockroom owner | sys_user reference | OOTB
Asset Management group ACL | Full CRUD on alm_stockroom + alm_hardware
Service Desk ACL | Read + Receive + Assign + Return
Field-truck owner | Field tech sys_user | Restricted to their assigned truck

## R&R
Stockroom Strategy — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Stockroom strategy workshop | R | C | ECS facilitates.
Disposal vendor consolidation | C | R | Customer's Procurement.
Repair vendor list curation | I | R | Customer's IT Operations.
Stock Rule configuration | R | C | ECS configures.
Capacity decisions | C | R | Customer's Stockroom Lead.
Field-operations stockroom design | C | R | Customer's Field Ops Manager.
alm_stockroom configuration | R | I | ECS configures.
UAT — multi-stockroom transfers | C | R | Customer testers.
Stockroom owner training | R | C | ECS trains; Customer's owners attend.
Production cutover | R | A | ECS executes; Customer signs off.
Post-go-live stockroom additions | C | R | Customer's HAM Process Owner submits change.

## Consultant Guide
Stockroom Strategy — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Stockroom Strategy Foundations
Realization extends Foundations alm_stockroom with type-specific behaviors. In-Transit stockrooms participate in Transfer events; Repair stockrooms have u_repair_vendor; Pending Disposal feeds the disposal pipeline (workbook 06). Stock Rules (alm_stock_rule) drive consumable reorder. Asset Management Workspace shows the stockroom network on a map.
Implementation Sequence
• Confirm Foundations Pack 01 stockrooms are live and stable in production.
• Add new stockrooms via this workbook's Data tab; ECS validates owner references and types.
• Activate Stock Rule plugin if not already on; configure rules for consumables only.
• Build the Transfer flow definition (referenced from workbook 04).
• Configure UI Policy: Pending Disposal stockroom blocks any non-Retired install_status.
• Configure UI Policy: In-Transit stockroom requires u_in_transit_eta date.
• Add u_repair_vendor field to alm_stockroom (choice list) for Repair-type stockrooms.
• Test transfer flow: HQ-Receiving → FieldOps-Truck-East with approval at source owner.
• Validate Asset Management Workspace map view shows full stockroom network.
Common Pitfalls to Avoid
• Adding stockrooms 'because we have a closet there' — closets are not stockrooms; locations are.
• Per-shipment-lane In-Transit stockrooms — operational noise without value.
• Per-vendor Repair stockrooms — vendor goes on u_repair_vendor field, not stockroom.
• Capacity tracking on every stockroom — only hub stockrooms benefit.
• Custom parent/child hierarchy on alm_stockroom — duplicates cmn_location.

## Adoption vs Re-engineering
Stockroom Strategy — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We need a stockroom for every conference room and IDF closet." | Hub model: 3–5 receiving stockrooms + In-Transit + Pending Disposal + Pending Repair = 8–10 total. | Closet stockrooms have no named owner, no audit cadence, and no operational receive process. They become phantom inventory within 90 days. | "For each closet you list, name the owner who'll run the monthly reconciliation. If you can't, it's not a stockroom — it's a location." | Genuinely federated multi-site facilities with separate physical security domains (data centers, federal facilities).
"Per-vendor repair stockroom so we can track which vendor has which device." | Single Pending Repair stockroom + u_repair_vendor field on alm_stockroom. | Per-vendor stockrooms create 5–8 stockrooms with no operational difference. The vendor information belongs on the asset, not on a stockroom. | "u_repair_vendor on the asset gives you the same vendor visibility without 8 extra stockrooms to maintain. Repair process is the same regardless of vendor." | Vendors with separate physical receive locations and distinct chain-of-custody paperwork.
"Hierarchy on alm_stockroom — Region → Site → Stockroom." | Use cmn_location for hierarchy. Stockroom references location. | cmn_location already supports parent/child hierarchy. Duplicating it on alm_stockroom creates two sources of truth. | "cmn_location's hierarchy is what your reports already use. Adding parent/child to alm_stockroom doubles the data; we'll just build reports off cmn_location." | Federated governance with separate stockroom approval chains per region (rare).
"Shared stockroom across multiple cost centers — split the cost center on the stockroom." | Stockroom belongs to one cost center. Multi-cost-center transactions split at the asset event level (Receive, Issue, Retire). | Multi-cost-center stockroom creates accounting ambiguity. Asset-level transactions provide the audit trail Finance needs. | "Cost center splits go on the asset events, not the stockroom. That's where Finance can verify them. Stockroom owns one cost center." | Joint-venture stockrooms with formal cost-allocation rules baked into the JV agreement.
"Stock Rules on every hardware class to auto-trigger replenishment POs." | Stock Rules on consumables only at Realization. Hardware Stock Rules deferred until refresh signals are clean. | Hardware Stock Rules without warranty + utilization signals trigger replenishment of devices nobody needs. Consumables are the right starting point. | "Hardware refresh is driven by warranty, age, and utilization — not stockroom levels. Get Refresh Planning live first; Stock Rules on hardware after that." | Spare-parts stockrooms (e.g., dispatch fleet) where reorder lag = downtime.

## ServiceNow Mapping
Stockroom Strategy — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | alm_stockroom (extended) and alm_stock_rule
Field mapping
Workbook column | ServiceNow field | Notes
stockroom_name | name
description | description
location_name | location | Reference cmn_location.
type | u_stockroom_type | Stockroom/In-Transit/Pending Disposal/Repair (existing).
owner_user_id | u_owner
repair_vendor | u_repair_vendor | Choice list, only for Repair type.
capacity | u_capacity | Number; only for hub stockrooms.
cost_center | cost_center | Reference cmn_cost_center.
audit_frequency | u_audit_frequency | Monthly/Quarterly/Annual.
Validation & import notes
• Stock Rules built separately via alm_stock_rule, scoped to consumables.
• UI Policy enforces Pending Disposal accepts only Retired-state assets.
• Transfer event flow defined in workbook 04 IMAC Workflows.
• Asset Management Workspace consumes stockroom data for map view.