## Instructions
02 — Asset Class & Model Catalog
HAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Extends Foundations workbook 02 to full asset class scope: laptops, desktops, mobile, monitors, peripherals, network gear, server. Establishes the full model catalog including warranties, end-of-support, refresh targets, and standard cost. Drives full cmdb_model_category, cmdb_model, and CI class extension records.
Who fills this out | Customer-side: HAM Process Owner with IT Procurement, IT Operations, and Network Operations leads. ECS-side: Solution Architect for CMDB extension validation; Process Consultant for class scoping discipline.
When it's due | Process Decisions tab by end of Sprint 2, Week 2. Workbook 04 IMAC Workflows depends on this.
How long it takes | Approximately 4–6 hours of class scope decisions plus 1 hour per 5 models added.
Where the data comes from | Foundations Pack workbook 02 baseline; procurement records; vendor catalogs; current CMDB exports; SCCM/Intune model lists.
How to use this workbook | Each class added to the catalog must have a documented receive-issue-retire process and a named class owner. Defer classes without operational discipline. Use Adoption vs Re-engineering tab to push back on class-proliferation requests.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Asset Class & Model Catalog — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Total class count after Realization? | 7–10 classes. Each must have a named owner running the class.
2 | Network gear (switches, routers) — track in HAM or only CMDB/Discovery? | HAM if customer manages physical lifecycle (refresh, RMA). Otherwise CMDB/Discovery only.
3 | Servers — track in HAM? | Track only if servers are physically asset-tagged and follow stockroom lifecycle (rare for cloud-heavy customers).
4 | Peripherals — individual asset records or consumable bulk? | Consumable bulk (alm_consumable). Individual records reserved for high-value items (>$500).
5 | Mobile phones — corporate-issued only or BYOD? | Corporate-issued only. BYOD lifecycle is HR/security domain.
6 | Per-class refresh target? | Yes — drives Refresh Planning. Captured as u_refresh_target_months on cmdb_model_category.
7 | Standard cost per model? | Yes for active models. Drives Refresh Planning ROI and disposal write-off.
8 | Vendor-direct vs distributor — track? | Optional. Realization workbook 05 Procurement uses if procurement workflow needs it.
9 | Configuration variants per model? | Variants stored as cmdb_model rows where build differs materially. Otherwise as alm_hardware fields.
10 | Lifecycle dates per model — capture or import from vendor? | Vendor-published lifecycle dates imported via integration where possible. Manual capture as fallback.
11 | Custom CI class extensions? | None at MVP. Use OOTB cmdb_ci_* with u_ fields for genuinely distinct attributes.
12 | Asset tag prefix — class-prefixed or sub-class? | Class-prefixed. IT-LAP, IT-DSK, IT-MON, IT-MOB, IT-PER, IT-NET, IT-SRV.
13 | Number Maintenance — per class or unified? | Per class (avoids tag collisions when classes diverge in volume).
14 | Image / icon per model? | Optional. Add only for self-service catalog items in Realization.
15 | Decommissioned class handling — retain catalog rows? | Retain inactive. No deletion of cmdb_model rows.

## Dependencies
Asset Class & Model Catalog — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Foundations Pack 02 Asset Classes live in production | Complete | Joint
2 | Foundations Pack 03 Asset Models live in production | Complete | Joint
3 | Network Operations confirms scope (network gear in/out) | Not Started | Customer
4 | Procurement Lead confirms vendor catalogs for full model catalog | Not Started | Customer
5 | OOTB cmdb_model_category and cmdb_model tables available | Complete | ECS
6 | Number Maintenance for added classes | Not Started | ECS
7 | Refresh Planning plugin activated | Not Started | ECS
8 | Standard cost data per active model | Not Started | Customer

## Configuration Data
Asset Class & Model Catalog — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Class Scope (Realization)
Class 1 | Laptop → cmdb_ci_computer | From Foundations
Class 2 | Desktop → cmdb_ci_computer (form_factor=Desktop) | Added
Class 3 | Monitor → cmdb_ci_display | From Foundations
Class 4 | Mobile Phone → cmdb_ci_mobile_device | From Foundations
Class 5 | Peripheral (high-value) → cmdb_ci_peripheral | Added; >$500 only
Class 6 | Network Gear → cmdb_ci_netgear | Added; if in-scope
Class 7 | Server → cmdb_ci_server | Added; if physically managed
2. Model Catalog
Total active models | ~80 | Across 7 classes
Per-class refresh target | u_refresh_target_months | Added on cmdb_model_category
Standard cost per model | u_standard_cost | Required for active models
3. Number Maintenance
Per-class prefixes | IT-LAP, IT-DSK, IT-MON, IT-MOB, IT-PER, IT-NET, IT-SRV
Format | 5-digit zero-padded | OOTB
4. Custom Fields
On cmdb_model | u_model_year, u_end_of_support, u_standard_cost | From Foundations + Realization additions
On cmdb_model_category | u_refresh_target_months, u_class_owner | Realization additions

## R&R
Asset Class & Model Catalog — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Class scope decisions workshop | R | C | ECS facilitates.
Network gear scope decision | C | R | Customer's Network Operations.
Server scope decision | C | R | Customer's Infrastructure team.
Standard cost per model | I | R | Customer's Procurement.
Refresh target per class | C | R | Customer's HAM Process Owner.
Number Maintenance configuration | R | I | ECS configures.
Model catalog import | R | C | ECS imports; Customer reviews.
Class extension validation | R | I | ECS validates against OOTB CMDB.
Refresh Planning activation | R | C | ECS configures plugin.
Per-class owner assignment | C | R | Customer's HAM Process Owner.
UAT — model search and refresh planning | C | R | Customer testers.

## Consultant Guide
Asset Class & Model Catalog — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Catalog Foundations
Realization extends the Foundations catalog. cmdb_model_category gains u_refresh_target_months and u_class_owner. cmdb_model gains u_standard_cost. Refresh Planning plugin (com.snc.itam.refresh) consumes warranty + age + refresh target to forecast replacement waves. Asset Management Workspace shows model utilization and refresh forecast.
Implementation Sequence
• Confirm Foundations Pack 02 and 03 are live and stable.
• Activate Refresh Planning plugin.
• Add u_refresh_target_months and u_class_owner to cmdb_model_category.
• Add u_standard_cost to cmdb_model.
• For each new class, configure Number Maintenance with the agreed prefix.
• Import additional models via Import Set; coalesce on (manufacturer, model_number).
• Configure Refresh Planning rules using warranty + standard cost + refresh target.
• Validate Asset Management Workspace shows correct refresh forecast for one full class.
• Demo refresh-wave preview for one quarter against a live customer dataset.
Common Pitfalls to Avoid
• Adding classes without naming the class owner — every class needs one named, accountable owner.
• Network gear added to HAM without physical asset-tagging discipline — generates audit drift fast.
• Server class enabled but stockroom lifecycle not really tracked — produces stale records.
• Per-variant model rows when the variant is a single SKU difference — use u_ fields on alm_hardware instead.
• Custom CI class extensions for end-user devices — OOTB classes are sufficient.

## Adoption vs Re-engineering
Asset Class & Model Catalog — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"Track every cable, mouse, and adapter as a hardware asset." | Consumables (alm_consumable) bulk-tracked by SKU. High-value peripherals (>$500) only as alm_hardware. | Per-cable hardware records are 10× rows for zero ITAM signal. Consumables track quantity per SKU per stockroom — the right granularity. | "What ITAM decision changes if you can identify cable serial #SN-12345 vs SN-12346? If the answer is 'nothing,' they're consumables." | Specialized cables / docks worth $500+ where individual lifecycle matters.
"Every server in HAM, even cloud VMs." | Physical-managed servers only. Cloud VMs in CMDB via Discovery or vendor connectors, not HAM. | Cloud VMs have no physical lifecycle (receive, retire, dispose). They are CMDB CIs, not assets. | "HAM tracks physical lifecycle — receive, assign, retire, dispose. Cloud VMs don't have that. They go in CMDB via Discovery; CMDB Health drives them." | Never. Use CMDB for non-physical CIs.
"Custom CI class for engineering laptops with 11 fields specific to our workflow." | cmdb_ci_computer with 5–11 u_ fields. No new class. | Custom classes break upgrade compatibility, OOTB CMDB Health, Discovery patterns, and OOTB reporting. u_ fields cost almost nothing. | "Add u_eng_workflow_*, u_lab_assignment, etc. as fields on cmdb_ci_computer. You get all the data you need, OOTB CMDB Health stays clean." | Devices with fundamentally different lifecycle (e.g., medical equipment with FDA recall states).
"Per-variant model row for every laptop config we ship." | One model row per (manufacturer, model_number). Variant data stored on alm_hardware. | Variant rows in cmdb_model multiply the catalog by 5–10× for the same family. Variants are per-instance. | "The catalog is the family. The instance carries the build. Variant data on alm_hardware (cpu, ram, storage, etc.) is OOTB." | Truly identical-build models with no variants.
"Custom approval to add a new model to the catalog." | Customer's HAM Process Owner has write access; ECS doesn't gate. | Approval-on-add creates queue. The risk (a junk model row) is low and easily fixed. | "Catalog hygiene is process discipline by your HAM Process Owner. If a junk model lands, mark it inactive — same outcome, no queue." | Highly regulated environments where catalog additions trigger compliance review.

## ServiceNow Mapping
Asset Class & Model Catalog — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | cmdb_model_category, cmdb_model, alm_consumable (for consumables track)
Field mapping
Workbook column | ServiceNow field | Notes
class_name | model_category.name
servicenow_class | sys_class_name | CI class extension.
class_owner | u_class_owner | Reference sys_user.
refresh_target_months | u_refresh_target_months | On model_category.
manufacturer | manufacturer | Reference core_company.
model_number | model_number
display_name | display_name
warranty_months | warranty_duration | Days = months × 30.
end_of_support | u_end_of_support | ISO date.
standard_cost | u_standard_cost | Numeric currency.
Validation & import notes
• Coalesce on (manufacturer, model_number).
• Refresh Planning rules built post-import using warranty + standard_cost + refresh_target.
• Consumable SKUs imported separately to alm_consumable.
• Number Maintenance per class configured before any alm_hardware import.