## Instructions
04 — IMAC Workflows
HAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Flow Designer flows that drive the full IMAC (Install / Move / Add / Change) lifecycle: Receive (extended from Foundations), Install (new-device-to-user), Move (in-transit between stockrooms), Add (additional asset to existing user), Change (refresh/replace), Return, Repair, Retire, Dispose, Lost/Stolen. Each flow has triggers, ACLs, approvals, and notifications.
Who fills this out | Customer-side: HAM Process Owner with Service Desk Manager and IT Service Manager. ECS-side: Senior Developer for Flow Designer; Process Consultant for IMAC workflow design.
When it's due | Process Decisions tab by end of Sprint 3, Week 1. Configuration finalized by end of Sprint 3, Week 2.
How long it takes | Approximately 6–8 hours of workflow design plus 2 hours per flow for build and test.
Where the data comes from | Foundations Pack workbook 06 (baseline workflows); workbook 03 lifecycle states; existing IMAC runbooks; Service Desk SOPs.
How to use this workbook | Workflows are how the lifecycle states (workbook 03) actually move. Each row defines one flow: trigger, performer, approval, notifications. Use Adoption vs Re-engineering tab to defend OOTB Flow Designer against custom Business Rules and Script Includes.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
IMAC Workflows — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Total flow count at Realization? | ~12 flows: Receive, Install, Move, Add, Change, Return, Repair, RMA-Out, RMA-In, Retire, Dispose, Lost/Stolen.
2 | Install flow trigger source? | Service Catalog 'Onboard New Hire' or 'Replacement Device' request fulfillment.
3 | Move flow trigger source? | Manual from Asset Management Workspace + auto from In-Transit stockroom transfer.
4 | Change (refresh/replace) trigger? | Refresh Planning recommendation OR Service Catalog 'Refresh Device' request.
5 | Repair flow approvals? | Stockroom owner approves dispatch to vendor. RMA-In requires Asset Management close-out.
6 | Retire approval — single tier or class-tiered? | Single tier (HAM Process Owner) at Realization. Tier by value if needed in steady state.
7 | Dispose flow trigger? | Vendor-uploaded certificate triggers via inbound email rule + manual close-out by Asset Management.
8 | Lost/Stolen flow approvals? | IT Security approves; HAM Process Owner co-approves for write-off financial impact.
9 | Notification tier for high-value retirements? | Add Finance + Internal Audit + Asset Owner DL when standard_cost > $5,000.
10 | Self-service Return — Employee Center or Workspace? | Employee Center catalog item 'Return IT Equipment' triggers Service Desk fulfillment.
11 | Self-service Refresh request? | Employee Center catalog item 'Request Refresh' with eligibility check against Refresh Planning.
12 | Bulk-IMAC events (e.g., office relocation)? | Yes via Move flow with batch trigger. Approval by Source-Stockroom owner.
13 | Workflow failure handling? | OOTB Flow retry (3, 5-min back-off). Failures escalate to Asset Management group inbox.
14 | Custom Business Rules on alm_hardware? | None. All logic in Flow Designer or OOTB Data/UI Policy.
15 | Workflow audit trail? | OOTB sys_audit + Flow Designer execution log. No custom audit table.

## Dependencies
IMAC Workflows — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 03 Lifecycle & IMAC States configured | Not Started | ECS
2 | Foundations Pack 06 Assignment & Receiving live | Complete | Joint
3 | OOTB Flow Designer activated | Complete | ECS
4 | Service Catalog items: Onboard New Hire, Replacement Device, Refresh Device, Return IT Equipment | Not Started | ECS
5 | Refresh Planning plugin live (workbook 02 dependency) | Not Started | ECS
6 | IT Security approval workflow integration (Lost/Stolen) | Not Started | Customer
7 | Inbound email rule for vendor certificate uploads | Not Started | ECS
8 | Finance distribution list for high-value retire notifications | Not Started | Customer

## Configuration Data
IMAC Workflows — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Flow Inventory
Receive | From Foundations | Extended with multi-step option
Install | Service Catalog → install_status In use | Fulfilled by Service Desk
Move | Manual + In-Transit transfer | State change to In Transit then In stock
Add | Catalog 'Additional Equipment' → install_status In use
Change (refresh) | Catalog 'Refresh Device' → previous to Pending Disposal, new to In use | Two-asset transition
Return | From Foundations + EC catalog
Repair | In stock/Returned → Pending Repair → vendor RMA
RMA-Out | Pending Repair → vendor | Tracking number captured
RMA-In | vendor → In stock | Receive-back validation
Retire | From Foundations + extended approvals
Dispose | Pending Disposal → Disposed via certificate | Inbound email trigger
Lost/Stolen | In use → Lost or Stolen | Incident link mandatory
2. Approval Matrix
Retire approval | HAM Process Owner | Single tier
High-value retire (cost > $5K) | + Finance + Internal Audit | Notification only
Repair dispatch | Stockroom owner
Lost/Stolen | IT Security + HAM Process Owner
3. Failure Handling
Retry policy | 3 attempts, 5-min back-off | OOTB
Escalation | Asset Management group inbox

## R&R
IMAC Workflows — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
IMAC workflow design workshop | R | C | ECS facilitates.
Service Catalog item design | R | C | ECS designs; Customer reviews UX.
Flow Designer flow build | R | I | ECS builds.
Approval matrix definition | C | R | Customer's HAM Process Owner.
Notification template review | R | C | ECS provides; Customer wordsmiths.
Lost/Stolen integration with IT Security | C | R | Customer's IT Security.
Vendor certificate inbound email setup | R | C | ECS configures; Customer confirms vendor list.
UAT — full IMAC scenarios end-to-end | C | R | Customer testers.
Production cutover | R | A | ECS executes.
Post-go-live workflow tuning | C | R | Customer's HAM Process Owner.

## Consultant Guide
IMAC Workflows — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB IMAC Workflow Foundations
Each IMAC event = one Flow Designer flow on alm_hardware. Service Catalog items trigger Install / Add / Change / Return. Approval via OOTB sysapproval_approver. Notifications via OOTB sys_notification with brand templates. No custom Business Rules, no custom Script Includes.
Implementation Sequence
• Confirm workbook 03 lifecycle states are configured.
• Build Service Catalog items first: Onboard New Hire, Replacement Device, Refresh Device, Additional Equipment, Return IT Equipment.
• Build flows in dependency order: Receive, Install, Add, Move, Change, Return, Repair (RMA-Out + RMA-In), Retire, Dispose, Lost/Stolen.
• Configure approval activities using OOTB sysapproval_approver pointing to designated groups.
• Configure notifications using OOTB sys_notification with brand header/footer.
• Configure inbound email rule for vendor disposal certificates: parse certificate ID, attach to alm_hardware, change state to Disposed.
• Configure ACLs: each flow accessible only to designated groups.
• Test each flow individually with sample data; confirm sys_audit and Flow execution logs.
• Run end-to-end IMAC scenario at integration test: procure → receive → install → add → move → refresh (change) → return → repair → re-stock → retire → dispose.
Common Pitfalls to Avoid
• Custom Business Rules on alm_hardware to handle state transitions — UI Policy + Flow Designer already cover this.
• Approval-on-everything — kills throughput. Approvals only on Retire, Lost/Stolen, Repair-dispatch.
• Custom email parser for vendor certificates — OOTB Inbound Email Action handles this.
• Custom Script Includes for IMAC logic — Flow Designer is sufficient.
• Notification spam — limit DLs to operational need.
• Self-service Refresh without eligibility check — explosion of refresh requests.

## Adoption vs Re-engineering
IMAC Workflows — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"Custom Business Rule to handle every state transition because Flow Designer is too slow." | Flow Designer for all state-transition workflows. | Custom Business Rules are upgrade burden, hidden from non-developers, and create double-trigger problems with OOTB UI Policy. Flow Designer is the OOTB-recommended path. | "Flow performance is rarely the actual bottleneck — measure the live execution time before assuming Business Rules are needed. We've delivered 12 IMAC events in Flow Designer with sub-second execution." | Genuinely high-volume synchronous transitions (>1000/sec). Almost never the case in HAM.
"Custom approval engine because OOTB approvals don't support our workflow." | OOTB sysapproval_approver with delegated-approval and multi-stage support. | Custom approval engines are upgrade burden, hidden from auditors, and break OOTB Service Portal approval views. | "Walk me through the specific approval pattern. OOTB supports parallel approvers, group approvals, delegated approvers, and multi-stage. The custom engine is rarely actually needed." | Highly specialized industries with bespoke regulatory approval flows (FedRAMP, certain banking).
"Auto-approve everything from a trusted requester role." | Approval still records who approved (the requester); no auto-approve. | Auto-approve breaks the audit trail. The point of approval is the audit record. | "Even if it always passes, the approval record proves the requester is the trusted role. Auto-approve removes that proof." | Never.
"Custom UI Page for the IMAC dashboard." | Asset Management Workspace + OOTB dashboards. | Custom UI Pages don't get OOTB upgrades, miss platform-wide UX improvements, and require ongoing maintenance. | "Asset Management Workspace + Performance Analytics dashboard cover what you've described. Walk me through what's specifically missing — it's usually a config gap, not a custom-UI need." | User-base trained on a specific bespoke UX with documented productivity gain over Workspace.
"Email parser to auto-create asset events from vendor confirmations." | OOTB Inbound Email Action with regex extraction. | Custom email parsers break the moment vendors change templates. OOTB Inbound Email Actions handle the common patterns. | "OOTB inbound email rules with regex patterns handle vendor confirmations. Vendor template drift breaks any parser, OOTB or custom — at least with OOTB you're not maintaining the parser yourself." | Highly structured EDI-like vendor email feeds.

## ServiceNow Mapping
IMAC Workflows — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | alm_hardware (Flow Designer flows), sc_cat_item, sysapproval_approver, sys_notification
Field mapping
Workbook column | ServiceNow field | Notes
event | Flow name
trigger_source | Flow trigger config | Catalog item / state change / inbound email.
from_state | Trigger condition
to_state | State action
performed_by_role | ACL
requires_approval | Approval activity
approver_role | Approval group
notification_to | sys_notification
Validation & import notes
• 12 Flow Designer flows on alm_hardware.
• Service Catalog items provide self-service triggers.
• OOTB sysapproval_approver handles approvals.
• Inbound email rule handles vendor disposal certificates.
• All notifications via OOTB sys_notification with brand templates.