## Instructions
05 — Procurement & Intake
HAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines how new assets enter the ServiceNow HAM environment from procurement and the receiving dock. Covers PO matching, vendor-direct shipments, multi-step receive (received → inspected → in stock), and pre-population of asset metadata from PO data. Drives configuration of alm_purchase_order, alm_receiving_slip, and the procurement integration.
Who fills this out | Customer-side: HAM Process Owner with Procurement Lead, Stockroom Lead, and Finance. ECS-side: Solution Architect for procurement integration; Process Consultant for intake workflow design.
When it's due | Process Decisions tab by end of Sprint 3, Week 1. Configuration finalized end of Sprint 3, Week 2. Depends on workbooks 01 (Stockroom Strategy) and 02 (Class & Model Catalog).
How long it takes | Approximately 4–5 hours of decisions plus 2 hours per integration tested.
Where the data comes from | Existing PO system (Coupa, Ariba, SAP, Oracle Procurement); current vendor list; existing receive process documentation.
How to use this workbook | Procurement integration depth varies by customer. Decide integration scope first, then design fallback for non-integrated vendors. Use Adoption vs Re-engineering tab to defend OOTB intake patterns.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Procurement & Intake — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Procurement integration depth? | PO header + lines via REST/SFTP from Coupa/Ariba/SAP. Receipts back to procurement post-receive.
2 | Vendors in scope for direct integration? | Top 5 by spend volume. Smaller vendors via manual receive.
3 | PO-to-asset matching key? | PO line item + serial number. Serial captured at receive.
4 | Multi-step receive (received → inspected → in stock)? | Yes for high-value or regulated devices. Single-step otherwise.
5 | Vendor-shipped-direct-to-user — handle? | Yes via 'Direct Ship' receive type. Asset goes In Transit then auto-In use after delivery confirmation.
6 | Pre-asset-tag on receive — printed labels or vendor-applied? | Vendor-applied where possible. Otherwise generate at receive via Number Maintenance.
7 | PO data fields auto-populated to asset? | manufacturer, model_number, model_year, standard_cost, warranty_months, acquired_date.
8 | Discrepancy handling — PO line vs received quantity? | Hold receipt; notify Procurement + Stockroom owner; resolve before close.
9 | Damage-on-arrival — separate workflow? | Yes. State Pending Repair + u_hold_reason='RMA Pre-Receipt'. Notify vendor.
10 | Cost capture — PO price or list price? | PO price as actual_cost; list price as standard_cost on cmdb_model.
11 | Tax and shipping allocation per asset? | Optional. If captured, allocated proportionally across PO lines.
12 | Asset Owner field at receive? | Stockroom owner by default. Reassigned on Install event.
13 | Receive-to-CMDB CI auto-create? | Yes for tracked classes (Computer, Display, Mobile). cmdb_ci record created in same flow.
14 | Procurement notification on receive? | Yes. PO match-to-receive triggers procurement closure notification.
15 | Bulk receipt — single PO with hundreds of items? | Yes via OOTB alm_receiving_slip with line-by-line scan or bulk CSV upload.

## Dependencies
Procurement & Intake — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 01 Stockroom Strategy live | Not Started | ECS
2 | Workbook 02 Class & Model Catalog finalized | In Progress | Joint
3 | Procurement system access (API credentials or SFTP) | Not Started | Customer
4 | Top-5 vendor list with PO formats | Not Started | Customer
5 | OOTB alm_purchase_order and alm_receiving_slip activated | Not Started | ECS
6 | Finance acknowledgment of cost field mapping | Not Started | Customer
7 | Vendor-shipped-direct delivery confirmation source | Not Started | Customer
8 | Receiving dock barcode scanner availability | Not Started | Customer

## Configuration Data
Procurement & Intake — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Procurement Integration
Integration source | Coupa REST API + SFTP for nightly batch | OOTB + ECS adapter
Sync frequency | PO created/updated → near-real-time; receipts back → hourly batch
PO-to-asset key | po_number + po_line + serial_number
2. Receive Modes
Single-step receive | Standard for low-value classes
Multi-step receive | received → inspected → in stock for Mobile, Server, Network
Direct Ship | State In Transit → In use after delivery confirmation
Bulk receipt | alm_receiving_slip with CSV upload | Up to 500 lines per slip
3. PO-to-Asset Field Mapping
Auto-populated from PO | manufacturer, model_number, model_year, standard_cost, warranty_months, acquired_date, vendor
Captured at receive | serial_number, asset_tag, stockroom
4. Notifications
On receive complete | Stockroom owner + Procurement
On discrepancy | Procurement + Stockroom owner + Asset Management group
On damage-on-arrival | Vendor + Procurement + Asset Management
5. Failure Handling
Procurement integration retry | 3 attempts, 15-min back-off | OOTB
PO mismatch escalation | Asset Management group inbox

## R&R
Procurement & Intake — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Procurement integration design | R | C | ECS designs; Customer's Procurement validates.
Vendor list curation | I | R | Customer's Procurement.
Receive workflow design | R | C | ECS designs.
Procurement system credential provisioning | I | R | Customer's IT Security + Procurement.
PO field mapping | R | C | ECS configures.
Multi-step receive activation | R | C | ECS configures.
Direct Ship workflow | R | C | ECS configures.
Discrepancy escalation list | C | R | Customer assigns.
UAT — full procurement-to-receive scenarios | C | R | Customer testers.
Production cutover | R | A | ECS executes.

## Consultant Guide
Procurement & Intake — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Procurement & Intake Foundations
alm_purchase_order and alm_receiving_slip are the OOTB tables. ServiceNow Procurement plugin (com.snc.itam.procurement) bridges to external procurement via REST/SFTP. Receive flow updates alm_hardware from PO data. Multi-step receive uses sub-states via u_hold_reason.
Implementation Sequence
• Activate ServiceNow Procurement plugin.
• Configure procurement integration (REST or SFTP) per top-5 vendors.
• Build PO ingestion: nightly batch updates alm_purchase_order with header + lines.
• Build receive flow: serial scan → match to PO line → populate alm_hardware → set state.
• Configure multi-step receive UI Policy: received → inspected → in stock with u_hold_reason at each step.
• Build Direct Ship flow: PO line marked direct → asset auto-creates In Transit → on delivery confirmation, state changes to In use.
• Build discrepancy handling: variance triggers hold + notification.
• Build damage-on-arrival flow: Pending Repair + u_hold_reason='RMA Pre-Receipt'.
• Configure receipts-back notification to procurement system.
• Test end-to-end: PO created → asset received → CMDB CI created → procurement notified.
Common Pitfalls to Avoid
• Integrating every vendor at MVP — top 5 by spend cover most volume.
• PO-to-asset matching by description text — fragile; use line + serial.
• Auto-creating PO records from receive without external PO source — creates orphans.
• Skipping discrepancy handling — guarantees mystery missing assets later.
• Direct Ship without delivery confirmation source — assets stuck In Transit forever.

## Adoption vs Re-engineering
Procurement & Intake — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"Integrate every procurement vendor on day one." | Top 5 by spend at Realization. Smaller vendors via manual receive. | Procurement integrations have non-trivial maintenance cost (cred rotation, format drift, vendor mergers). Top 5 covers ~80% of volume; the long tail isn't worth the cost. | "Top 5 by spend covers ~80% of volume. The long tail is manual receive — same data quality, no integration burden. Add vendor 6 only when its volume justifies the build." | Heavily fragmented vendor base where no top-5 dominates.
"Custom PO-to-asset matching using description text fuzzy match." | Strict match on PO line + serial number captured at receive. | Description-text matching breaks every vendor template change. Strict matching is unambiguous and audit-defensible. | "Description matches break the moment a vendor renames a SKU. PO line + serial is unambiguous and reconciles at audit time." | Vendors that systematically don't provide line numbers (rare in modern ERP).
"Auto-receive — when PO closes in procurement system, automatically mark assets in stock." | Manual receive at the dock with serial scan. Procurement closure ≠ physical receipt. | Procurement-driven receive bypasses the physical scan that confirms what actually arrived. Vendors lose, mis-ship, or partial-ship — auto-receive masks this. | "Procurement says it's been ordered. Receive says it's been received. They're different events. The dock scan is the truth." | Vendor-managed inventory programs with formal stock-room access agreements.
"Pre-assign assets to users at PO time so they're ready when received." | Receive in Stockroom; Install (assign) when issued. Pre-assignment created via Service Catalog 'Onboard New Hire' that holds until receive. | Pre-assignment at PO is brittle — new hire delays, PO changes, mis-ships break the chain. Catalog-based pending request is OOTB and self-corrects. | "Catalog 'Onboard New Hire' creates the pending assignment; receive triggers fulfillment. Same outcome, no broken pre-assignments." | Customer-specific staffing systems with deeply integrated provisioning.
"Custom inventory cost calculation — overhead allocation, currency conversion, tax tiers." | Standard cost on cmdb_model + actual cost on alm_hardware. Tax/shipping allocated proportionally if captured. | Custom cost calculation duplicates Finance's general ledger. ServiceNow HAM is not the cost-of-goods-sold system. | "HAM tracks cost as ITAM data. Detailed cost accounting is Finance's GL. Pulling actual cost from PO + standard cost from model gives ITAM what it needs without duplicating the ERP." | Customer chose ServiceNow as their asset accounting system (rare and inadvisable).

## ServiceNow Mapping
Procurement & Intake — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | alm_purchase_order, alm_purchase_order_line, alm_receiving_slip, alm_hardware
Field mapping
Workbook column | ServiceNow field | Notes
po_number | alm_purchase_order.number
po_line | alm_purchase_order_line.line_number
vendor | vendor | Reference core_company.
manufacturer | manufacturer | Reference core_company.
model_number | model.model_number | Resolved against cmdb_model.
standard_cost | model.u_standard_cost
po_actual_cost | cost | Actual cost on alm_hardware.
warranty_months | warranty_duration | Days = months × 30.
acquired_date | acquired
serial_number | serial_number | Captured at receive.
asset_tag | asset_tag | Generated or captured.
Validation & import notes
• Procurement integration via REST/SFTP per vendor.
• Receive flow on alm_receiving_slip triggers alm_hardware creation.
• Direct Ship flow updates state via delivery confirmation source.
• Discrepancy holds receipt with notification.