## Instructions
08 — Integrations & KPIs
HAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the integration dependencies that keep HAM data honest and the KPIs that prove the program is working. Covers SCCM (Service Graph Connector), Intune, AD/Entra ID (user reconciliation), HR (onboarding/offboarding triggers), and the HAM KPI dashboard. Cross-references the existing Sprint 5 Service Graph and Integrations workbooks.
Who fills this out | Customer-side: HAM Process Owner with HR Operations Lead, IT Security, and Solution Architect. ECS-side: Solution Architect for integration design; Process Consultant for KPI selection.
When it's due | Process Decisions by end of Sprint 4, Week 2. Configuration finalized end of Sprint 5, Week 1. Depends on existing Service Graph and Integration workbooks (Sprint 5).
How long it takes | Approximately 6–8 hours of decisions plus 2 hours per integration tested.
Where the data comes from | Existing Sprint 5 Service Graph workbook (11), Integrations workbook (13), Integration Accelerator Pack workbooks (AD, Intune, SCCM, SSO); HR onboarding/offboarding system; ITAM industry KPI references.
How to use this workbook | Integrations and KPIs are how HAM Realization closes the loop. Decide integration scope, owner-of-truth rules, and KPI cadence. Use Adoption vs Re-engineering tab to defend OOTB integration patterns.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
Dependencies | Other Packs and source data that must be in place before this workbook can be imported.
Configuration Data | Final OOTB-aligned configuration parameters used by ECS to configure ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership for each activity.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant.
Adoption vs Re-engineering | Pushback scenarios when the customer asks for legacy patterns; OOTB defense language.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.

## Process Decisions
Integrations & KPIs — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled; Customer fills Decision column in workshop.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | SCCM scope — workstations only or +servers? | Both per Integration Pack workbook 03 SCCM. Reuse existing SGC config.
2 | Intune scope — corporate mobile only? | Yes. Personal devices excluded per Integration Pack workbook 04 Intune.
3 | AD/Entra reconciliation — user owner-of-truth? | AD/Entra is owner-of-truth for user_id, manager, department. HAM is owner-of-truth for assigned_to.
4 | HR onboarding integration — auto-trigger Install event? | Yes. HR creates user → Service Catalog 'Onboard New Hire' auto-fires.
5 | HR offboarding integration — auto-trigger Return event? | Yes. Termination event triggers Catalog 'Recover IT Equipment' fulfillment task.
6 | HR system — direct integration or via Foundation Data Pack? | Direct integration to HR for onboarding/offboarding events. Foundation Data for static user attributes.
7 | Conflict resolution — HAM vs SCCM/Intune assigned_to? | SCCM/Intune wins for last_seen + login_user. HAM wins for the formal assigned_to (driven by Install event).
8 | Discovery integration — extend asset coverage? | Yes for tracked classes. Discovery-found assets land in CMDB; manual reconcile to HAM.
9 | KPI selection — how many top-level KPIs? | 5 top-level: Utilization, Lifecycle Aging, Audit Variance, Refresh Forecast, Disposal Aging.
10 | KPI dashboard audience — who consumes? | HAM Process Owner (operational), CIO (executive summary), Internal Audit (variance focus).
11 | KPI cadence? | Daily auto-refresh. Monthly review meeting with HAM Process Owner + Internal Audit.
12 | Predictive Intelligence on HAM data? | Defer to post-go-live. Need 90+ days of clean data first.
13 | External KPI publication — to executive dashboard? | Yes. Monthly snapshot to existing exec BI tool via OOTB REST.
14 | Integration failure escalation? | Each integration has a named owner; failures notify owner + Asset Management group.
15 | Integration credential rotation cadence? | 90 days per security policy; managed via Credentials store with rotation reminder.

## Dependencies
Integrations & KPIs — Dependencies
Other Packs and source data that must be in place before this workbook can be imported.
# | Dependency | Status | Owner | Due | Notes
1 | Sprint 5 Service Graph workbook complete | Complete | Joint
2 | Sprint 5 Integrations workbook complete | Complete | Joint
3 | Integration Accelerator Pack — AD, Intune, SCCM, SSO complete | Complete | Joint
4 | HR onboarding/offboarding API access | Not Started | Customer
5 | AD/Entra ID sync configured | Complete | ECS
6 | OOTB Performance Analytics activated | In Progress | ECS
7 | OOTB Refresh Planning live | Not Started | ECS
8 | Executive BI tool API endpoint | Not Started | Customer
9 | Discovery / Service Graph for tracked classes | In Progress | ECS

## Configuration Data
Integrations & KPIs — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are example placeholders to confirm in workshop.
Field / Setting | Value | Notes
1. Integration Inventory
SCCM (Service Graph Connector) | Per Integration Pack workbook 03 | Daily delta
Intune | Per Integration Pack workbook 04 | Daily delta
AD/Entra ID | Per Integration Pack workbook 01 | Continuous
SSO | Per Integration Pack workbook 02
HR onboarding/offboarding | REST integration to HR system | Realization-added
Discovery | Tracked classes only | Per Sprint 5 workbooks
2. Owner-of-Truth Rules
User identity (user_id, manager, department) | AD/Entra
Endpoint last-seen + login | SCCM (workstations) / Intune (mobile)
Asset assigned_to (formal) | HAM (driven by Install event)
Asset_tag, stockroom, lifecycle_state | HAM
Configuration items + relationships | CMDB (Discovery)
3. KPI Set
KPI 1 — Utilization | % In use vs total active | Performance Analytics
KPI 2 — Lifecycle Aging | Avg days in current state per class
KPI 3 — Audit Variance | % variance per stockroom
KPI 4 — Refresh Forecast | # devices warranty-expiring next 90/180/365 days
KPI 5 — Disposal Aging | Avg days from Pending Disposal to Disposed
4. Dashboards
HAM Process Owner dashboard | All 5 KPIs + audit findings + integration status
CIO dashboard | 3 summary KPIs (Utilization, Refresh Forecast, Disposal Aging)
Internal Audit dashboard | Audit Variance + Lost/Stolen rate + open findings
5. Refresh Cadence
KPI auto-refresh | Daily | Performance Analytics
Executive BI snapshot | Monthly
Internal Audit review | Monthly

## R&R
Integrations & KPIs — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Integration scope decisions | R | C | ECS facilitates.
HR onboarding/offboarding integration design | R | R | Joint.
Owner-of-truth rules sign-off | C | R | Customer's HAM Process Owner.
KPI selection | C | R | Customer's HAM Process Owner.
Performance Analytics indicator configuration | R | I | ECS configures.
Dashboard build | R | C | ECS builds.
HR API access provisioning | I | R | Customer's IT Security + HR.
Credential rotation policy | R | C | ECS configures schedule; Customer owns secrets.
Integration owner assignment | C | R | Customer.
UAT — onboarding-to-asset and offboarding-to-recover | C | R | Customer testers + HR.
Executive BI feed configuration | R | C | ECS configures.
Production cutover | R | A | ECS executes.
Post-go-live KPI review meeting | I | R | Customer's HAM Process Owner + Internal Audit.

## Consultant Guide
Integrations & KPIs — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Not for customer distribution.
OOTB Integrations & KPI Foundations
Integrations leverage existing Service Graph (SCCM, Intune), Integration Pack (AD, SSO), and Foundation Data Pack patterns. New for Realization: HR onboarding/offboarding integration triggering Service Catalog items. KPIs via OOTB Performance Analytics with 5 top-level indicators. Executive BI feed via OOTB REST.
Implementation Sequence
• Confirm Sprint 5 Service Graph and Integrations workbooks are live.
• Confirm Integration Accelerator Pack (AD, Intune, SCCM, SSO) is live.
• Build HR onboarding integration: HR REST → 'Onboard New Hire' Service Catalog request.
• Build HR offboarding integration: termination → 'Recover IT Equipment' Service Catalog request.
• Configure owner-of-truth rules in CMDB IRE.
• Build the 5 Performance Analytics indicators.
• Build HAM Process Owner dashboard with all 5 indicators + open findings + integration status.
• Build CIO dashboard (3 summary KPIs).
• Build Internal Audit dashboard.
• Configure executive BI feed via REST: monthly snapshot of dashboard data.
• Configure credential rotation reminders.
• Test end-to-end: HR creates user → Onboard request → asset received and installed → KPI updates daily.
• Test offboarding: termination → Recover request → asset returned → KPI updates.
Common Pitfalls to Avoid
• Too many KPIs — 5 top-level is the right cardinality for executive consumption.
• Owner-of-truth rules without conflict resolution — circular updates.
• HR integration without offboarding equivalent — assets stay assigned to terminated users.
• Custom dashboard widgets — OOTB Performance Analytics has the patterns.
• Predictive Intelligence at MVP — needs 90+ days of clean data.
• Credential rotation without reminder — integrations break silently.

## Adoption vs Re-engineering
Integrations & KPIs — Adoption vs Re-engineering
When the customer says "but our old tool did X." Use these to defend OOTB before agreeing to customize.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"15 KPIs because each team wants their own." | 5 top-level + drill-down. Each team consumes filtered views, not separate KPIs. | 15 KPIs at the top level dilutes attention. Each team's questions are usually filtered views of the 5 top-level indicators. | "Walk me through each team's question. Usually it's a filter on Utilization, Lifecycle Aging, or Audit Variance — not a new top-level KPI." | Distinct business units with materially different ITAM economics.
"Real-time KPI refresh — sub-minute updates." | Daily auto-refresh with on-demand recalculation. | ITAM KPIs measure trends, not real-time signal. Sub-minute refresh creates load without informing decisions. | "What ITAM decision requires sub-minute KPI signal? Daily refresh + on-demand drill-down covers operational and executive cadence." | Real-time fleet operations where ITAM = service availability.
"HR integration only for onboarding — we'll handle offboarding manually." | Both onboarding and offboarding integrated. | Manual offboarding is the #1 source of asset-still-assigned-to-terminated-employee findings. The integration eliminates the most common audit drift. | "Offboarding is where assets get lost. Manual offboarding finds your former employees still owning laptops 6 months later. The integration is the fix." | Manual-process organizations where HR offboarding is genuinely consistent (very rare).
"Custom integration code instead of OOTB Service Graph Connectors." | Service Graph Connectors for SCCM and Intune. OOTB IntegrationHub for HR. | Custom integration code is upgrade burden, hidden security exposure, and ongoing maintenance. OOTB connectors are tested and supported. | "What's specifically wrong with the OOTB Service Graph Connector? Usually it's a config gap, not a connector limitation. Custom code costs more than the configurable patterns can do." | Genuinely unsupported source systems (rare in modern enterprise stacks).
"Bypass owner-of-truth rules for ad-hoc data fixes." | All updates flow through owner-of-truth rules. Ad-hoc fixes go via 'Correct State' UI Action with audit log. | Bypassing owner-of-truth makes the data unreliable. The next reconciliation cycle reverts the fix and surprises the customer. | "Ad-hoc fixes that bypass IRE get reverted on next reconciliation. 'Correct State' UI Action gives you the same outcome with audit trail." | Never. This is data discipline.

## ServiceNow Mapping
Integrations & KPIs — ServiceNow Mapping
Internal reference — target tables, OOTB features used, and import behavior.
Primary table(s) | OOTB integration tables, Performance Analytics indicators, sys_dashboard
Field mapping
Workbook column | ServiceNow field | Notes
integration_name | Service Graph Connector / IntegrationHub flow
scope | Connector scope config
owner_of_truth | CMDB IRE rule
kpi_name | pa_indicator | Performance Analytics.
kpi_calculation | pa_indicator formula
Validation & import notes
• Cross-references existing Service Graph (Sprint 5), Integrations (Sprint 5), and Integration Accelerator Pack workbooks.
• HR integration is the new build at Realization — REST in for onboarding, REST in for offboarding.
• All KPIs via OOTB Performance Analytics indicators.
• Dashboards via OOTB sys_dashboard with PA widgets.
• Executive BI feed via OOTB outbound REST.