## Instructions
06 — Knowledge Management
ITSM Process Pack · ECS Federal · ServiceNow Practice
Purpose | Knowledge Management captures and curates the articles that drive AI Search results, Virtual Agent answers, and Service Desk efficiency. KM is the most-leveraged process for AI ROI — without curated KB content, AI Search returns noise and Virtual Agent deflects nothing. This workbook captures the KB structure, lifecycle, audience model, and migration approach from legacy KB.
Who fills this out | Customer-side: Knowledge Manager (named role), KM Process Owner, subject-matter experts. ECS-side: Solution Architect, Process Consultant.
When it's due | Process Decisions in Sprint 1; configuration in Sprint 5 alongside Employee Experience build.
How long it takes | 3–5 hours of decision-making, plus the heavier work of curating articles for migration (per article: 5–15 minutes review).
Where the data comes from | Existing KB inventory, article usage analytics, subject-matter expert interviews.
How to use this workbook | Same workflow. KM has the unique constraint that the migration work (curating articles) happens AFTER decisions are made — so decisions need to be tight to keep curation focused.
Tabs in this workbook
Instructions | How to use this workbook (this tab).
Process Decisions | Key decisions to make collectively. ECS recommendation pre-populated; customer confirms or proposes alternative with rationale.
Dependencies | Other Packs and source data that must be in place before this process can be configured.
Configuration Data | The final OOTB-aligned configuration parameters — used by the consultant to build in ServiceNow.
R&R | RACI matrix — ECS vs Customer ownership.
Consultant Guide | Internal reference for the ECS Solution Architect / Process Consultant building the configuration.
Adoption vs Re-engineering | Pushback scenarios — when the customer asks for legacy patterns, how to redirect to OOTB.
ServiceNow Mapping | Internal reference — target tables and OOTB features used.
Common pitfalls
• | Porting all legacy KB articles without curation — stale articles return wrong answers in AI Search.
• | Custom KB types per audience — OOTB KBs with audience criteria handle this.
• | Manual approval workflow for every article — kills the publication pipeline.
• | Articles in SharePoint with link-back from ServiceNow — AI Search can't index them.
Who to ask | Your engagement's ECS Solution Architect.

## Process Decisions
Knowledge Management — Process Decisions
Decisions to make collectively. ECS recommendation pre-populated; customer confirms or proposes alternative with rationale.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | KB structure — by audience, function, or topic? | By audience (IT Knowledge Base for IT staff; Employee Knowledge Base for end users) with topic categorization within each
2 | Article types | How-to (procedure), FAQ, Troubleshooting, Reference, Known Error (linked from Problem)
3 | Audience criteria | User Criteria (sys_user_criteria) — by group, location, or role
4 | Article lifecycle | Draft → Review → Published → Retired (OOTB lifecycle)
5 | Approval workflow | OOTB Knowledge Approval — Knowledge Manager approves new and major-revision articles
6 | Article ownership | Each article has named owner; quarterly review for relevance
7 | Retirement criteria | Articles not viewed in 12 months OR flagged as outdated → Knowledge Manager review → retire or refresh
8 | AI Search optimization | Title clarity, keyword tagging, Short Description population, audience scoping all required
9 | Virtual Agent topic seeding | Top 20 articles seeded as VA topic blocks
10 | Migration from legacy KB | Curate, don't lift — per article: keep & port, edit & port, retire
11 | New article workflow | Author → Self-review → Knowledge Manager approval → Publish (1–3 day cycle)

## Dependencies
Knowledge Management — Dependencies
Other Packs and source data that must be in place before this process can be configured.
# | Dependency | Status | Owner | Due | Notes
1 | Foundation Data Pack — Users, Groups complete (for audience criteria) | Complete | Customer
2 | Employee Center configured | Complete | ECS
3 | AI Search activated | In Progress | ECS
4 | Virtual Agent designer access | Complete | ECS
5 | Knowledge Manager named | Not Started | Customer
6 | Legacy KB inventory exported with usage stats | Not Started | Customer
7 | Subject-matter experts identified per top-level KB category | Not Started | Customer
8 | Article retirement criteria approved by Knowledge Manager | Not Started | Customer

## Configuration Data
Knowledge Management — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are recommendations; replace with customer-confirmed values.
Field / Setting | Value | Notes
1. Knowledge Bases
KB 1 | IT Knowledge Base — IT staff (Service Desk, IT Ops) | Audience: IT roles
KB 2 | Employee Knowledge Base — all employees | Audience: all active users
KB 3 (optional) | Confidential KB — restricted (HR, Finance) | Audience: specific groups; future phase
2. Categories (per KB)
IT KB top-level | Network, Compute, Identity, Security, Applications
Employee KB top-level | Get Help, How-to, Office Resources, Policies, Contacts
3. Article Lifecycle
States | Draft, Review, Published, Retired | OOTB
Default approval | Knowledge Manager review for new + major revisions | OOTB
Auto-retire threshold | 12 months without view + 6 months since last update | OOTB scheduled job
4. Audience and Visibility
Audience mechanism | User Criteria (sys_user_criteria) | OOTB
Default visibility | Article visible to KB audience unless restricted
5. AI Search and Virtual Agent
AI Search indexing | Activated for both KBs
VA topic seeding | Top 20 articles by view count
AI feedback loop | User article feedback (helpful/not) feeds AI re-ranking | OOTB
6. Migration
Migration approach | Curate-then-port: keep, edit, retire — no mass lift
Migration timeline | Sprint 5
Per-article review estimate | 5–15 min

## R&R
Knowledge Management — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Process Decisions facilitation | R | C
KB structure design | R | C | ECS designs OOTB structure.
Article curation (legacy review) | C | R | Customer SMEs decide keep/edit/retire.
Article authoring (new content) | C | R | Customer SMEs author.
Knowledge Manager training | R | C
AI Search configuration | R | I | ECS configures.
Virtual Agent topic seeding | R | C | ECS seeds; Customer reviews accuracy.
Audience criteria configuration | R | C | ECS configures.
UAT for AI Search results | R | R | Joint.
Production cutover | R | A
Long-term ownership of KM | I | R | Customer's Knowledge Manager.

## Consultant Guide
Knowledge Management — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant. Step-by-step ServiceNow updates.
OOTB KM Foundations
Use OOTB Knowledge Management (com.snc.knowledge_management). KBs are records in kb_knowledge_base; articles in kb_knowledge. Audience via User Criteria. Lifecycle via OOTB approval workflow.
Implementation Sequence
• Activate Knowledge Management plugin (OOTB).
• Activate Knowledge Service Portal extensions and Employee Center KB widget.
• Create the two KBs per Process Decisions (IT Knowledge Base, Employee Knowledge Base).
• Create top-level categories per KB.
• Configure User Criteria for each KB audience.
• Configure OOTB Knowledge Approval workflow; assign Knowledge Manager.
• Configure auto-retire scheduled job (OOTB; configure threshold per Process Decisions).
• Activate AI Search; configure indexing for both KBs.
• Configure feedback collection (Helpful/Not Helpful) on articles.
• Curate legacy KB: load to staging KB; SMEs review per category; mark keep/edit/retire; port keepers to live KBs.
• Seed Virtual Agent topics: top 20 articles by view count → VA topic blocks.
• Configure Performance Analytics: article views, helpful rate, search-result clickthrough, deflection rate.
Common Pitfalls to Avoid
• Mass-porting legacy articles without curation — stale content corrupts AI Search.
• Custom KB types instead of OOTB KB + audience criteria.
• Approval workflow with multiple required reviewers — slows publication; one reviewer (Knowledge Manager) is the OOTB recommendation.
• Articles in external sources (SharePoint, Wiki) — not indexable by AI Search.
• Skipping retirement — stale articles return wrong answers as platform ages.
References
• ServiceNow Docs: Knowledge Management
• ServiceNow Docs: AI Search
• ServiceNow Docs: Virtual Agent Topic Discovery

## Adoption vs Re-engineering
Knowledge Management — Adoption vs Re-engineering
When the customer says "but our old system did X." Use these scenarios to redirect the conversation toward OOTB adoption rather than re-engineering legacy patterns.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
"We have 5,000 KB articles in our legacy instance — let's port them all." | Curate-then-port: SMEs review by category; keep, edit, or retire per article. | Mass-porting carries forward stale and duplicate content. AI Search learns to return wrong answers if the source data is wrong. | "AI Search is only as good as what it indexes. Five thousand articles with 60% stale = 60% wrong answers — and users learn not to trust the search. Curated 1,500 articles outperform 5,000 stale articles every time. Sprint 5 is curation time." | Compliance scenarios where every article must be retained (rare; usually solved by archive KB).
"Custom KB types per department — IT KB, HR KB, Finance KB, etc." | Two OOTB KBs (IT staff, Employee) with audience criteria for restricted content. | Per-department KBs fragment search and confuse end users about where to look. | "OOTB KB + User Criteria handles this. Two KBs, audience criteria for HR/Finance restricted content. End user sees one search box; results respect the audience model." | Multi-tenant scenarios with regulatory separation.
"Articles in SharePoint, link from ServiceNow KB stub." | Article content in ServiceNow KB; AI Search indexes natively. | AI Search and Virtual Agent can't index SharePoint. The deflection benefit dies. | "AI Search needs the content in ServiceNow to index it. Linking out means Virtual Agent can't quote it, AI Search can't return it. Move the source of truth to the KB; keep SharePoint as the editorial workspace if needed." | Don't customize.
"Custom approval workflow with 4 reviewers per article." | OOTB Knowledge Approval with single Knowledge Manager reviewer. | Multi-step approval kills the publication pipeline. Articles sit in Review for weeks. | "Articles are time-sensitive. Knowledge Manager + author self-review captures the quality bar. Major-revision articles can route to SME for technical review, but make that the exception, not the default." | Compliance KBs requiring multi-reviewer audit (rare and usually for specific KB only).
"Custom article numbering scheme." | OOTB KB number (KB0000123). | Custom numbering breaks with upgrades and serves no operational purpose. | "OOTB number is unique, sortable, and survives upgrades. What does the custom scheme need to capture that the OOTB number doesn't?" | Don't customize.
"Skip article retirement — disk is cheap." | OOTB auto-retire (12 months no view + 6 months no update). | Disk is cheap; user trust is not. Stale articles return wrong answers and erode trust in AI Search. | "Retirement isn't about disk — it's about search accuracy. Stale 'how-to' articles for the old VPN return when users search for the new VPN. Each wrong answer trains users to bypass AI Search." | Don't customize.

## ServiceNow Mapping
ServiceNow Mapping (for ECS Solution Architect reference)
Primary tables: kb_knowledge_base (KBs), kb_knowledge (articles), kb_category (categories). Audience: sys_user_criteria + kb_uc_can_read_mtom. Approval: kb_approval (OOTB workflow). Search: AI Search indexer. Virtual Agent: sys_cs_topic_block (seeded from articles). Plugins: Knowledge Management (OOTB), AI Search.