## Instructions
01 — Software Publishers
SAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the software publishers ServiceNow SAM will track at MVP and the contract relationship ECS holds with each. Publishers are the root of the SAM hierarchy — every product, model, and entitlement traces back to one.
Who fills this out | Customer-side: SAM Process Owner working with the Procurement and Vendor Management leads. Publishers without an active commercial relationship can be excluded at MVP.
Sprint window | End of Sprint 0, Week 1
Estimated effort | 2-4 hours for a typical mid-market customer (40-60 publishers)
Related workbooks | 02 Software Products · 03 Software Models & Versions · Foundation Data Pack — Vendors
Success criteria
• | Every active commercial software publisher is represented with at least one named relationship owner.
• | Publisher categorization (Tier 1 strategic / Tier 2 managed / Tier 3 tracked-only) is decided and applied.
• | The pre-loaded baseline of 40 common publishers has been reviewed; in-scope ones marked, out-of-scope removed.
• | Procurement contact for the top 10 spend publishers is captured.

## Process Decisions
01 — Software Publishers — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Publisher coverage at MVP — all commercial relationships or top-spend only? | Top 50 by spend + every publisher with a true-up clause in the next 12 months. Tracking 200+ publishers at MVP creates noise without commensurate value. |  | SAM Foundations is the credibility-building phase. Customers who try to boil the ocean here typically lose 3-4 weeks before realizing they can't keep the data current.
2 | Publisher tiering — formal tiers or flat list? | Three tiers: Tier 1 strategic (top 10 by spend or risk), Tier 2 managed (next 30), Tier 3 tracked-only (the rest). Tier drives review cadence and reconciliation frequency. |  | Tier 1 publishers get quarterly reconciliation; Tier 2 semi-annual; Tier 3 annual. Without tiering, every publisher gets the same effort and the program loses focus.
3 | Publisher record ownership — IT or Procurement? | Procurement owns the publisher record; IT owns the products and installs. Both are named on the publisher record. |  | Procurement holds the contract relationship; IT consumes the products. Single-owner models break down at the first true-up.
4 | Treatment of acquisitions and rebrands (e.g., publishers acquired by another publisher)? | Maintain the historical publisher record; add the acquiring publisher as the new parent in the publisher hierarchy. Do not retire the historical record until all related entitlements roll forward. |  | Premature retirement loses install history and breaks reconciliation. The publisher table in ServiceNow supports parent_publisher for this exact case.
5 | Open-source and freeware publishers — track or exclude? | Exclude from MVP. Track only publishers with a contractual relationship that creates compliance risk or commercial reporting obligation. |  | Open-source has no compliance signal at MVP; including it inflates the publisher count and dilutes focus on the publishers that matter.
6 | Internal-developed software — separate publisher or under 'In-House'? | Single 'In-House' publisher record; products under it identified with the actual development team. |  | Avoids creating dozens of fake publishers for internal apps while still capturing the products in the same SAM hierarchy.
7 | Publisher records source of truth — ServiceNow or external? | ServiceNow becomes source of truth at go-live. Pre-loaded from this workbook + Procurement export. Maintained going forward via Vendor Management workflow. |  | If the publisher table stays read-only against an external system, the SAM Workspace experience degrades and reconciliation requires constant cross-system reference.
8 | Vendor Management integration — feed or separate? | ServiceNow Vendor Management module is the integration target. Publishers in SAM reference the Vendor record via vendor_id link. |  | Decouples the publisher entity (SAM concern) from the vendor entity (Procurement concern). Both can evolve without breaking the other.

## Dependencies
01 — Software Publishers — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Foundation Data Pack — Vendors imported (publisher records link to vendor records) | In Progress | ECS | End of Sprint 0, Wk 1
2 | Procurement spend report (last 24 months) provided | Pending | Customer | Sprint 0, Wk 1 | CSV or Excel acceptable; ECS will normalize against the SAM publisher list
3 | Top 20 publisher Procurement contacts identified | Pending | Customer | Sprint 0, Wk 1 | Name + email per publisher; needed for true-up and renewal coordination
4 | Customer-specific publisher list (acquired, renamed, internal) reviewed | Pending | Customer | Sprint 0, Wk 1 | Use the baseline tab in this workbook as starting point
5 | SAMP plugin activated in ServiceNow instance | Pending | ECS | Sprint 0, Wk 1 | Required for cmdb_sam_sw_publisher table; cannot proceed without this

## Configuration Data
01 — Software Publishers — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Publisher Catalog
Total publishers at MVP | 50 | 40 baseline pre-loaded + 10 customer-specific. Customer reviews & adjusts.
Naming convention | Official legal name (per Procurement) | e.g., 'Microsoft Corporation' not 'MSFT' or 'Microsoft'. Aliases captured in alt_names field.
Publisher table | cmdb_sam_sw_publisher | OOTB SAMP table
Active flag default | Y for all in-scope; N for tracked-only / historical-only | OOTB
2. Tiering & Ownership
Tier 1 strategic — count | 10 | Top 10 by spend OR by compliance risk
Tier 2 managed — count | 30 | Next 30 by spend / contract complexity
Tier 3 tracked-only — count | 10 | Remaining in-scope publishers
Procurement owner — named per publisher | Customer to populate | Required for Tier 1 and Tier 2; optional for Tier 3
IT owner — named per publisher | Customer to populate | Single named individual; group ownership not permitted at Tier 1
3. Vendor Management Integration
Link to Vendor Management | Yes | publisher.vendor → vmt_vendor
Vendor record must exist before publisher creation | Yes (enforced via UI policy) | Prevents orphan publisher records
Contract record link — required at Tier 1/2 | Yes | contract_id field on publisher; supports renewal alerts
4. Reconciliation Cadence
Tier 1 reconciliation frequency | Quarterly | Aligned to fiscal quarters
Tier 2 reconciliation frequency | Semi-annual | April and October by default
Tier 3 reconciliation frequency | Annual | Per fiscal year close
Reconciliation report owner | SAM Process Owner | Receives the auto-generated report; routes to Procurement for action

## R&R
01 — Software Publishers — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Publisher baseline review (the 40 pre-loaded) | C | R | ECS provides; Customer marks in/out of scope
Procurement spend report extraction | I | R | Customer-only activity; ECS receives result
Customer-specific publisher list (acquired, internal) | C | R | Customer authoritative; ECS validates against vendor table
Tiering decisions (Tier 1/2/3 classification) | R | C | ECS facilitates the tiering workshop; customer makes the calls
Procurement and IT owner assignment per publisher | I | R | Customer-only; ECS provides the role definition
Vendor record validation (Vendor Mgmt link) | R | C | ECS owns the integration; customer confirms vendor coverage
Publisher table configuration in ServiceNow | R | I | ECS executes; customer informed of imports
Reconciliation cadence calendar setup | R | C | ECS configures; customer confirms fiscal alignment

## Consultant Guide
01 — Software Publishers — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB Software Publishers Foundations
Use cmdb_sam_sw_publisher OOTB. Do not create a custom publisher table — every customer who has tried inherits months of integration debt when they later adopt SAMP fully. The OOTB table supports parent_publisher (for acquisitions), vendor link (for Procurement integration), and alt_names (for renamed publishers). All three are non-negotiable at MVP.
Implementation Sequence
Day 1-2: import the 40 baseline publishers from this workbook. Day 3-5: customer review session, mark in/out of scope, add customer-specific publishers. Day 6-8: tiering workshop with Procurement and SAM Process Owner together. Day 9-10: owner assignment, vendor record validation, reconciliation calendar config.
Common Failure Modes
Three patterns we have seen kill SAM Foundations: (1) trying to track every publisher the customer has ever purchased — leads to a publisher table no one trusts; (2) building a custom publisher hierarchy with five tiers when OOTB has three — never extends to SAMP later; (3) skipping the Vendor Management link because 'we will integrate later' — orphans every publisher record and breaks renewal workflow.
Field Mapping to SAMP
The SAMP module reads publisher data from cmdb_sam_sw_publisher directly. If the customer is on a SAMP-enabled subscription, this table immediately powers the SAMP Workspace home page and the publisher-level true-up forecast. No custom integration required.
Sprint 1 Handoff
By the end of Sprint 0, publishers are loaded and tiered. Sprint 1 picks up with Software Products (workbook 02), which references publisher_id. If publishers are not locked by end of Sprint 0, Sprint 1 stalls — flag this in the variance scan if it slips.

## Adoption vs Re-engineering
01 — Software Publishers — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We need a custom field for the publisher's account manager.' | Use the Vendor Management contact_account_manager field (linked via publisher.vendor → vmt_vendor → contacts). | Two custom fields on publisher diverge from SAMP's expectations. Vendor Mgmt is the OOTB home for contacts. | 'The account manager belongs to the vendor relationship, not the SAM product hierarchy. Let me show you how Vendor Mgmt holds this — it links straight to the publisher.' | Never. This is a process discipline question, not a system limitation.
'We track each publisher's renewal date on the publisher record.' | Renewal dates live on the contract record (vmt_contract), linked from publisher via contract_id. One publisher → many contracts → many renewal dates. | Storing a single renewal date on the publisher record is the #1 reason renewal alerts miss. Most publishers have 3-5 active contracts with different renewal windows. | 'A renewal date on the publisher record only tells you about one contract. Let me show you the contract-level view — it's where the renewal alerts actually fire.' | Never. Customer process should evolve to the contract-level model.
'Publisher names should match our PO system exactly, including the abbreviations.' | Use legal name in cmdb_sam_sw_publisher.name; capture PO-system abbreviations in alt_names field. Reconciliation tolerates both. | Different systems will always have different naming conventions. The alt_names field is exactly designed for this case. | 'The publisher table needs to match SAMP's expectations to work with Now Assist. Let me show you how alt_names handles your PO abbreviations without breaking the SAMP linkage.' | Never. The alt_names approach is OOTB and Now-Assist-compatible.
'We need separate publisher records for each subsidiary of a large publisher.' | Use the parent_publisher field for hierarchies. Microsoft Corp can have child publishers if the customer has separate contracts; one publisher record with multiple contracts is the default. | Subsidiary proliferation creates dozens of false publishers. The parent_publisher hierarchy was designed for this exact case. | 'Let me show you the publisher hierarchy view — it preserves the subsidiary distinction without creating duplicate records that break reconciliation.' | Yes, when subsidiaries have entirely separate contracts AND separate Procurement relationships. Rare but legitimate.
'Internal apps should each have their own publisher record.' | Single 'In-House' publisher record; products under it identified with the actual development team via dev_team_owner field. | Creating a publisher record per internal app inflates the publisher count and makes Procurement-driven workflows nonsensical for internal apps. | 'In-house apps don't have a commercial publisher relationship. The In-House publisher is a single record; the actual ownership lives at the product level.' | Never.
'We want to exclude all open-source publishers entirely.' | Open-source IS excluded at MVP. Re-introduce in SAM Realization (AP-07) when compliance-tracked open-source becomes in scope. | Open-source has no commercial signal at Foundations stage; tracking it now is process overhead with no business outcome. | 'Agreed — open-source is out of Foundations scope. Realization (AP-07) adds it back with the right compliance metadata.' | Already aligned; no customization needed.

## ServiceNow Mapping
01 — Software Publishers — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_publisher | SAM software publisher master record | OOTB SAMP plugin table
2. Field mapping (customer data → ServiceNow field)
Publisher name | cmdb_sam_sw_publisher.name | Legal name per Procurement
Aliases / abbreviations | cmdb_sam_sw_publisher.alt_names | Comma-separated list
Tier | cmdb_sam_sw_publisher.u_tier | Choice field (1/2/3) — custom but flat, no schema change
Procurement owner | cmdb_sam_sw_publisher.procurement_owner | Reference to sys_user
IT owner | cmdb_sam_sw_publisher.it_owner | Reference to sys_user
Vendor link | cmdb_sam_sw_publisher.vendor | Reference to vmt_vendor
Active | cmdb_sam_sw_publisher.active | Boolean; default Y for in-scope publishers
3. OOTB features leveraged
Publisher hierarchy | parent_publisher field | Supports acquisitions, subsidiaries
Vendor Management link | vendor reference | Integrates with vmt_vendor and contracts
SAMP Workspace home | Reads publisher table directly | No additional config required
Now Assist for SAM | Publisher-level true-up forecast | Available on SAMP-enabled subscriptions
4. Integrations
Procurement spend export | Manual one-time import + monthly delta | CSV via Import Set
Vendor Management module | Native ServiceNow integration | Via vendor reference field
Active Directory / SSO | Owner references | Foundation Data Pack — Users