## Instructions
03 — Software Models & Versions
SAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | The specific versions of each product the customer has deployed or is licensed for. Models/versions are the child of product and the parent of install/usage. At MVP we capture the licensed-and-deployed versions, not every version that has ever existed.
Who fills this out | Customer-side: IT Operations and Application Owners. Discovery / SCCM / Intune feeds can populate much of this automatically once mapping is established.
Sprint window | End of Sprint 0, Week 2 (data prep) → Sprint 1 Week 1 (validation)
Estimated effort | 6-10 hours including discovery validation
Related workbooks | 02 Software Products · 04 Install & Usage Capture · Foundation Data Pack — Locations
Success criteria
• | Every MVP product has at least one version record.
• | Unauthorized / unlicensed versions are surfaced for action (not silently included).
• | Version-to-product mapping rules are documented for discovery normalization.
• | Major version vs. minor/patch tracking depth is decided.

## Process Decisions
03 — Software Models & Versions — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Version depth — major-only or major.minor.patch? | Major version at MVP (e.g., 'Windows 11', not 'Windows 11 22H2 19045.2965'). Minor versions tracked only for products with version-specific licensing (Oracle DB, SQL Server). |  | Tracking every patch version explodes the model table without adding compliance signal for most products. Major version is the licensable granularity.
2 | Version normalization — strict or fuzzy match? | Strict for top 20 products (Microsoft, Oracle, SAP, IBM); fuzzy match for the rest with quarterly cleanup. |  | Strict matching catches license violations but rejects valid installs that don't conform. Fuzzy matching trades precision for completeness; right answer depends on product.
3 | Unauthorized version handling — surface or suppress? | Surface. Unauthorized versions appear in a separate 'Unmapped' bucket; never silently mapped to authorized versions. |  | Silent mapping hides license violations. The Unmapped bucket forces conscious decisions about each unauthorized install.
4 | Discovery source priority — SCCM, Intune, or SN Discovery? | SCCM primary for Windows workstations and servers; Intune primary for mobile and Mac; SN Discovery for Linux/Unix. Customer-specific priorities adjusted as needed. |  | Single-source discovery misses entire device classes. Tiered priority by device type is the OOTB-defensible approach.
5 | Beta / preview versions — track? | No. Beta/preview installs filtered out at the discovery normalization layer. |  | Beta installs are not licensable and inflate the model count. Filtering at normalization keeps the model table clean.
6 | Custom-built versions of commercial products — how? | Tag with model.is_modified = true; keep linked to the upstream product/version. |  | Most commercial products tolerate light customization without changing the licensing posture. The is_modified flag preserves the linkage while flagging the divergence.
7 | End-of-support versions — flag for action? | Yes. Versions past vendor support date appear in a quarterly EOS report routed to the Application Owner. |  | EOS versions are the highest-risk source of audit findings and security exposure. Quarterly EOS reporting is OOTB.

## Dependencies
03 — Software Models & Versions — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 02 (Products) complete and imported | Pending | ECS | Sprint 0, Wk 2 | Model records require product_id reference
2 | SCCM / Intune / SN Discovery feeds operational | In Progress | ECS | Sprint 0, Wk 1 | Required for automated version capture
3 | Discovery normalization rules drafted | Pending | ECS | Sprint 0, Wk 2 | ECS provides starting rules; customer review
4 | Vendor support lifecycle data sourced | Pending | ECS | Sprint 0, Wk 2 | From vendor websites or licensed source like Flexera / Snow

## Configuration Data
03 — Software Models & Versions — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Model Catalog
Total model records at MVP (est.) | 300 | 75 products × ~4 versions each on average
Model table | cmdb_sam_sw_product_model | OOTB SAMP table
Version granularity (default) | Major version only | OOTB choice; per-product overrides allowed
Active flag default | Y for currently deployed versions; N for retired/EOS | OOTB
2. Discovery Source Priority
SCCM coverage — workstations | 100% Windows | Primary
SCCM coverage — Windows servers | 100% | Primary
Intune coverage — Mac and mobile | 100% | Primary for these device classes
SN Discovery — Linux/Unix | TBD by customer environment | Required for non-Windows server coverage
Manual entry — appliances and embedded | Annual refresh | For non-discoverable devices
3. Normalization Rules
Strict-match products (no fuzzy) | Top 20 by audit risk | Microsoft, Oracle, SAP, IBM, Adobe Enterprise
Fuzzy-match threshold | 85% string similarity + publisher match | OOTB SAMP setting
Unmapped bucket size budget | ≤5% of total installs | Above 5% triggers a normalization review
Beta / preview filter | Active (regex pattern) | Excludes beta, preview, RC, CTP installs
4. Lifecycle / Support Flags
End-of-support reporting cadence | Quarterly | Routed to Application Owner
Mainstream support end source | Vendor data feed (where available) | Manual for niche products
Action on EOS finding | Remediation plan due in 30 days | Tracked in SAM Workspace

## R&R
03 — Software Models & Versions — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Discovery normalization rules | R | C | ECS authors; customer reviews exceptions
Top 20 strict-match product list | R | C | ECS proposes; customer confirms
SCCM / Intune integration validation | R | C | ECS executes; customer validates coverage
Unmapped bucket triage | R | C | ECS produces; customer adjudicates
Vendor support lifecycle data sourcing | R | I | ECS sources; customer informed
Model record creation in ServiceNow | R | I | ECS automated via discovery; customer informed
Quarterly EOS review | C | R | Customer-led after Foundations; ECS supports first cycle
Custom-built / modified version tagging | C | R | Customer identifies; ECS configures

## Consultant Guide
03 — Software Models & Versions — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB Software Models Foundations
Use cmdb_sam_sw_product_model OOTB. The model table captures versions of each product. At Foundations we go to major-version granularity for most products and major.minor for products with version-specific licensing (Oracle DB, SQL Server, IBM DB2). Going deeper inflates the table without compliance benefit.
Discovery is the leverage point
The model table should be 90% populated from discovery automatically. Manual model creation at MVP is a process failure waiting to happen. Spend Sprint 0 Week 1 getting SCCM/Intune/SN Discovery feeds operational; spend Week 2 on the normalization rules. The actual model records appear in the table once the feeds flow.
The Unmapped Bucket
Discovery will land 5-15% of installs as 'unmapped' at first run. This is normal. The Unmapped Bucket is the queue for normalization tuning. Target ≤5% unmapped within 30 days of go-live. Above 5% indicates a normalization gap that needs cleanup before reconciliation runs.
EOS Reporting
End-of-Support version reporting is one of the highest-leverage SAM outputs. Quarterly EOS reports surface the products customers should be migrating off; they convert SAM from a compliance burden into a security and modernization driver. Make sure the EOS report is configured before go-live.
Sprint 1 Handoff
By end of Sprint 0, discovery feeds operational and normalization rules drafted. Sprint 1 picks up with the first full discovery sweep and the unmapped bucket triage. Workbook 04 (Install & Usage Capture) builds on the model table established here.

## Adoption vs Re-engineering
03 — Software Models & Versions — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want every patch version tracked, not just major versions.' | Major version at MVP; minor for products with version-specific licensing only. | Patch-level granularity creates a 10× larger model table without compliance signal for most products. Limited value, high maintenance cost. | 'Let me show you the version-specific licensing list — these get minor-version tracking. Everything else, the major version is what licensing actually cares about.' | Yes for specific products if Oracle DB / SQL Server / IBM DB2 / similar require minor-level tracking. Configure at the product level, not globally.
'Unmapped installs should auto-suppress — they clutter the view.' | Surface them in a dedicated bucket. Never silently suppress. | Silent suppression hides license violations and unauthorized installs. The Unmapped bucket is the discipline that prevents that. | 'The Unmapped bucket is where audit findings come from. Hiding it isn't reducing risk — it's deferring it to the auditor.' | Never.
'Beta versions should be tracked too — we have a lot of preview deployments.' | Beta/preview filtered at normalization. Tracked separately if customer truly needs beta visibility. | Beta installs are not licensable and inflate the model count. If beta visibility is genuinely needed, a separate tag handles it without polluting the model table. | 'Beta isn't licensable, so it doesn't belong in the SAM model table. If you need beta visibility, let me show you the discovery-tag approach that keeps it separate.' | Yes when customer has a structured beta program with compliance implications; tag in discovery, not in model table.
'Custom-modified versions should be entirely new model records.' | Tag is_modified = true on the existing model. Keep the upstream linkage. | Detaching from the upstream model breaks vendor support lookups and EOS reporting; the is_modified flag preserves both. | 'The is_modified flag preserves your license entitlement linkage to the upstream version. Creating a separate model orphans the modification from the license terms.' | Never at Foundations.
'SCCM doesn't catch our DevOps tools — we need manual entries for those.' | Add SN Discovery for the Linux/cloud surface where DevOps tools run; manual entries only as last resort. | Manual entries become stale within a quarter. SN Discovery covers the gap SCCM leaves on cloud/Linux. | 'Let me show you what SN Discovery picks up on your DevOps surface. Manual entry is the fallback, not the default.' | Yes for genuinely non-discoverable systems (appliances, embedded devices). Manual entries require annual refresh process.
'EOS reporting is a security team thing — keep it out of SAM.' | EOS reporting lives in SAM. Quarterly route to Application Owner; security team copied. | SAM owns the version inventory; that inventory is exactly where EOS is detected. Splitting the report creates duplicate effort with version mismatches. | 'SAM is where the version data lives, so EOS detection has to start here. Security gets the report; they don't need to maintain a parallel inventory.' | Never.

## ServiceNow Mapping
03 — Software Models & Versions — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_product_model | Specific version of a product | OOTB SAMP plugin table
cmdb_sam_sw_discovery_map | Discovery → product/version mapping rules | OOTB SAMP normalization layer
2. Field mapping
Version | cmdb_sam_sw_product_model.version | Major version string
Product reference | cmdb_sam_sw_product_model.product | Reference to cmdb_sam_sw_product_definition
Edition | cmdb_sam_sw_product_model.edition | Standard / Pro / Enterprise / etc.
Release date | cmdb_sam_sw_product_model.release_date | From vendor data
EOS date | cmdb_sam_sw_product_model.end_of_support | Drives quarterly EOS report
Is modified | cmdb_sam_sw_product_model.is_modified | Boolean
3. OOTB features leveraged
Discovery normalization engine | cmdb_sam_sw_discovery_map | Rules-based discovery → model
EOS reporting | Scheduled report on end_of_support | Quarterly OOTB
SAMP Workspace version drill-down | Reads model table | Native
4. Integrations
SCCM | Native ServiceNow integration | Primary for Windows
Microsoft Intune | Native ServiceNow integration | Primary for Mac/mobile
ServiceNow Discovery | Native | Primary for Linux/Unix/cloud
Vendor support lifecycle feed (Flexera / Snow / vendor sites) | Manual + scheduled refresh | EOS data source