## Instructions
04 — Install & Usage Capture
SAM Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | How ServiceNow captures every software install and (where licensed) usage signal. Install data is the basis for reconciliation against entitlement. Without reliable install capture, SAM is decorative.
Who fills this out | Customer-side: IT Operations, Endpoint Management, and Application Owners. ECS configures the integration plumbing.
Sprint window | Sprint 0 Wk 2 (integration setup) → Sprint 1 Wk 1 (first full capture)
Estimated effort | 8-16 hours including discovery validation and reconciliation testing
Related workbooks | 02 Software Products · 03 Software Models & Versions · Integration Pack — SCCM/Intune
Success criteria
• | Discovery sources cover ≥95% of in-scope devices (workstations + servers).
• | Install records flow to cmdb_sam_sw_install with publisher/product/model resolution.
• | Usage capture is operational for the top 10 license-constrained products.
• | First reconciliation run completed with <5% unmapped variance.

## Process Decisions
04 — Install & Usage Capture — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Install capture sources — which feeds at MVP? | SCCM (Windows), Intune (Mac/mobile), SN Discovery (Linux/Unix). Manual entries only for non-discoverable. |  | Three-source coverage handles 95%+ of typical enterprise environments. Manual entries become stale fast.
2 | Usage capture — measured or inferred? | Measured for the top 10 license-constrained products (Microsoft Office launch tracking, Adobe license server, Oracle DB sessions). Inferred (last-login, last-active) for the rest. |  | Measured usage requires per-product instrumentation; inferred usage is good enough for 80% of license reconciliation purposes.
3 | Inactive install threshold — what defines unused? | 90 days without usage signal = inactive. 180 days = candidate for reclamation. |  | Industry-standard thresholds. Aggressive (30/90) creates user friction; loose (180/365) leaves licenses on the shelf.
4 | Reclamation workflow — automated or human-gated? | Human-gated at MVP. Inactive licenses surface in a reclamation queue; the Application Owner approves reclamation. |  | Automated reclamation at MVP creates user backlash. Human gate at Foundations; selective automation in Realization.
5 | Server install handling — track entitlements differently? | Server installs capture the host CI; entitlement calculation deferred to Realization (AP-07). |  | Server licensing (Oracle DB processor-based, SQL Server core-based) is complex enough to warrant its own workbook in Realization.
6 | VDI / virtual desktop installs — count once or per session? | Count once per persistent VDI image; per-session for non-persistent. |  | VDI licensing depends on persistence; this is the OOTB-defensible default.
7 | Cloud SaaS install capture — API or SSO logs? | SSO logs (Okta, Entra) for SaaS coverage at MVP. Vendor API integration deferred to Realization. |  | SSO logs are universally available; vendor APIs require per-publisher integration work.
8 | Mobile / BYOD install tracking — in scope? | Yes for managed mobile (via Intune). BYOD out of scope at Foundations — privacy and discovery constraints. |  | BYOD raises HR/privacy issues that Foundations is not the right stage to resolve.

## Dependencies
04 — Install & Usage Capture — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | SCCM integration operational | In Progress | ECS | Sprint 0, Wk 1 | From Integration Accelerator Pack 03
2 | Intune integration operational | In Progress | ECS | Sprint 0, Wk 1 | From Integration Accelerator Pack 04
3 | SN Discovery configured for Linux/Unix | Pending | ECS | Sprint 0, Wk 2 | Mid-server, credentials
4 | Workbook 03 (Models) discovery normalization rules | Pending | ECS | Sprint 0, Wk 2 | Prerequisite for install resolution
5 | SSO logs accessible (for SaaS coverage) | Pending | Customer | Sprint 0, Wk 2 | Read-only access to Okta or Entra audit logs
6 | Endpoint count baseline established | Pending | Customer | Sprint 0, Wk 1 | From CMDB or asset inventory; defines 95% coverage target

## Configuration Data
04 — Install & Usage Capture — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Install Capture Sources
SCCM coverage target | 100% Windows workstations + servers | Primary source
Intune coverage target | 100% Mac + managed mobile | Primary for these device classes
SN Discovery coverage target | 100% Linux/Unix + cloud workloads | Required for non-Windows server coverage
Manual entry budget | ≤2% of total installs | Annual refresh only
Coverage gap threshold (alert if missed) | 5% of in-scope devices | Triggers integration health alert
2. Usage Capture
Measured usage — top 10 products | Per-product instrumentation | Microsoft Office telemetry, Adobe license server, Oracle DB sessions, etc.
Inferred usage — last-login / last-active | All other products | From OS / SSO / discovery probes
Inactive threshold (warn) | 90 days no usage signal | OOTB SAMP default
Inactive threshold (reclamation candidate) | 180 days no usage signal | OOTB SAMP default
Reclamation workflow | Human-gated via Application Owner | OOTB SAMP workflow
3. Reconciliation
First reconciliation run target date | Sprint 1, Wk 1 | Required for Sprint 1 demo
Unmapped variance budget (first run) | ≤10% | Tightens to ≤5% by Sprint 2
Reconciliation cadence post-go-live | Monthly automated; quarterly review with Procurement | OOTB scheduled report
4. Cloud SaaS Capture
SaaS coverage source at MVP | SSO logs (Okta or Entra) | Login frequency = usage signal
API integration for top 5 SaaS products | Deferred to Realization (AP-07) | Salesforce, Workday, ServiceNow self, etc.
5. VDI / Virtual
Persistent VDI handling | Count once per image | Per-image entitlement tracking
Non-persistent VDI handling | Per-session | Concurrent licensing model

## R&R
04 — Install & Usage Capture — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
SCCM / Intune integration setup | R | C | ECS executes; customer provides access
SN Discovery configuration for Linux/Unix | R | C | ECS executes; customer provides credentials
Discovery normalization rule tuning | R | C | ECS authors; customer reviews exceptions
Usage capture instrumentation (top 10) | R | C | ECS configures; customer confirms per-product approach
Inactive / reclamation threshold setting | C | R | ECS recommends; customer policy decision
First reconciliation run execution | R | I | ECS runs; customer informed of results
Unmapped bucket triage | R | C | ECS provides; customer adjudicates
Cloud SaaS coverage via SSO logs | R | C | ECS integrates; customer provides log access

## Consultant Guide
04 — Install & Usage Capture — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB Install & Usage Foundations
Use cmdb_sam_sw_install OOTB. Install records are populated from SCCM/Intune/SN Discovery via the SAMP normalization layer. The normalization layer maps discovery output to publisher/product/model records (workbooks 01-03). The unmapped bucket captures discovery output that does not normalize cleanly; the goal is ≤5% unmapped by Sprint 2.
Usage capture — measured vs. inferred
Measured usage requires per-product instrumentation: Microsoft Office telemetry, Adobe license server logs, Oracle DB session counts, etc. We do this for the top 10 license-constrained products at MVP. Inferred usage (last-login from OS/SSO) covers the rest. Most license reconciliation uses cases work fine on inferred usage.
The Reconciliation Trigger
Reconciliation is the moment SAM proves its value. The first run is the credibility test. Target: first run completes by Sprint 1 Wk 1 with ≤10% variance, dropping to ≤5% by Sprint 2. If variance is wider than 10% at first run, the customer concludes SAM is unreliable and Realization gets hard.
Reclamation Discipline
Reclamation is human-gated at MVP because automated reclamation creates user backlash. The reclamation queue routes to the Application Owner; the owner approves or defers. Selective automation can come in Realization once trust is established with the user community.
Sprint 1 Handoff
By end of Sprint 0, integrations are operational and normalization rules drafted. Sprint 1 Wk 1: first full reconciliation. Sprint 1 Wk 2: variance triage and unmapped bucket cleanup. Sprint 2 picks up with Realization-track entitlement setup (AP-07).

## Adoption vs Re-engineering
04 — Install & Usage Capture — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want to automate reclamation — pull licenses after 60 days inactive.' | Human-gated reclamation at MVP via Application Owner approval. | Auto-reclamation at MVP creates user backlash strong enough to delegitimize the program. Foundations is when trust is built; aggressive automation comes later. | 'Auto-reclamation at MVP is how SAM programs lose their internal champion. Let me show you the human-gated workflow — it's the same reclamation outcome with the trust-building step intact.' | Never at Foundations. Realization (AP-07) can introduce selective auto-reclamation for clearly inactive licenses.
'Inactive should be 30 days, not 90 — we want aggressive recovery.' | 90 days warn / 180 days reclaim at MVP. OOTB SAMP defaults. | 30-day thresholds catch users on parental leave, sabbatical, or seasonal cycles. 90/180 is the industry default for a reason. | 'Let me show you why the 90/180 thresholds exist. Aggressive thresholds create false positives that consume more Application Owner attention than the licenses recover.' | Specific products can override (rarely). Per-product threshold is OOTB; global aggressive thresholds are not OOTB-defensible.
'BYOD users need their installs tracked too.' | BYOD out of scope at Foundations. Privacy and discovery constraints. | BYOD raises HR and privacy issues Foundations is not the right stage to resolve. Realization with the right legal review is the path. | 'BYOD opens privacy questions that should be answered before we start tracking installs on personal devices. Let me note this for Realization where we can scope it properly.' | Never at Foundations. Realization with explicit HR/legal sign-off.
'We need per-session usage on every product, not just the top 10.' | Measured per-session for top 10 license-constrained; inferred (last-login) for the rest. | Per-session instrumentation requires per-product integration work. The top 10 captures 80% of the license value; the long tail does fine on inferred usage. | 'Per-session for every product is multi-quarter integration work. Inferred usage covers reconciliation needs for the tail. Let me show you the 80/20 cut.' | Yes for additional products where customer has compliance audit pressure — case by case.
'Cloud SaaS should use vendor APIs, not SSO logs.' | SSO logs at MVP; vendor APIs in Realization. | SSO logs are universally available; vendor APIs require per-publisher integration work. Foundations covers the breadth; Realization adds depth. | 'SSO gives us SaaS visibility for all your SaaS providers in one move. Vendor APIs are better data but require per-product engineering work — Realization is the right place for that.' | Never at Foundations.
'Server installs need full entitlement calculation now.' | Server installs capture host CI at Foundations; entitlement calculation deferred to Realization. | Server licensing (Oracle processor-based, SQL Server core-based, IBM PVU) is complex enough to warrant its own workbook in Realization. | 'Server entitlements are a separate engineering effort because the licensing models are so different. Let me note this for Realization where we have the right workbook for it.' | Never at Foundations.
'We have a homegrown discovery tool — keep using it.' | Phase-out plan. SCCM/Intune/SN Discovery is the OOTB stack; homegrown discovery becomes a maintenance liability. | Custom discovery diverges from the SAMP normalization layer. Maintenance burden grows; SAMP capability gains are forfeited. | 'Your homegrown tool can run alongside through Sprint 1 for validation. By Realization, we want to have phased it out — the SAMP integration depends on the OOTB discovery stack.' | Never. Transition plan required.

## ServiceNow Mapping
04 — Install & Usage Capture — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_install | Software install record | OOTB SAMP plugin table
cmdb_sam_sw_usage | Usage signal record | OOTB SAMP usage tracking
cmdb_sam_sw_discovery_map | Discovery normalization rules | OOTB SAMP
2. Field mapping
Host CI | cmdb_sam_sw_install.installed_on | Reference to cmdb_ci
Product / model | cmdb_sam_sw_install.product_model | Reference to cmdb_sam_sw_product_model
Install date | cmdb_sam_sw_install.install_date | From discovery source
Last seen | cmdb_sam_sw_install.last_scanned | Discovery refresh timestamp
Usage status | cmdb_sam_sw_install.usage_status | Active / Inactive / Reclamation candidate
Discovery source | cmdb_sam_sw_install.discovery_source | SCCM / Intune / SN Discovery / Manual
3. OOTB features leveraged
SAMP normalization engine | cmdb_sam_sw_discovery_map | Discovery → install resolution
Usage tracking | cmdb_sam_sw_usage | Per-install usage signals
Reclamation workflow | OOTB SAMP workflow | Human-gated approval
Reconciliation engine | OOTB scheduled report | Install ↔ entitlement match
4. Integrations
SCCM / MECM | Native | Primary Windows
Microsoft Intune | Native | Primary Mac/mobile
ServiceNow Discovery | Native | Primary Linux/Unix/cloud
Okta / Microsoft Entra (SSO) | Audit log import | SaaS coverage
Application Portfolio Management | Native (if licensed) | Cross-link to cmdb_ci_appl