ACCELERATOR PACK · SAM REALIZATION

SAM Realization

Accelerator Pack — README

Eight workbooks. Stand up full entitlement counting, reconciliation, vendor-specific licensing, forecasting, audit defense, SaaS subscription management, renewals, and KPIs.

ECS Federal · ServiceNow Practice

Audience: Customer Project Sponsor, Procurement Lead, Legal Liaison, and named SAM SMEs; ECS Federal SAM consultants

Companion to: SAM Foundations Accelerator Pack (AP-06) · Foundation Data Pack (AP-01) · ITAM_HAM Realization (AP-05)

Document ID: AP-07     ·     Version: 1.0     ·     Status: Released

Confidential — for the recipient and their organization

This Accelerator Pack contains eight workbooks that capture the realization layer of a ServiceNow Software Asset Management (SAM) program. Realization picks up everything SAM Foundations (AP-06) deferred: full entitlement counting, reconciliation rules and per-vendor overrides, true-up forecasting, audit defense discipline, cloud SaaS subscription management, renewal workflow, and the KPI framework that quantifies the program's value.

Realization is where SAM converts from operational discipline into commercial leverage. The Foundations pack (AP-06) gets the publisher / product / install / lifecycle data in place; Realization adds the entitlement side of the reconciliation equation and the workflows that turn the resulting data into procurement decisions, audit defense, and savings reporting.

The pack assumes Foundations is operational. Customers who attempt Realization without Foundations either discover the data gap mid-engagement (and stall) or produce reconciliation output that nobody trusts. The Foundations-first sequence is non-optional for engagement credibility.

# The Eight Workbooks

| # | Workbook | What it Captures | Customer Owner | Sprint |
| --- | --- | --- | --- | --- |
| 01 | Entitlement Catalog | License entitlements per SKU; contract terms; true-up clauses | SAM PO + Procurement | Sprint 2 Wk 1 |
| 02 | Reconciliation Rules | Install ↔ entitlement match logic; per-product overrides | SAM Process Owner | Sprint 2 Wk 2 |
| 03 | Vendor-Specific Licensing | Big Six publisher overrides (Oracle / MS / IBM / SAP / Adobe / Salesforce) | SAM PO + Per-publisher SMEs | Sprint 3 Wk 1 |
| 04 | True-Up Forecast | 12-month projection of install growth vs. entitlement headroom | SAM PO + Procurement | Sprint 3 Wk 2 |
| 05 | Audit Defense | Audit response playbook; evidence pack; escalation matrix | SAM PO + Procurement + Legal | Sprint 4 Wk 1 |
| 06 | Cloud SaaS Subscription Mgmt | Per-SaaS API integration; seat tracking; over-subscription | SAM PO + IT Operations | Sprint 4 Wk 2 |
| 07 | Renewal Workflow | Renewal triggers; lead-time alerts; negotiation prep; outcomes | Procurement Lead + SAM PO | Sprint 5 Wk 1 |
| 08 | KPIs & Savings Tracking | Six core KPIs; baseline; ROI reporting; Steering Committee pack | SAM Process Owner | Sprint 5 Wk 2 |

Each workbook follows the canonical 8-tab ECS Accelerator Pack architecture: Instructions, Process Decisions, Dependencies, Configuration Data, R&R, Consultant Guide, Adoption vs Re-engineering, and ServiceNow Mapping. Customers focus on Instructions, Process Decisions, and Dependencies. ECS owns Configuration Data, Consultant Guide, and ServiceNow Mapping. Both work R&R and Adoption together.

# Roles & Responsibilities

Realization is delivered as a partnership. ECS provides the structure, the platform expertise, the publisher intelligence (Big Six overrides), and the configuration. The customer provides authoritative data, named decision-makers, contract documents, audit history, and the access ECS needs to extract and configure.

## ECS Federal Responsibilities

| Role | Owns |
| --- | --- |
| Solution Architect | Workbook structure; mapping to OOTB SAMP tables (cmdb_sam_sw_entitlement, cmdb_sam_sw_recon_rule, cmdb_sam_sw_renewal_case, cmdb_sam_sw_kpi); Big Six override authoring; reconciliation rule tuning; first reconciliation run; SaaS API integration |
| Process Consultant | Workshop facilitation for Big Six publishers; audit defense playbook customization; renewal workflow design; KPI calibration coaching |
| Engagement Manager | Schedule; dependencies; escalation; sponsor sync; scope discipline (defer post-Realization tail to ongoing operations) |
| Developer | Configuration of entitlement / reconciliation / renewal / KPI tables; per-publisher integration plumbing; SaaS API connectors |

## Customer Responsibilities

| Role | Owns |
| --- | --- |
| SAM Process Owner | Full-time. Owns decisions in workbooks 01-08; convenes monthly KPI review; participates in Big Six workshops |
| Procurement Lead | Contract extraction; renewal negotiation; outcome capture; quarterly Steering Committee renewal review |
| Legal Liaison | Audit defense privilege markings from day 1; external counsel engagement at thresholds |
| Per-publisher SMEs | Big Six workshop attendance and contract specifics (one SME per publisher) |
| IT Operations | SaaS API service account provisioning; SCCM/Intune data validation; mover workflow execution |
| Finance | Pre-program baseline cost data; SAM program operating cost data; ROI reporting |
| SAM Steering Committee | Quarterly review attendance; walk-or-renegotiate decisions; KPI pack review |

# Sprint Timing

AP-07 spans Sprints 2 through 5. Workbook 01 (Entitlement Catalog) starts Sprint 2 Wk 1 immediately after Foundations operational; workbook 02 (Reconciliation Rules) follows in Sprint 2 Wk 2. Sprint 3 covers vendor-specific licensing (workbook 03) and true-up forecast (workbook 04). Sprint 4 adds audit defense (workbook 05) and SaaS subscription management (workbook 06). Sprint 5 closes with renewal workflow (workbook 07) and KPIs (workbook 08). The first quarterly Steering Committee KPI pack delivers in Sprint 6.

Workbook 02 (Reconciliation Rules) is the credibility moment. The first full reconciliation run with both installs and entitlements should produce ≤10% variance from contracted entitlement. Above that, customer concludes SAM data is unreliable and Realization gets hard to defend. Spend Sprint 2 Wk 2 getting the rules right; the rest of Realization depends on it.

# Cross-References

AP-06 SAM Foundations — required prerequisite. AP-07 builds on Foundations data (publishers, products, installs, lifecycle).

AP-01 Foundation Data Pack — Vendors, Users, Locations, Groups (cross-referenced by every workbook).

AP-05 ITAM_HAM Realization — sister pack on the hardware side; demonstrates the Realization-after-Foundations pattern.

ECS Accelerator Pack Blueprint (03_Shared/01_Accelerator_Packs/) — canonical 8-tab architecture.

ECS Internal Governance Operating Guide — deviation lifecycle for any custom override beyond the Big Six.

Manager's Trust-But-Verify Playbook (INT-TBV-01) — Customization Variance signal monitors SAM rule customization rate during Realization.