## Instructions
01 — Entitlement Catalog
SAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | The license entitlement record for every in-scope product: what the customer has the right to use, in what quantity, on what terms, until when. Entitlements are the right-side of the reconciliation equation; installs (from AP-06 workbook 04) are the left side.
Who fills this out | Customer-side: Procurement, SAM Process Owner, Vendor Management. ECS extracts from contract data; customer validates against active agreements.
Sprint window | Sprint 2, Week 1
Estimated effort | 8-16 hours including contract extraction and validation
Related workbooks | AP-06/01 Publishers · AP-06/02 Products · 02 Reconciliation Rules · 03 Vendor-Specific Licensing
Success criteria
• | Every in-scope product has at least one active entitlement record.
• | Entitlement quantities match the executed contracts (validated by Procurement).
• | Term dates, true-up clauses, and renewal triggers are captured.
• | Entitlement → product → publisher hierarchy resolves without orphans.

## Process Decisions
01 — Entitlement Catalog — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Entitlement granularity — per contract or per license SKU? | Per license SKU. One contract may grant multiple SKUs with different terms; each becomes its own entitlement record. |  | Contract-level granularity hides per-SKU complexity (different quantities, different effective dates within one contract). Per-SKU is OOTB SAMP.
2 | Historical entitlements — load or only active? | Active + most-recent-expired. Two-year lookback at most. Older entitlements are audit-only and live in archive. |  | Loading full history inflates the entitlement table without reconciliation value. Two-year lookback covers audit defense; older sits in archive.
3 | Free / freeware entitlements — track? | No. Free products (open-source, freeware) have no entitlement record at Realization; tracked via product lifecycle state only. |  | Free entitlements have no compliance signal; their reconciliation always produces 'unlimited entitlement.' Skipping them keeps the entitlement table meaningful.
4 | True-up clause capture — required fields? | Yes. Every entitlement record with a true-up clause has: trigger condition, frequency, lead time, and named owner. |  | True-up clauses are the source of most surprise SAM costs. Missing one of these four fields turns the true-up into a fire drill.
5 | Entitlement quantity unit — match license model? | Yes. User-based products → quantity in users; device-based → devices; capacity-based → cores/PVUs; concurrent → simultaneous-user limit. |  | Unit consistency lets the reconciliation engine compare apples to apples. Per-product license model from AP-06 workbook 02 drives the unit choice.
6 | Contract reference — required on every entitlement? | Yes. Every entitlement links to a Vendor Management contract record (vmt_contract). Orphan entitlements not permitted. |  | Without contract linkage, audit defense cannot prove the entitlement; renewal workflow has no anchor; true-up triggers have no source.
7 | Entitlement validity buffer — calendar days before expiry to alert? | 120 days (lead time for renewal negotiation) and 30 days (escalation if not renewed). |  | Most enterprise renewal cycles need 90-120 days. The 30-day backstop catches stalls. Per-product overrides allowed for products with shorter negotiation lead times.
8 | Entitlement adjustment workflow — automated true-up or human approval? | Human approval at MVP. Auto-true-up surfaces in a queue routed to Procurement + SAM Process Owner; both sign. |  | Auto-true-up at MVP creates surprise commercial exposure. Human gate maintains discipline; selective automation can come later for low-risk products.

## Dependencies
01 — Entitlement Catalog — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | AP-06 workbooks 01-06 imported and validated | Required | ECS | Sprint 1 Wk 2 | Foundations prerequisites
2 | Vendor Management contract records exist | In Progress | ECS | Sprint 1 Wk 2 | Required for entitlement → contract link
3 | Procurement contract extracts (last 24 months active) | Pending | Customer | Sprint 2 Wk 1 | PDF or structured data; ECS normalizes
4 | Top 20 publisher entitlement spreadsheets (current state) | Pending | Customer | Sprint 2 Wk 1 | What customer thinks they have, before ECS validates
5 | Audit history (last 2 years) reviewed | Pending | Customer + ECS | Sprint 2 Wk 1 | Findings inform entitlement validation

## Configuration Data
01 — Entitlement Catalog — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Entitlement Catalog
Total entitlement records at MVP | 150-300 | Estimated from product count × avg SKU count per product
Entitlement table | cmdb_sam_sw_entitlement | OOTB SAMP table
Granularity | Per license SKU | OOTB
Lookback window | 2 years (active + recently expired) | Older in archive
2. Required Fields per Entitlement
Product link | cmdb_sam_sw_entitlement.product | Reference to cmdb_sam_sw_product_definition
Contract link | cmdb_sam_sw_entitlement.contract | Reference to vmt_contract
Quantity | cmdb_sam_sw_entitlement.quantity | Integer; unit per license model
Unit of measure | cmdb_sam_sw_entitlement.unit | Choice: users / devices / cores / concurrent / etc.
Term start | cmdb_sam_sw_entitlement.term_start | Date
Term end | cmdb_sam_sw_entitlement.term_end | Date
True-up clause present | cmdb_sam_sw_entitlement.true_up_clause | Boolean
True-up trigger / frequency / lead time / owner | Fields populated if true_up_clause = Y | Required when true-up present
3. Alert Configuration
Renewal alert — first warning | 120 days before term_end | Routes to Procurement owner
Renewal alert — escalation | 30 days before term_end | Routes to SAM Process Owner + Procurement Director
True-up review cadence | Per true-up clause frequency (quarterly / annual) | Auto-scheduled
Unmapped entitlement bucket size budget | ≤2% of total | Above 2% triggers manual review
4. Adjustment Workflow
True-up approval | Procurement + SAM Process Owner (two-signature) | OOTB SAMP workflow
Adjustment audit trail | Auto-captured | Required for audit defense
Adjustment effective date | Customer to populate at approval | Backdating requires written justification

## R&R
01 — Entitlement Catalog — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Contract extraction from Procurement system | C | R | Customer-only; ECS provides extraction template
Entitlement quantity validation against contracts | R | C | ECS validates; Customer adjudicates discrepancies
Vendor Management contract linkage | R | C | ECS executes; Customer confirms contract coverage
True-up clause field population | R | C | ECS extracts from contract text; Customer validates
Renewal alert configuration | R | I | ECS configures; Customer informed of alert recipients
Audit history review and entitlement adjustments | R | C | ECS surfaces findings; Customer approves adjustments
Entitlement adjustment approval workflow | R | C | ECS configures workflow; Customer staffs approvers
First reconciliation run with entitlements | R | I | ECS executes; Customer reviews variance

## Consultant Guide
01 — Entitlement Catalog — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB Entitlement Foundations
Use cmdb_sam_sw_entitlement OOTB. Entitlements are per-SKU records linked to products (cmdb_sam_sw_product_definition) and contracts (vmt_contract). Granularity-per-SKU is the OOTB default; contract-level granularity is not OOTB-defensible because it hides per-SKU complexity that reconciliation needs.
True-up Clauses are the Critical Field
True-up clauses are the #1 source of unexpected SAM cost. Every entitlement with a true-up clause needs four specific fields populated: trigger condition (e.g., 'when install count exceeds 110%'), frequency (quarterly / semi-annual / annual), lead time before adjustment (typically 30-60 days), and named owner. Missing any one of these four turns a planned true-up into a fire drill.
Contract Linkage Discipline
Every entitlement record must link to a Vendor Management contract record (vmt_contract). Orphan entitlements are not permitted. Customers will request 'we don't have the contract scanned yet' — answer: 'we create the contract record first, then the entitlement.' The discipline holds; auditors specifically test for orphan entitlements.
Reconciliation Triggers from Entitlements
The renewal alert (120 days / 30 days backstop) and the true-up cadence are the two automated mechanisms entitlements drive. Both are OOTB. The 120-day lead is calibrated for typical enterprise negotiation cycles; products with faster cycles can override per-product. The 30-day backstop catches the cases where the 120-day alert was missed.
Sprint 2 Handoff
By end of Sprint 2 Wk 1, entitlement catalog is loaded for top 20 publishers. Sprint 2 Wk 2 picks up with reconciliation rules (workbook 02) and the first full reconciliation run against entitlements (vs the install-only reconciliation Sprint 1 produced). The variance from that first run is the credibility test.

## Adoption vs Re-engineering
01 — Entitlement Catalog — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We track entitlements at the contract level — one record per contract.' | Per-SKU entitlement records linked to one contract. | Contract-level granularity hides per-SKU complexity. One contract often grants 5-10 SKUs with different effective dates, true-up clauses, and quantities. | 'Let me show you the per-SKU reconciliation — it surfaces drift at the level the publisher actually enforces. Contract-level rolls up the SKUs and hides the variances.' | Never. Per-SKU is the OOTB-defensible answer.
'Historical entitlements should all be loaded — we want full lookback.' | Two-year lookback to entitlement table; older in archive. | Full history inflates the entitlement table and slows reconciliation queries; older entries have no active compliance signal. | 'Two years covers any active audit lookback window. Older records live in archive and are still queryable for the rare longer audit; they just aren't in the day-to-day reconciliation table.' | Specific industries with 7+ year audit obligations can extend. Default is 2.
'We don't need contract linkage at MVP — we know what we bought.' | Contract linkage required. Vendor Management contract records mandatory. | Orphan entitlements fail audit defense. Auditors test specifically for entitlement → contract linkage. | 'Audit defense starts with provable entitlements. Without the contract record, the entitlement is a claim; with it, it's evidence.' | Never.
'True-up clauses are too detailed — we can capture as a single notes field.' | Four required fields: trigger, frequency, lead time, owner. | A notes field becomes a place where critical detail gets lost. Each of the four fields drives a specific automated workflow. | 'The four fields each trigger a workflow. Notes don't trigger workflows; that's why the structured fields exist.' | Never.
'Auto-true-up at every threshold — we have the data, let the system act.' | Human approval at MVP. Auto-true-up surfaces a queue; Procurement + SAM Process Owner sign. | Auto-true-up creates surprise commercial exposure. Procurement controls when to negotiate vs. when to true-up; automating that decision strips control. | 'Auto-true-up makes the commercial decision for Procurement. The queue + two-signature pattern preserves negotiating leverage while still automating detection.' | Specific low-risk products (sub-$50K annual spend) can move to auto-true-up in subsequent year. Not at MVP.
'Renewal alerts at 90 days are enough — 120 is too early.' | 120 days first warning; 30 days escalation backstop. | Enterprise procurement negotiation cycles routinely run 60-90 days; 90-day alerts leave no buffer. 120 gives the negotiation team room. | '90 days seems generous until you're in the third week of a negotiation that's not closing. The 120-day lead is what gives Procurement leverage; 90 puts them in a corner.' | Specific publishers with faster cycles can override per-product. Not the global default.
'Free product entitlements should be tracked too.' | No entitlement records for free products. Tracked via product lifecycle state only. | Free entitlements have no compliance signal; reconciliation always produces 'unlimited entitlement'. They add noise without value. | 'Free products don't have an entitlement to reconcile against — they're tracked at the product level for inventory but they don't belong in the entitlement table.' | Never.

## ServiceNow Mapping
01 — Entitlement Catalog — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_entitlement | Entitlement record per license SKU | OOTB SAMP
vmt_contract | Vendor Management contract | OOTB Vendor Management
2. Field mapping
Product | cmdb_sam_sw_entitlement.product | Reference to cmdb_sam_sw_product_definition
Contract | cmdb_sam_sw_entitlement.contract | Reference to vmt_contract
Quantity | cmdb_sam_sw_entitlement.quantity | Integer
Unit of measure | cmdb_sam_sw_entitlement.unit | Choice field
Term start / Term end | term_start / term_end | Date fields
True-up clause | true_up_clause + 4 detail fields | Boolean + structured detail
Active | active flag | Boolean
3. OOTB features leveraged
Renewal alert workflow | Scheduled job + notification rules | 120-day + 30-day
True-up review workflow | Scheduled per clause frequency | OOTB
Adjustment approval workflow | Two-signature (Procurement + SAM PO) | OOTB SAMP
SAMP Workspace entitlement view | Native UI | Native
4. Integrations
Vendor Management module | Native ServiceNow | vmt_contract linkage
Procurement systems (Coupa, Ariba, SAP) | Manual + scheduled import | Per-customer
Audit defense pack (workbook 05) | Cross-references entitlement records | Internal