## Instructions
02 — Reconciliation Rules
SAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | The match logic that compares installs (left side) to entitlements (right side) and produces compliance variance per product. Reconciliation rules are where SAM proves its value — or fails to.
Who fills this out | ECS-led with Customer validation. ECS authors rules from product license models; Customer adjudicates edge cases.
Sprint window | Sprint 2, Week 2
Estimated effort | 12-20 hours including rule tuning across publishers
Related workbooks | 01 Entitlement Catalog · AP-06/04 Install & Usage Capture · 03 Vendor-Specific Licensing
Success criteria
• | Every in-scope product has an active reconciliation rule.
• | First full reconciliation produces ≤10% variance from contracted entitlement.
• | Per-product overrides documented for products that don't fit standard rules.
• | Reconciliation cadence (monthly + quarterly review) operational.

## Process Decisions
02 — Reconciliation Rules — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Reconciliation cadence — daily, weekly, monthly? | Monthly automated + quarterly review-with-action. Daily reconciliation is computational overkill at MVP; quarterly is too slow. |  | Monthly produces actionable cadence with manageable Procurement workload. Quarterly review formalizes Procurement engagement.
2 | Variance threshold — when does compliance break? | 100% compliant = green. 100-105% = yellow (within tolerance for most contracts). >105% = red (action required). |  | Most publishers tolerate 5% variance before triggering true-up. Going stricter creates false alarms; looser creates exposure.
3 | Bonus/extra-use allowance handling — per contract terms? | Yes. If contract specifies bonus user allowance, the rule encodes the bonus. |  | Some contracts (Microsoft EA, some Adobe enterprise) include explicit overage allowances. Rule must reflect contract specifics.
4 | Reconciliation for products without entitlement records? | Surface as 'No Entitlement' bucket. Routes to Procurement for sourcing. |  | Installs without entitlements are either unlicensed (compliance risk) or missing-contract (entitlement record gap). Either way, surface.
5 | Cross-product license grants — how handled? | Per-publisher license-grant rules. Microsoft 365 E5 grants Office, Teams, SharePoint, etc.; rule encodes the grant. |  | Big publishers' bundled licenses are the most common reconciliation complexity. Per-publisher rules are OOTB-defensible.
6 | Reciprocal usage — same user with multiple installs of the same product? | Count once per user for user-based; count each install for device-based. Per-product license model from AP-06 drives. |  | Counting reciprocal use as separate consumption double-counts user-based licenses. License model is the deciding factor.
7 | Stale install handling — how long before suppressing from reconciliation? | 180 days no usage signal → exclude from reconciliation count. Aligns with AP-06 lifecycle Inactive threshold. |  | Counting stale installs creates phantom consumption. 180-day alignment with lifecycle is OOTB.
8 | Exception products — how marked? | product.reconciliation_exception field. Logged with justification + sign-off + expiry date. |  | Some products genuinely cannot be reconciled (legacy custom-built, free-but-required). Mark them; don't pretend the rule works.

## Dependencies
02 — Reconciliation Rules — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Workbook 01 (Entitlement Catalog) populated | Required | ECS | Sprint 2 Wk 1 | Reconciliation needs both sides
2 | AP-06 workbook 04 (Install & Usage) operational | Required | ECS | Sprint 1 | Install data source
3 | Publisher contract grant tables (M365 bundling, etc.) | Pending | ECS | Sprint 2 Wk 1 | From publisher documentation
4 | Procurement willing to receive monthly variance report | Pending | Customer | Sprint 2 Wk 1 | Confirm recipient + format
5 | SAM Process Owner staffed (per AP-06 workbook 06) | In Progress | Customer | Ongoing | Required for quarterly review execution

## Configuration Data
02 — Reconciliation Rules — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Reconciliation Rule Coverage
Active reconciliation rules at MVP | 75 (one per product, from AP-06 workbook 02) | Some products share base rules
Rule table | cmdb_sam_sw_recon_rule | OOTB SAMP
Cadence | Monthly automated; quarterly review-with-action | OOTB schedule
Variance thresholds | 100-105% yellow; >105% red | Per-product overrides allowed
2. Cross-Product Grants (Bundle Rules)
Microsoft 365 E5 grants | Office, Teams, SharePoint, OneDrive, Power Platform basics | Encoded as rule
Microsoft 365 E3 grants | Office, Teams, SharePoint, OneDrive | Encoded as rule
Adobe Creative Cloud All Apps grants | All Creative Cloud apps | Encoded as rule
Office 365 with EMS grants | Office + Intune CALs | Encoded as rule
Customer-specific bundle grants (list TBD) | Customer to add | Per-publisher
3. Reconciliation Behavior
User-based count rule | Count once per user with active install | Excludes 180-day inactive
Device-based count rule | Count each device install (active) | Excludes 180-day inactive
Capacity-based count rule | Sum of cores / PVUs / capacity units | Per-vendor calculation
Concurrent count rule | Peak simultaneous user count (rolling 30-day max) | OOTB
4. Output / Reporting
Monthly variance report — recipient | Procurement + SAM Process Owner | Auto-routed
Quarterly review report — recipient | SAM Steering Committee | Includes trending
Variance report — exception products excluded | Yes, with separate exception list | OOTB
No-entitlement bucket review cadence | Monthly | Routed to Procurement for sourcing

## R&R
02 — Reconciliation Rules — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Reconciliation rule authoring per product | R | C | ECS authors; Customer validates
Bundle / cross-product grant rule encoding | R | C | ECS extracts from publisher docs; Customer validates
Exception product identification and sign-off | C | A | Customer decides; ECS configures
First full reconciliation run execution | R | I | ECS runs; Customer reviews variance
Variance triage (per-product) | R | C | ECS provides report; Customer adjudicates
Monthly automated reconciliation oversight | I | R | Customer-led post Foundations
Quarterly review with Procurement | C | R | Customer-led; ECS supports first cycle
Rule tuning based on variance findings | R | C | ECS adjusts; Customer signs off

## Consultant Guide
02 — Reconciliation Rules — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB Reconciliation Foundations
Use cmdb_sam_sw_recon_rule OOTB. Rules are per-product with the option of per-product overrides on top of standard rule templates. The OOTB SAMP reconciliation engine handles user-based, device-based, capacity-based, and concurrent licensing models natively; cross-product grants (Microsoft 365 bundling, Adobe Creative Cloud, etc.) are encoded as discrete rules referenced by the affected products.
The First Reconciliation is the Credibility Moment
The first full reconciliation run is when SAM proves its value or loses its mandate. Target: variance ≤10% from contracted entitlement at first run. Above 10%, customer concludes 'SAM data is unreliable' and Realization becomes hard to defend. The path to ≤10%: clean entitlement catalog (workbook 01), tuned rules per product, exception products clearly marked, no-entitlement bucket separated.
Cross-Product Grants are the #1 Variance Source
Microsoft 365 E5 grants Office, Teams, SharePoint, and others; if the reconciliation rule doesn't encode the grant, all four products show as over-deployed against their nominal entitlements. The first variance triage almost always surfaces 'we're 800% over on Office' — and the answer is 'because the M365 E5 grant rule isn't encoded yet.' Pre-encode the major bundles before the first reconciliation run.
Exception Products are Honesty
Some products genuinely cannot be reconciled by the rule engine — legacy custom-built systems, embedded firmware, freely-licensed development tools. Mark them with reconciliation_exception flag, capture the justification, set an expiry date for re-review. Pretending the rule works produces noise that erodes confidence in the rules that do work.
Sprint 3 Handoff
By end of Sprint 2 Wk 2, rules authored and first reconciliation run complete. Sprint 3 picks up with vendor-specific licensing (workbook 03) which deepens the rules for Oracle, Microsoft enterprise, IBM, SAP, Adobe enterprise, and Salesforce. The True-Up Forecast (workbook 04) consumes reconciliation output to project 12-month exposure.

## Adoption vs Re-engineering
02 — Reconciliation Rules — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'Daily reconciliation — we want real-time compliance.' | Monthly automated + quarterly review. Daily is computational overkill. | Daily reconciliation produces noise (install data takes time to settle); monthly produces actionable signal. Most customers who run daily turn it off within a quarter. | 'Daily compliance sounds appealing, but the daily variance is mostly install-data settling noise. Monthly is when the signal is clean enough to act on.' | Never at MVP.
'Strict 100% compliance threshold — any overage is red.' | 100-105% yellow; >105% red. Aligned with publisher tolerance. | Strict 100% creates false alarms. Most publishers explicitly tolerate 5% variance before invoking true-up. | 'Publishers themselves tolerate 5% variance before invoking true-up clauses. A 100% strict threshold creates alerts where the publisher itself isn't concerned.' | Specific high-risk publishers (Oracle, IBM) can have stricter thresholds per-product. Not the global default.
'No-entitlement installs should be auto-suppressed — they're noise.' | Surface in dedicated bucket. Routes to Procurement for sourcing. | No-entitlement installs are either unlicensed (compliance risk) or missing-contract (gap). Auto-suppression hides both. | 'The No-Entitlement bucket is exactly where audit findings come from. Hiding it doesn't reduce risk — it defers it to the auditor.' | Never.
'Cross-product grants are too complex — count each product independently.' | Encode bundle grants as rules. Independent counting double-counts M365 / Adobe CC. | Independent counting against nominal entitlements produces 'we're 800% over on Office' false alarms. Bundle rules are OOTB. | 'The bundle rules are exactly what SAMP was designed to handle. Let me show you the M365 E5 grant rule — it eliminates the false-overage on the bundled products.' | Never. Bundle rules are required.
'Stale installs should count — we paid for them.' | 180-day inactive threshold; stale installs excluded. | Counting stale installs creates phantom consumption that obscures actual variance. The 180-day threshold aligns with AP-06 lifecycle. | 'Stale installs aren't actual usage — they distort the variance. The reclamation workflow in AP-06 is how you recover those licenses; counting them as active doesn't help.' | Never.
'Concurrent licensing — count current actives, not 30-day peak.' | 30-day peak. Aligns with how publisher contracts measure. | Current actives miss the contract-relevant peak that drives compliance. Publishers measure peak. | 'Publishers contractually measure peak concurrent usage, not point-in-time. The 30-day peak is the contractually-relevant number.' | Specific concurrent licensing contracts with different measurement windows can override. Default is 30-day peak.
'Exception products shouldn't exist — every product should have a rule.' | Exception products are honesty. Reconciliation_exception flag with justification + expiry. | Forcing a rule on a product that genuinely can't be reconciled produces noise that erodes confidence in valid rules. | 'Some products genuinely can't be rule-reconciled — legacy custom systems, free dev tools. Marking them honestly preserves the credibility of the rules that do work.' | Always. Exception flag is the OOTB-supported pattern.

## ServiceNow Mapping
02 — Reconciliation Rules — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_recon_rule | Reconciliation rule per product | OOTB SAMP
cmdb_sam_sw_recon_result | Per-run reconciliation results | OOTB SAMP
cmdb_sam_sw_bundle_grant | Cross-product bundle grants | OOTB SAMP
2. Field mapping
Product | cmdb_sam_sw_recon_rule.product | Reference
Rule type | cmdb_sam_sw_recon_rule.rule_type | Choice: user/device/capacity/concurrent
Variance threshold (yellow) | cmdb_sam_sw_recon_rule.threshold_yellow | Default 100%
Variance threshold (red) | cmdb_sam_sw_recon_rule.threshold_red | Default 105%
Exception flag | cmdb_sam_sw_product_definition.reconciliation_exception | Boolean
Last run timestamp | cmdb_sam_sw_recon_result.run_time | Datetime
Variance percent | cmdb_sam_sw_recon_result.variance_pct | Calculated
3. OOTB features leveraged
Reconciliation engine | OOTB SAMP | Monthly + on-demand
Bundle grant rules | cmdb_sam_sw_bundle_grant | Pre-loaded for major publishers
Variance reports | Scheduled + ad-hoc | OOTB
SAMP Workspace compliance view | Reads recon_result table | Native
4. Integrations
Install data (AP-06 workbook 04) | cmdb_sam_sw_install | Reconciliation input
Entitlement data (workbook 01) | cmdb_sam_sw_entitlement | Reconciliation input
True-up forecast (workbook 04) | Consumes recon_result | Forward projection
Audit defense pack (workbook 05) | Cross-references rules | Evidence chain