## Instructions
05 — Audit Defense
SAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | The audit response playbook: when an audit lands, who does what, in what order, and with what evidence. Audit defense is the moment SAM's investment pays back; without this playbook, audit response becomes a fire drill.
Who fills this out | ECS-built playbook; Customer staffs the named roles. Sample audit pack lives separately (not in this workbook).
Sprint window | Sprint 4, Week 1
Estimated effort | 4-8 hours playbook customization to customer context
Related workbooks | 01 Entitlement Catalog · 02 Reconciliation Rules · 03 Vendor-Specific Licensing
Success criteria
• | Named audit response roles staffed (Audit Lead, Procurement Lead, Legal Liaison, SAM Process Owner).
• | Evidence pack template structure agreed.
• | Escalation matrix in place for findings ≥ defined dollar threshold.
• | Communication discipline rules captured (what to share, what to hold).

## Process Decisions
05 — Audit Defense — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Audit response lead — SAM Process Owner or external? | SAM Process Owner leads internally; external counsel engaged at finding threshold (typically >$250K). |  | Internal lead preserves negotiation flexibility; external counsel preserves privilege for high-dollar findings.
2 | Initial response time SLA — calendar days to acknowledge? | 5 business days to acknowledge; 30 days to first evidence pack. |  | Most audit clauses specify 30-day response for evidence; 5-day acknowledgment establishes good-faith engagement.
3 | Evidence pack structure — single document or layered? | Layered: executive summary (1 page) + per-product detail + raw data appendix. |  | Layered structure controls disclosure; auditors get what they're entitled to without volunteering peripheral information.
4 | Communication channels — single point of contact? | Single point of contact: Audit Lead. All auditor communication routes through Audit Lead. |  | Multiple channels create the situation where different responses contradict each other; single-channel discipline is non-negotiable.
5 | Privilege protection — when to invoke legal? | At first audit notice. Legal copied on all auditor communications from day 1. |  | Privilege has to be invoked at the start; invoking later in the audit doesn't retroactively cover earlier communications.
6 | Finding response — accept, negotiate, dispute? | Three-tier framework: <$50K threshold → accept and settle; $50K-$250K → negotiate with vendor; >$250K → engage external counsel and dispute selectively. |  | Thresholds tune the response effort to the dollar exposure. Settling every finding under $50K saves negotiation effort for the consequential findings.
7 | Audit cost capture — how tracked? | Each audit gets a tracking record with: internal hours, external counsel fees, settlement amount, lessons learned. |  | Audit cost data feeds the program's ROI story (workbook 08 KPIs). Without capture, the program's value is invisible.

## Dependencies
05 — Audit Defense — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Workbooks 01-03 (entitlements, rules, vendor-specific) operational | Required | ECS | Sprint 3 Wk 2
2 | Customer Legal liaison identified | Pending | Customer | Sprint 4 Wk 1 | Named individual for privilege
3 | Customer Procurement Lead for audit responses identified | Pending | Customer | Sprint 4 Wk 1
4 | External counsel relationship (pre-engaged) | Pending | Customer | Sprint 4 Wk 1 | Pre-engaged at retainer level
5 | Audit history (last 5 years) reviewed | Pending | ECS + Customer | Sprint 4 Wk 1 | Lessons learned input

## Configuration Data
05 — Audit Defense — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Named Audit Response Roles
Audit Lead | SAM Process Owner | Single point of contact with auditor
Procurement Lead | Customer to name | Negotiates settlements
Legal Liaison | Customer to name | Privilege + dispute strategy
External Counsel | Pre-engaged firm | Engaged at >$250K threshold
SAM Technical Lead | ECS Solution Architect during engagement; Customer post-go-live | Evidence pack assembly
2. Response SLAs
Audit notice acknowledgment | 5 business days | From audit letter date
First evidence pack delivery | 30 calendar days | Aligned with typical audit clauses
Follow-up evidence requests | 10 business days each | Standard
Finding response | 30 calendar days from finding receipt | Negotiation window
3. Evidence Pack Structure
Layer 1: Executive Summary (1 page) | Findings count, total exposure, key contested items | What auditor's manager reads
Layer 2: Per-Product Detail | Entitlement records, reconciliation results, exception products | What auditor reviews
Layer 3: Raw Data Appendix | Install records, contract excerpts, ILMT outputs | Provided on request only
Customer-specific evidence (legal, M&A, etc.) | Layer 3 with privilege markings | Controlled disclosure
4. Finding Response Tiers
Tier 1: <$50K finding | Accept and settle | Save negotiation effort
Tier 2: $50K-$250K finding | Negotiate with vendor (internal) | Procurement Lead-led
Tier 3: >$250K finding | External counsel + selective dispute | Privilege-protected
Finding threshold customization | Customer-specific (size-of-finding context) | Per customer's commercial baseline
5. Communication Discipline
Single channel — Audit Lead only | Yes (enforced) | No side-channel auditor conversations
Auditor questions — written-only | Yes | Verbal conversations summarized in writing
Internal status comms | Weekly to Sponsor + Steering | Maintains executive visibility
Privilege markings on all internal docs | Yes | From day 1

## R&R
05 — Audit Defense — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Audit notice receipt and triage | C | R | Customer-only; ECS supports during engagement
Named-role staffing | I | R | Customer-only
Evidence pack assembly (initial) | R | C | ECS Solution Architect during engagement; Customer post-go-live
Auditor communication management | C | R | Customer Audit Lead; ECS supports
Negotiation with vendor (Tier 2 findings) | C | R | Customer Procurement; ECS supports
External counsel engagement (Tier 3 findings) | I | R | Customer Legal
Settlement execution | I | R | Customer-only
Post-audit lessons learned capture | R | C | ECS facilitates first audit; Customer continues

## Consultant Guide
05 — Audit Defense — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB Audit Defense Foundations
Audit defense isn't a ServiceNow feature — it's a process built on the data SAMP collects. The playbook in this workbook is the operational discipline that converts SAMP data into audit-ready evidence. The playbook is publisher-agnostic; vendor-specific traps from workbook 03 cross-reference into the per-product evidence sections.
The First Hour of an Audit
When an audit notice arrives, the first hour determines the next six months. Steps: (1) Audit Lead acknowledges receipt by close of business; (2) Legal Liaison copied; (3) external counsel notified of pending engagement; (4) initial scope assessment by SAM Process Owner; (5) first internal status to Sponsor by end of day. Skipping any of these five creates downstream friction.
Layered Evidence Pack Discipline
The three-layer evidence pack structure — executive summary, per-product detail, raw data appendix — is the disclosure-control mechanism. Auditors get what their scope entitles them to; volunteering raw data appendix material proactively often surfaces additional audit threads. Layer 3 is provided on request only, never up-front.
Finding Tier Discipline
Three-tier finding response (<$50K accept, $50K-$250K negotiate, >$250K external counsel) is what keeps audit response effort proportional to exposure. Customers who negotiate every finding regardless of size run out of negotiation capital before reaching the consequential findings. Customers who escalate every finding to external counsel run up legal fees that exceed the findings themselves.
Privilege from Day 1
Privilege has to be invoked at the start. Legal Liaison copied on all auditor communications from day 1; privilege markings on all internal audit documents from day 1. Invoking privilege three weeks in does not retroactively cover earlier communications. This is the single most-skipped audit defense step among unprepared customers.
Sprint 4 Handoff
By end of Sprint 4 Wk 1, audit defense playbook customized to customer context and named roles staffed. Sprint 4 Wk 2 picks up with cloud SaaS subscription mgmt (workbook 06). Audit defense doesn't have a 'go-live' moment — it's ready when the next audit notice lands. The first dry-run exercise (tabletop) is recommended within 6 months of go-live.

## Adoption vs Re-engineering
05 — Audit Defense — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We don't need a playbook — when we get audited we'll figure it out.' | Playbook is required. Improvised audit response averages 3x the cost of playbook-driven response. | Audit response without a playbook produces inconsistent communications, missed deadlines, and disclosure mistakes. Each of those compounds. | 'The audit cost data is unambiguous. Customers without a playbook average 3x the response cost and 1.5x the settlement amount of customers with one. The playbook is the highest-ROI hour you'll spend on SAM.' | Never.
'Audit Lead can rotate — split across multiple owners.' | Single Audit Lead. Rotation produces inconsistent communications. | Multiple Audit Leads invariably produce contradicting responses to the auditor; auditors exploit this systematically. | 'Single Audit Lead is the discipline that prevents the auditor playing different responses against each other. Rotation can happen between audits, not within one.' | Never within a single audit.
'Send the auditor everything up-front — show good faith.' | Layered evidence; Layer 3 on request only. | Volunteering raw data surfaces audit threads beyond the scope of the engagement. Good faith doesn't require pre-emptive disclosure. | 'Good faith means meeting your contractual evidence obligations completely. Pre-emptive disclosure isn't good faith — it's expanded scope. The layered structure meets the obligation precisely.' | Never.
'Skip the small findings — focus only on big ones.' | Accept-and-settle <$50K findings to preserve negotiation capital for big ones. | Trying to negotiate every finding burns Procurement and Legal time on small dollar amounts; the big findings get less attention. | 'Settling small findings isn't admitting fault — it's preserving negotiation capacity for the consequential ones. The three-tier framework concentrates effort where the dollars are.' | Never. Three-tier is OOTB-defensible.
'Verbal conversations with the auditor are fine — saves time.' | Written-only. Verbal conversations summarized in writing. | Verbal conversations create ambiguity later about what was discussed and agreed. Written discipline preserves the record. | 'Written-only is what protects both sides. If the auditor asks something verbally, you summarize in writing and confirm. It's not slower; it's safer.' | Never.
'Privilege markings are paranoid — we have nothing to hide.' | Privilege from day 1. | Privilege isn't about hiding; it's about controlling what the auditor can compel. Without it, internal strategic discussions become discoverable in disputes. | 'Privilege isn't about concealment — it's about preserving your negotiation latitude. Invoking it at day 1 keeps options open; invoking it later doesn't cover earlier discussions.' | Never.
'External counsel for any audit — they handle it best.' | External counsel at >$250K threshold; internal handling below. | External counsel below the threshold runs up fees that exceed the findings. Internal handling below $250K is OOTB. | 'External counsel is the right call when the dollar exposure justifies it. Below $250K, internal handling is more efficient — the fees would exceed the finding.' | Never below threshold.

## ServiceNow Mapping
05 — Audit Defense — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_audit_case | Audit case record | OOTB SAMP audit module
cmdb_sam_sw_audit_evidence | Evidence pack components | OOTB SAMP
cmdb_sam_sw_audit_finding | Auditor findings | OOTB SAMP
2. Field mapping
Auditor | cmdb_sam_sw_audit_case.auditor | Reference to publisher
Audit period | cmdb_sam_sw_audit_case.period_start / period_end | Date range
Audit Lead | cmdb_sam_sw_audit_case.audit_lead | Reference to sys_user
Status | cmdb_sam_sw_audit_case.status | Choice: Acknowledged / Evidence / Finding / Settlement / Closed
Finding amount | cmdb_sam_sw_audit_finding.amount | Currency
Finding tier | cmdb_sam_sw_audit_finding.tier | Choice: 1 / 2 / 3
Privilege flag | cmdb_sam_sw_audit_case.privileged | Boolean
3. OOTB features leveraged
Audit case management workflow | OOTB SAMP | Status-driven workflow
Evidence pack assembly | OOTB report templates | Layered output
SAMP Workspace audit view | Native UI | Audit Lead's working surface
4. Integrations
Reconciliation results (workbook 02) | Evidence source | Auto-attached
Entitlement records (workbook 01) | Evidence source | Auto-attached
Legal Hold (if licensed) | Native ServiceNow integration | Privilege markings
Document Management | Native | Evidence pack storage