## Instructions
08 — KPIs & Savings Tracking
SAM Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | The SAM program's KPIs: reclamation savings, audit cost avoidance, renewal savings, license utilization rate. These are the metrics that justify SAM as a profit center and protect the program budget.
Who fills this out | ECS-built KPI configuration; Customer SAM Process Owner reports monthly.
Sprint window | Sprint 5, Week 2
Estimated effort | 4-8 hours including KPI calibration
Related workbooks | 02 Reconciliation Rules · 05 Audit Defense · 07 Renewal Workflow
Success criteria
• | Six core KPIs operational with monthly auto-refresh.
• | First quarterly SAM Steering Committee review delivered with KPI pack.
• | Annual savings projection produces credible 12-month estimate.
• | Baseline (pre-SAM) cost data captured for ROI comparison.

## Process Decisions
08 — KPIs & Savings Tracking — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Core KPI set — six metrics or expanded? | Six core: Reclamation Savings, Audit Cost Avoidance, Renewal Savings, License Utilization Rate, Compliance Variance, Forecast Accuracy. |  | More KPIs dilute focus. Six is enough to tell the full SAM story without overwhelming the audience.
2 | Baseline cost data — pre-SAM or pre-program? | Pre-program (year before SAM Realization started). Pre-SAM is too far back; data is unreliable. |  | Pre-program baseline gives credible ROI comparison; pre-SAM (multi-year lookback) typically lacks reliable data.
3 | Reclamation savings — gross or net? | Net (reclamation savings minus reclamation workflow operating cost). |  | Gross reclamation is the publisher-facing number; net is the honest savings number that survives scrutiny.
4 | Audit cost avoidance — how calculated? | Audit findings prevented (vs. industry benchmark) plus negotiated reduction on actual audit findings. |  | Industry benchmark for unprepared audits is roughly 1.5-2x prepared response. Difference is the avoidance value.
5 | Renewal savings — vs. publisher list or vs. prior contract? | Both. Two metrics: savings vs. publisher list (negotiation effectiveness) and savings vs. prior contract (containment). |  | Single metric tells half the story. Vs. publisher list shows discount; vs. prior contract shows price discipline.
6 | License utilization rate — across all products or per-product? | Aggregate (program-wide) + per-product detail. Aggregate for executive view; per-product for operational view. |  | Aggregate is the headline; per-product is where the operational story lives.
7 | KPI reporting cadence — monthly or quarterly? | Both. Monthly automated dashboard; quarterly executive pack to Steering Committee. |  | Monthly catches drift in time to act; quarterly pack maintains executive visibility.
8 | Annual savings projection methodology? | Trailing 12-month savings × forward growth factor (default 1.0 unless customer-specific reason to project growth). |  | Conservative projection survives scrutiny. Growth factor > 1.0 requires explicit justification.

## Dependencies
08 — KPIs & Savings Tracking — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Workbooks 02 (reconciliation), 05 (audit), 07 (renewal) operational | Required | ECS | Sprint 5 Wk 1
2 | Pre-program baseline cost data extracted | Pending | Customer Procurement + Finance | Sprint 5 Wk 1 | Year prior to SAM Realization start
3 | SAM Steering Committee meeting cadence established | Pending | Customer | Sprint 4 Wk 2
4 | SAM program operating cost data | Pending | Customer Finance | Sprint 5 Wk 1 | ECS fees + customer FTE allocation; for net savings calc

## Configuration Data
08 — KPIs & Savings Tracking — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Six Core KPIs
KPI 1: Reclamation Savings (net) | Annual reclaimed license value minus operating cost | OOTB SAMP KPI
KPI 2: Audit Cost Avoidance | Industry benchmark minus actual audit response cost | OOTB SAMP KPI
KPI 3: Renewal Savings vs. Publisher List | Sum of (list - settled) per renewal | OOTB SAMP KPI
KPI 4: License Utilization Rate | Active installs / total entitled | OOTB SAMP KPI
KPI 5: Compliance Variance Rate | Products with variance >5% / total in-scope products | OOTB SAMP KPI
KPI 6: Forecast Accuracy | Avg absolute variance of 12mo forecast vs. actual | OOTB SAMP KPI
2. Baseline Cost Data
Pre-program annual license spend | Customer to populate | From Finance records
Pre-program audit cost (last 24 months) | Customer to populate | From Finance records
Pre-program reclamation rate (if measured) | Customer to populate (estimate if not measured) | For comparison
3. Operating Cost Capture
ECS Realization fees | From SOW | Allocated annually
Customer SAM team FTE allocation | Customer to populate | Per HR data
Tool costs (ServiceNow SAMP licenses) | From contract | Reference
Total operating cost | Sum of above | For net savings calc
4. Reporting Configuration
Monthly KPI dashboard | OOTB SAMP dashboard | Native UI
Quarterly Steering Committee pack | OOTB report template | Executive-ready
Annual SAM program review pack | OOTB report template | Year-end pack
Dashboard recipients | Customer to staff | SAM Process Owner + Steering Committee + Sponsor
5. Annual Savings Projection
Projection methodology | Trailing 12-month × growth factor | OOTB SAMP
Default growth factor | 1.0 | Conservative
Customer-specific growth factor override | Customer to populate if applicable | Requires justification

## R&R
08 — KPIs & Savings Tracking — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
KPI configuration in SAMP | R | I | ECS configures the six KPIs
Baseline cost data extraction | C | R | Customer Finance + Procurement
Operating cost capture | R | C | ECS extracts SOW; Customer adds FTE allocation
Monthly KPI dashboard review | I | R | Customer SAM Process Owner
Quarterly Steering Committee pack delivery | C | R | Customer-led; ECS supports first 2 quarters
Annual SAM program review | C | R | Customer-led; ECS contributes during engagement
KPI tuning based on actual data | R | C | ECS proposes adjustments; Customer approves
ROI reporting to Sponsor and Finance | I | R | Customer-only

## Consultant Guide
08 — KPIs & Savings Tracking — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
OOTB KPI Foundations
Use OOTB SAMP KPIs. The six core KPIs cover the full SAM value story: cost recovery (reclamation), risk reduction (audit), commercial discipline (renewal), efficiency (utilization), compliance (variance), and predictive accuracy (forecast). All six are OOTB; no custom KPI infrastructure required.
The KPI Pack is the Budget Defense
The quarterly Steering Committee pack is what protects the SAM program budget. Programs without quantified KPIs lose budget when the company tightens; programs with quantified savings keep budget regardless. Spending the four hours per quarter to maintain the KPI pack is the single highest-ROI activity in SAM operations.
Net Savings, Not Gross
Always report reclamation savings net of operating cost. Gross numbers look better but get attacked in budget review when someone asks 'what does this program cost?' Net numbers survive the scrutiny because the program cost is already factored in.
Audit Cost Avoidance is the Hardest to Communicate
Audit cost avoidance is genuinely valuable but hard to communicate to Finance because the savings are 'didn't spend' rather than 'did save.' Frame it as: industry benchmark cost per audit (unprepared) is X; our actual cost per audit (prepared) is Y; the difference is avoidance. Concrete numbers survive better than abstract claims.
Conservative Projection Survives Scrutiny
Annual savings projection uses trailing 12-month × growth factor (default 1.0). Aggressive projections produce headlines but get attacked when actuals fall short. Conservative projections produce reliable budget defense year after year.
Sprint 5 Handoff
By end of Sprint 5 Wk 2, all six KPIs operational and first month's data collected. Sprint 6 picks up with go-live preparation and hypercare planning. The first quarterly Steering Committee KPI pack delivers in Sprint 6.

## Adoption vs Re-engineering
08 — KPIs & Savings Tracking — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'More KPIs = better visibility.' | Six core KPIs. More dilutes focus. | Twelve-KPI dashboards become wallpaper. Six is the maximum that executive audiences track. | 'Executive attention is the constraint. Six KPIs get tracked; twelve become a wall of numbers that gets ignored.' | Operational dashboards can have more detail; executive KPI set stays at six.
'Pre-SAM baseline — go back 3-5 years for the full story.' | Pre-program baseline (one year prior). | Multi-year baseline has unreliable data and risks comparing apples to oranges (org changes, M&A, etc.). | 'Pre-program baseline is the most defensible comparison. Multi-year lookback inevitably has confounding changes that get challenged in review.' | Never multi-year.
'Gross savings — that's the publisher-facing number.' | Net savings (gross minus operating cost). | Gross savings looks bigger but loses credibility in budget defense. Net survives scrutiny. | 'Gross savings is what we tell publishers we recovered. Net savings is what we tell Finance the program returns. The latter is the one that protects budget.' | Specific external comms can use gross; internal/budget always net.
'Aggressive growth factor in the projection — show the upside.' | Default 1.0; override requires justification. | Aggressive projections look great until actuals fall short. Conservative projections build trust over years. | 'Aggressive projections set up year-three credibility problems. Conservative projections build trust year over year — and conservative isn't bad news, it's just reliable news.' | Customer-specific justification (e.g., known M&A integration) can support higher factor. Default stays 1.0.
'Audit cost avoidance — too abstract, skip it.' | Include it. Frame concretely vs. industry benchmark. | Audit cost avoidance is among the largest SAM savings categories. Skipping it removes the second-largest part of the SAM ROI story. | 'Audit avoidance is real money. The framing — industry benchmark minus actual — makes it concrete enough for Finance to credit it. Skipping it gives away the second-biggest part of your ROI story.' | Never.
'Per-product KPIs in the executive pack — show the detail.' | Aggregate in exec pack; per-product detail in operational view. | Per-product detail in the exec pack overwhelms the executive audience. Aggregate is the headline; detail is for SAM Process Owner. | 'Exec pack is for the headline KPIs. Per-product detail is for the operational view that the SAM Process Owner uses monthly.' | Never in exec pack.
'Annual reporting cadence — quarterly is too frequent.' | Monthly dashboard + quarterly Steering Committee pack. | Annual cadence loses the operational signal. Quarterly maintains executive engagement. | 'Annual is the post-mortem; quarterly is the operating cadence. The KPI pack is what keeps the program visible and protected.' | Never.

## ServiceNow Mapping
08 — KPIs & Savings Tracking — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Primary table(s)
cmdb_sam_sw_kpi | KPI definition records | OOTB SAMP
cmdb_sam_sw_kpi_value | KPI value history (monthly snapshots) | OOTB SAMP
cmdb_sam_sw_program_cost | Program operating cost record | OOTB SAMP
2. Field mapping
KPI name | cmdb_sam_sw_kpi.name | One of six core KPIs
KPI calculation script | cmdb_sam_sw_kpi.calculation | JS
KPI target value | cmdb_sam_sw_kpi.target | Customer-set
Monthly value | cmdb_sam_sw_kpi_value.month / value | Time series
Baseline (pre-program) | cmdb_sam_sw_kpi.baseline | From Customer Finance data
Trailing-12 projection | cmdb_sam_sw_kpi.projection | Calculated
3. OOTB features leveraged
SAMP KPI dashboard | OOTB | Native UI
Quarterly Steering Committee pack | OOTB report template | Auto-assembled
Annual SAM program review pack | OOTB report template | Year-end
Performance Analytics integration | Native (if PA licensed) | Cross-program KPI roll-up
4. Integrations
Reconciliation results (workbook 02) | Compliance Variance KPI input | Native
Audit outcomes (workbook 05) | Audit Cost Avoidance input | Native
Renewal outcomes (workbook 07) | Renewal Savings input | Native
Forecast accuracy (workbook 04 vs. actual) | Forecast Accuracy input | Native
Customer Finance system | Baseline + operating cost data | Manual import