# 1.  How to Use This Question Bank

Use these questions across 1-3 discovery sessions before SOW development. Not all questions are appropriate for every call — select based on conversation context and audience. Mark answers in your notes; high-risk answers should shape SOW scope and Sprint 0 planning.

# 2.  1. Platform and Technical Baseline

| Question | Why It Matters | High-Risk Answer |
| --- | --- | --- |
| What ServiceNow modules are currently licensed? | Confirms scope boundaries and prevents out-of-scope assumptions | Unknown or 'we'll find out' — means no license inventory |
| What version are you on today? | Pre-Quebec instances have significant OOTB gaps; affects sprint planning | Pre-Quebec or customer doesn't know |
| How many update sets are in your current instance? | High update set count = high customization debt = higher risk | More than 50 unexplained update sets |
| Have you had a ServiceNow Health Scan or Technical Assessment? | Health Scan reveals hidden technical debt before we scope | No — means we're scoping blind |
| Who administers the ServiceNow instance today? | Determines whether we have a capable customer IT partner | External party not engaged in the project |
| Are you on a shared instance or dedicated? | Shared instances have change control restrictions that affect sprint velocity | Shared with other business units or agencies |
| Do you have a Dev / Test / Prod environment separation? | No separation = no safe place to configure | No — all work goes directly to production |

# 3.  2. Process and Organizational Readiness

| Question | Why It Matters | High-Risk Answer |
| --- | --- | --- |
| Who are the process owners for ITSM today? | Process owners are required for workshop participation and decision-making | No identified process owners / IT owns everything |
| How are incidents managed today — tool and process? | Baseline for OOTB gap analysis in Sprint 1 workshops | Multiple tools, no standard process |
| What does your current approval process look like? | Complex approval chains often drive customization requests | More than 3 sequential approval levels for routine requests |
| How many catalog items do you currently have, and how were they built? | Large custom catalog = Sprint 2 re-rationalization effort | More than 200 items, most custom-built |
| Have you documented your ITSM processes? | Undocumented process = workshop will surface surprises | No documented processes or last updated more than 3 years ago |
| What is your change advisory board (CAB) model? | Non-standard CAB models often require Change module customization | Daily CAB with 30+ approvers, or no CAB at all |
| What percentage of incidents are handled via self-service today? | Low self-service adoption = Virtual Agent/Employee Center priority | Under 20% self-service adoption |

# 4.  3. Stakeholder and Governance

| Question | Why It Matters | High-Risk Answer |
| --- | --- | --- |
| Who has final authority on process design decisions? | Unclear authority = delayed decisions = sprint blockers | Committee of 10+ stakeholders, no clear tie-breaker |
| Has IT leadership aligned on the OOTB-first delivery model? | Without IT buy-in, customization pressure will derail delivery | IT leadership not yet engaged / heard about project third-hand |
| What happened with your last ServiceNow project (if any)? | Past failures reveal organizational and technical risk patterns | Prior project was cancelled, went over budget, or was never adopted |
| Who will be the dedicated customer PM for this engagement? | Part-time PMs create communication gaps and decision delays | PM is also handling 3 other projects / PM not yet identified |
| Is there a change management / OCM workstream? | Without OCM, user adoption fails regardless of technical quality | No OCM plan / IT will handle all communications |
| What is the executive sponsor's level of engagement? | Disengaged sponsors cannot break customization deadlocks | Sponsor is 'available for escalations only' |

# 5.  4. Scope and Commercial

| Question | Why It Matters | High-Risk Answer |
| --- | --- | --- |
| What modules are in scope for this engagement? | Uncontrolled scope is the #1 cause of OOTB delivery failure | All of them / whatever you think we need |
| What does 'go-live' mean to your organization? | Different definitions of go-live create project end-state ambiguity | Full feature parity with legacy system |
| What are the hard deadlines, if any? | Regulatory or audit deadlines compress sprint flexibility | Must go live by a date that doesn't allow 18 weeks |
| What is the budget envelope for this project? | Under-budgeted projects lead to scope pressure and OOTB shortcuts | Budget not yet approved / we'll figure it out |
| Are there any known integration requirements? | Undisclosed integrations appear as late-sprint blockers | Probably 10-15, we'll document them later |
| Are legacy systems being decommissioned? | Parallel-run commitments extend project duration and team bandwidth | Legacy system stays live indefinitely as fallback |

# 6.  Scoring Guide

After each discovery session, count high-risk answers:

| High-Risk Count | Assessment | Recommended Action |
| --- | --- | --- |
| 0-2 | Low risk — strong candidate for standard 18-week model | Proceed to SOW development with standard scope |
| 3-5 | Moderate risk — addressable in Sprint 0 with targeted interventions | Add Sprint 0 readiness conditions to SOW; plan targeted workshops |
| 6-9 | High risk — engagement requires pre-Sprint 0 remediation work | Recommend pre-engagement readiness workstream; adjust timeline |
| 10+ | Very high risk — not ready for structured delivery | Hold SOW; recommend assessment engagement first |