INTERNAL · SPRINT 0 FACILITATOR PLAYBOOK

Sprint 0 Facilitator Playbook

Complete guide to running Sprint 0: kickoff, customer readiness validation, decision rights setup, and engagement baseline configuration

ECS Federal · ServiceNow Practice

Audience: ECS Lead Consultant, Engagement Manager

Companion to: CLT-S0-01 Customer Readiness Checklist · CLT-S0-02 Customer Kickoff Deck · INT-S0-02 Readiness Validation Checklist

Document ID: INT-S0-01     ·     Version: 1.0     ·     Status: Released

Internal Use Only · Confidential

# Sprint 0 Purpose and Structure

Sprint 0 is the engagement setup sprint. It runs for 2-3 weeks before Sprint 1 begins. By the end of Sprint 0, the customer must have made every foundational commitment required for the build sprints to succeed: named decision makers, data delivered, environments provisioned, and governance structures activated. Sprint 0 that ends without these commitments in place is not Sprint 0 complete — it is Sprint 1 delayed.

Sprint 0 success criterion: every item on the Customer Readiness Checklist (CLT-S0-01) is checked off and signed by the IT Director before Sprint 1 begins. No exceptions. Sprint 0 is not complete until the checklist is signed.

# 1.  Sprint 0 Week-by-Week Plan

| Week | Focus | ECS Deliverables | Customer Deliverables |
| --- | --- | --- | --- |
| Week 1 | Kickoff and baseline setup | Dev/test environment provisioned, Kickoff deck delivered, Foundation Data Pack workbooks distributed | Kickoff meeting attendance (IT Director + all process owners), Named SMEs for each process area, Foundation Data Pack data entry started |
| Week 2 | Customer readiness validation and governance setup | Customization Council charter drafted, Risk register baseline, Decision Rights document v1 | Foundation Data Pack data completed (users, groups, locations, schedules), MID Server server provisioned (if Discovery in scope), AD/SSO credentials provided |
| Week 3 (if needed) | Data quality review and sprint planning | Sprint 1 workshop schedules published, Dev environment validated | Foundation Data Pack data reviewed and corrected, All Sprint 0 checklist items signed off |

# 2.  Kickoff Agenda (Customer)

| Time | Topic | Facilitator | Notes |
| --- | --- | --- | --- |
| 0:00–0:15 | Welcome and introductions | EM | Set the tone: partnership, shared ownership, OOTB-first commitment. Introduce the ECS team. |
| 0:15–0:35 | Engagement overview — The 18-Week Journey | Lead Consultant | Walk through the 18-week plan at a high level using the customer kickoff deck (CLT-S0-02). Focus on: what we build in each sprint, when the customer sees working functionality, and what the sprint demo cadence looks like. |
| 0:35–0:55 | OOTB-First Commitment | Lead Consultant | Frame the governing principle: we configure to OOTB first, demonstrate it working, then consider governed exceptions through the Customization Council. This is not a constraint — it is the model that delivers AI realization. |
| 0:55–1:15 | Decision Rights and Customization Council | EM | Walk through the decision rights model. Introduce the Customization Council: who is on it, when it meets, how it governs exceptions. Customer must name the Council chair before the meeting ends. |
| 1:15–1:30 | Sprint 0 commitments — what we need from you | Lead Consultant | Walk through the Customer Readiness Checklist. Name the items, name the owners, set the deadlines. Every item needs a named owner from the customer side. |
| 1:30–1:45 | Q&A | EM | Open floor. Capture all questions in the Decision Log — answers provided in writing within 24 hours. |
| 1:45–2:00 | Next steps and schedule | EM | Confirm Sprint 0 Week 2 working sessions schedule. Confirm Sprint 1 Workshop 1 date. |

# 3.  Foundation Data Pack Management

The Foundation Data Pack (AP-01) contains 8 workbooks that the customer must complete with their organizational data. This data drives every configuration decision in Sprints 1-6. The ECS consultant is responsible for distributing the workbooks, reviewing the completed data, and flagging data quality issues before Sprint 1 begins.

| Workbook | Data Required | Quality Check | Common Gap |
| --- | --- | --- | --- |
| 01_users.xlsx | All users: first name, last name, email, department, location, manager | Check for duplicate email addresses, missing managers, missing department codes | Contractor and vendor users often excluded — confirm whether they need ServiceNow access |
| 02_locations.xlsx | Location hierarchy: country, state/region, city, building, floor | Check for orphaned child locations (city without a state parent) | Remote worker locations often missing — add 'Remote' as a location under each relevant country |
| 03_departments.xlsx | Department names, department heads, cost center codes | Check that every department has at least one user assigned | Department hierarchy often not maintained — flatten if necessary |
| 04_groups.xlsx | Assignment groups: name, type (assignment/approval), group manager, members | Check that every group has a named manager | Groups from the old system that no longer exist in the org often included — purge before import |
| 05_group_members.xlsx | Group membership: group name, member email | Check that all members exist in the users workbook | Members who left the company often still in groups — purge |
| 06_assignment_rules.xlsx | Category → assignment group mapping | Check that every Incident category has at least one assignment rule | Categories added after the initial taxonomy discussion often not included |
| 07_schedules.xlsx | Working hours schedule: time zone, working days, working hours, holidays | Check that the holiday list is current year | Multiple time zones often omitted — confirm all office locations have schedules |
| 08_slas.xlsx | SLA definitions: priority level, response SLA target, resolution SLA target, schedule | Check that P1 targets are achievable (not set at impossible levels that will always breach) | SLA targets often copied from old system without review — validate against actual performance data |

# 4.  Common Sprint 0 Failure Patterns

## Failure Pattern 1 — Data Delivered Late

Foundation Data Pack workbooks are not completed before Sprint 1 begins. Sprint 1 workshops are discussing theoretical configuration decisions instead of configuring real customer data. The sprint demo shows placeholder data and executive confidence drops. Prevention: set a hard deadline of 5 business days before Sprint 1 Workshop 1. No data = Sprint 1 postponed. This is a commitment, not a preference.

## Failure Pattern 2 — SME No-Shows in Workshops

Sprint workshops are scheduled but process owner SMEs don't attend because Sprint 0 wasn't used to establish the cadence and commitment. Prevention: in Sprint 0 kickoff, get calendar invitations sent and accepted by all SMEs for all sprint workshops through Sprint 6. No invitations accepted = Sprint 0 not complete.

## Failure Pattern 3 — No Named Customization Council Chair

The engagement begins without a named Customization Council chair. Governed exceptions accumulate with no decision authority. By Sprint 3, there are 15 open exceptions and no mechanism to resolve them. Prevention: Customization Council chair is a Sprint 0 kickoff deliverable. If the IT Director cannot name a chair at the kickoff meeting, the EM escalates before Sprint 0 Week 2.

## Failure Pattern 4 — Environment Not Provisioned

The customer's ServiceNow instance is not provisioned at Sprint 0 start. ECS cannot configure anything until the instance is available. Prevention: instance provisioning is a Sprint 0 Week 1 ECS action for new instances. For existing instances, the sandbox/dev instance must be cloned and ready. Include instance provisioning status in the Sprint 0 Week 1 check-in.