INTERNAL · SPRINT 0 SETUP

Engagement Kickoff Facilitation Guide

Internal guide for running the Sprint 0 kickoff meeting

ECS Federal · ServiceNow Practice

Audience: ECS Lead Consultant, Engagement Manager

Companion to: INT-S0-01 Sprint 0 Facilitator Playbook

Document ID: INT-S0-03     ·     Version: 1.0     ·     Status: Released

Internal Use Only · Confidential

# 1.  Pre-Meeting Preparation

| Item | Owner | Status |
| --- | --- | --- |
| Kickoff deck (CLT-S0-02) customized with customer name and engagement specifics | ECS Lead | ☐ |
| Foundation Data Pack workbooks distributed 5 days before kickoff | ECS Lead | ☐ |
| Customization Council charter draft prepared | EM | ☐ |
| Sprint calendar with all workshop dates and demo dates prepared | EM | ☐ |

# 2.  Kickoff Meeting — Confirm Before Closing

| Item | Owner | Status |
| --- | --- | --- |
| IT Director named a Customization Council chair | IT Director | ☐ |
| Foundation Data Pack deadlines agreed (5 business days before Sprint 1 W1) | All | ☐ |
| SME calendar invitations accepted for Sprint 1 workshops | All SMEs | ☐ |
| Decision log initialized — all kickoff questions captured | EM | ☐ |

# 3.  Post-Meeting Actions

| Item | Owner | Status |
| --- | --- | --- |
| Kickoff meeting notes sent to all attendees within 24 hours | EM | ☐ |
| Open questions answered in writing within 24 hours | ECS Lead | ☐ |
| Risk register baseline entries created for any Sprint 0 risks identified | EM | ☐ |