## Risk Register
ECS OOTB Engagement Risk Register
Risk ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Risk Score | Status | Mitigation Action | Owner | Target Date
R-001 | Foundation Data Pack not delivered before Sprint 1 — configuration uses placeholder data | Data | 3 | 4 |  | Open | Enforce hard deadline: Foundation Data Pack due 5 business days before Sprint 1 W1. No data = Sprint 1 postponed. | EM
R-002 | MID Server server provisioned late — Discovery sprint delayed | Infrastructure | 3 | 4 |  | Open | Raise MID Server requirement in Sprint 0 kickoff. Include in Customer Readiness Checklist. | IT Admin
R-003 | Customer SMEs unavailable for sprint workshops — decisions made without authority | Governance | 3 | 4 |  | Open | Calendar invitations accepted by all SMEs before Sprint 1. No SME = workshop rescheduled. | EM
R-004 | Customization requests accumulate without Customization Council governance | Governance | 3 | 5 |  | Open | Council activated in Sprint 0. Bi-weekly cadence. Governed exceptions logged in each sprint. | ECS Lead
R-005 | SSO identity provider configuration delayed — go-live forced with username/password | Integration | 2 | 3 |  | Open | IdP metadata requirement in Sprint 0 readiness checklist. ECS to confirm in Week 2 status. | Identity team
R-006 | KB article count insufficient at Sprint 3 — Virtual Agent deflection below target | Content | 2 | 3 |  | Open | 50-article target set in Sprint 3 Workshop 1. SME drafts assigned by category with deadlines. | Knowledge Mgr