INTERNAL · PER-SPRINT FACILITATOR GUIDE

Sprint 4 — Service Catalog & Request

Facilitator Guide

Workshop agenda, decision pre-fills, OOTB defense language, common pitfalls, and retro template for Sprint 2 Catalog

ECS Federal · ServiceNow Practice

Audience: ECS Lead Consultant, Solution Architect, Engagement Manager

Companion to: Sprint 4 Catalog Workbook · INT-DS-02 Catalog Demo Script · INT-AR-01 Catalog Rationalization Cheatsheet

Document ID: INT-FG-03     ·     Version: 1.0     ·     Status: Released

Internal Use Only · Confidential

# How to Use This Guide

This guide is for the ECS consultant facilitating Sprint 4 Service Catalog & Request Management workshops. Catalog is where customer expectations peak. The workshop must rationalize the catalog to a maintainable OOTB baseline before configuration begins.

The governing principle: catalog items that cannot be owned and updated by a named business owner should not exist in production. Ownership is the filter. Complexity is the enemy.

# 1.  Sprint Overview

| Item | Detail |
| --- | --- |
| Sprint number | Sprint 2 of 6 (Month 2, Weeks 5-6), concurrent with Employee Center (INT-FG-04) |
| Duration | 2 weeks (workshops Week 5; configuration Weeks 5-6; demo Week 6) |
| Sprint goal | Rationalized service catalog with ≤ 40 published items, each with a named owner, clear fulfillment path, and OOTB approval chain |
| Customer participants | Catalog Owner, Service Desk Manager, Department heads (HR, IT, Facilities), Portal Admin |
| Key artifacts produced | Catalog item inventory (rationalized), Category hierarchy, Fulfillment workflow matrix, Approval chain decisions, Service Catalog Accelerator Pack (completed) |
| Sprint dependency | Employee Center (INT-FG-04) portal validation requires catalog items published first |

# 2.  Workshop Agendas

## Workshop 1 — Catalog Item Inventory and Rationalization (90 min)

| Time | Agenda Item | Facilitation Notes |
| --- | --- | --- |
| 0:00–0:15 | Inventory review | Ask the Catalog Owner to share the current catalog item list. Count total items. Items with zero requests in 90 days are candidates for retirement. |
| 0:15–0:40 | The 40-item MVP filter | Apply two filters: (1) Usage — requested in last 90 days? (2) Ownership — named maintainer? Items failing both go to Governed Exceptions log. |
| 0:40–1:05 | Category structure alignment | Present ECS recommended category hierarchy: ≤ 6 top-level categories, ≤ 8 items per category, grouped by employee need (not department). |
| 1:05–1:20 | Decision record + parking lot | Confirm 40-item MVP list. Non-MVP items deferred to Phase 2 — not deleted. |
| 1:20–1:30 | Next steps | ECS configures category structure. Customer provides fulfillment workflow details for top 10 items before Workshop 2. |

## Workshop 2 — Fulfillment Workflows and Approval Chains (90 min)

| Time | Agenda Item | Facilitation Notes |
| --- | --- | --- |
| 0:00–0:10 | Review Workshop 1 decisions | Show dev instance with category structure and item placeholders. |
| 0:10–0:40 | Fulfillment workflow design | Three OOTB patterns: (1) Auto-fulfillment; (2) Single-group; (3) Multi-stage (max 3 stages at MVP). Items needing custom catalog client scripts → Customization Council. |
| 0:40–1:05 | Approval design | Three OOTB approval patterns: (1) None; (2) Group manager; (3) Named approver. Map each item. Demonstrate sequential approval chains before customer requests custom code. |
| 1:05–1:20 | Variable set standards | Rule: ≤ 8 variables per item at MVP. Reused variable sets should be common variable sets (OOTB feature). |
| 1:20–1:30 | Decisions and next steps | ECS configures top 10 items fully before validation session. |

## Workshop 3 — Catalog Validation (60 min)

| Time | Agenda Item | Facilitation Notes |
| --- | --- | --- |
| 0:00–0:10 | Live catalog walkthrough | Open dev EC portal. Navigate catalog as requester. |
| 0:10–0:40 | Item-by-item validation | Submit test request for each of top 10 items. Confirm workflow, approval routing, fulfillment task. Capture discrepancies without fixing on the spot. |
| 0:40–0:55 | Notification review | Confirm request acknowledgment, fulfillment task, and completion notifications all working. |
| 0:55–1:00 | Sprint demo prep | Confirm demo participants, date, and which 5 items to feature. |

# 3.  Decision Pre-Fills — ECS Recommendations

## Decision 1 — Catalog Category Structure

| ECS Recommendation | Rationale | Common Pushback | ECS Response |
| --- | --- | --- | --- |
| 6 top-level categories: IT Services, Software & Access, Hardware, HR Services, Facilities, Employee Onboarding/Offboarding | Reflects most common employee request patterns. Mirrors CSDM service taxonomy. | 'HR wants their own separate section.' | 'HR Services is already a top-level category. Items are owned by HR — the category name is the employee lens, not the department.' |
| ≤ 40 items at MVP. Publish only items with named owners. | Unmaintained catalog items are the primary source of portal abandonment. | 'We have 200 items in our current catalog.' | 'Of those 200, how many were requested in the last 90 days? That number is almost always under 40.' |

## Decision 2 — Fulfillment Workflow Pattern

| ECS Recommendation | Rationale | Common Pushback | ECS Response |
| --- | --- | --- | --- |
| OOTB Flow Designer workflows only. No Workflow Editor (legacy). No inline catalog client scripts. | Flow Designer workflows are upgrade-safe and visible to non-developers. Client scripts are the primary source of catalog technical debt. | 'Our current catalog uses client scripts extensively.' | 'That is why we are rebuilding it. We migrate the logic, not the scripts.' |
| Maximum 3-stage fulfillment for MVP. Items needing more → Phase 2. | 3-stage fulfillment covers 90% of IT and HR scenarios. | 'Some items need 5 approval steps.' | '5 approval steps is a process design problem. Three of those 5 are almost always handled internally by the fulfillment group.' |

# 4.  Common Pitfalls

## Pitfall 1 — The Catalog Migration Trap

The customer wants to migrate all 200 existing items 'as-is' before rationalizing. This makes rationalization politically impossible afterward. Redirect: 'Migration and rationalization are the same project. We migrate only what passes the ownership and usage filters.'

## Pitfall 2 — Variable Set Scope Creep

A department submits a catalog item with a 25-variable intake form. Every variable 'is required.' Redirect: 'How many of these 25 variables could be pre-populated from the user's HR record? How many could the fulfillment team look up themselves? Let us do that exercise before we build the form.'

## Pitfall 3 — Approval Chain Ownership Gap

Named approvers are not set up as users in ServiceNow yet. Redirect: 'Approval routing to named individuals is fragile — what happens when that person is on leave? OOTB group-based approval is more resilient. Use group-based approval for MVP.'

## Pitfall 4 — The Portal Branding Blocker

Comms team gets involved and the sprint stalls on portal branding. Redirect: 'Portal branding is an Employee Center decision in INT-FG-04. Today we are locking catalog item structure.'

# 5.  Sprint Demo Discipline

## Pre-Demo Checklist

| # | Check | Owner | Status |
| --- | --- | --- | --- |
| 1 | Top 10 catalog items published with correct category, variables, and fulfillment workflows | ECS SA | ☐ |
| 2 | Approval chains tested end-to-end for at least 3 items requiring approval | ECS SA | ☐ |
| 3 | Employee Center portal showing catalog with correct category navigation | ECS SA | ☐ |
| 4 | Test requests submitted and fulfilled for top 5 items — confirmation emails working | ECS SA | ☐ |
| 5 | INT-TBV-06 Sprint Demo Discipline Audit prepared | EM | ☐ |

# 6.  Sprint Retro Template

| Category | Question | Capture Here |
| --- | --- | --- |
| What worked | Which catalog items were configured cleanest? |  |
| What worked | How did the customer respond to the 40-item filter? |  |
| What didn't work | Which items required the most back-and-forth? Why? |  |
| Governed exceptions | How many items in Phase 2 backlog? Who owns the review? |  |
| Sprint 3 readiness | Is the customer ready for Sprint 3 (Knowledge + Virtual Agent)? |  |
| ECS learning | What would we do differently? |  |