INTERNAL · PER-SPRINT FACILITATOR GUIDE

Sprint 6 — Integrations

Facilitator Guide

Workshop agenda, decision pre-fills, OOTB defense language, common pitfalls, and retro template for Sprint 6 Integrations

ECS Federal · ServiceNow Practice

Audience: ECS Lead Consultant, Solution Architect, Engagement Manager

Companion to: Sprint 6 Integrations Workbook · Integration Accelerator Pack (AP-03) · CLT-WP-15 Service Graph Pre-Read

Document ID: INT-FG-13     ·     Version: 1.0     ·     Status: Released

Internal Use Only · Confidential

# How to Use This Guide

Integration Sprint is often where the engagement is at highest risk of scope expansion. Every stakeholder has a system they want connected. The workshop must lock scope to the 3-4 integrations that are required for go-live and defer everything else to Phase 2 with clear documentation.

An integration that is not tested end-to-end before go-live will fail in production at the worst possible moment. Every integration configured in Sprint 5 must be fully tested — not just 'it connected' but 'data flows correctly, errors are handled, and there is a monitoring alert if the integration stops working.'

# 1.  Sprint Overview

| Item | Detail |
| --- | --- |
| Sprint number | Sprint 5 of 6 (Month 4-5, Weeks 11-12), concurrent with Service Graph (INT-FG-11) and HAM (INT-FG-12) |
| Sprint goal | Core integrations configured and tested: Active Directory/Entra ID (user sync), SSO (SAML), SCCM or Intune (asset data). All configured integrations passing end-to-end validation. |
| Customer participants | Active Directory Admin, Identity team (SSO/SAML), SCCM/Intune Admin, Security team (API access approval) |
| Key artifacts produced | AD/Entra user sync configured, SSO tested and working, SCCM/Intune data feed validated, Integration health monitoring configured |
| Sprint dependency | Requires MID Server from Sprint 4 Discovery (INT-FG-10) for on-premise integrations. Service Graph Connector licensing must be confirmed before Sprint 5 begins. |

# 2.  Workshop Agendas

## Workshop 1 — Integration Scope Lock and Credential Requirements (90 min)

| Time | Agenda Item | Facilitation Notes |
| --- | --- | --- |
| 0:00–0:15 | Integration inventory | List all integration requests on the table. Do not commit to any in this step — just inventory. Common list: AD/Entra user sync, SSO, SCCM, Intune, email (SMTP), monitoring tools, ITSM-to-ITSM (external ticketing system), procurement, HR system. |
| 0:15–0:40 | Go-live required vs. Phase 2 | Apply the filter: is this integration required for the platform to function at go-live, or is it an enhancement? Go-live required: AD/Entra user sync (authentication), SSO (security mandate), SMTP (notifications). Phase 2: monitoring tool integration, HR system sync, procurement system, external ticketing. Lock the scope. |
| 0:40–1:05 | Credential and API requirements | For each go-live required integration, document the credential requirements. AD/Entra: service account or App Registration. SSO: Identity Provider metadata (IdP metadata URL or XML). SCCM: service account with read access. Confirm who provides each credential and by when. |
| 1:05–1:20 | Integration testing plan | Define the acceptance criteria for each integration: what does 'working' look like? AD sync: new user created in AD appears in ServiceNow within 4 hours. SSO: employee logs in with corporate credentials without being prompted for a ServiceNow-specific password. SCCM: CMDB CI records show SCCM-sourced software inventory. |
| 1:20–1:30 | Next steps | Customer to provide all integration credentials. ECS to configure integrations. Workshop 2 is validation-focused. |

## Workshop 2 — Integration Validation and Error Handling (60 min)

| Time | Agenda Item | Facilitation Notes |
| --- | --- | --- |
| 0:00–0:30 | End-to-end integration tests | Walk through the acceptance test for each integration. For each test, document: Pass/Fail, and if Fail, what is the error and who owns the resolution. |
| 0:30–0:45 | Error handling review | For each integration, review what happens when it fails: does the platform log an error? Does an alert trigger? Is there a fallback? OOTB integration health monitoring must be configured for each integration. |
| 0:45–0:55 | Phase 2 integration backlog | Document the integrations deferred to Phase 2. Include: integration name, data flow, technical requirements, and business justification. This is the input to the Phase 2 scope discussion. |
| 0:55–1:00 | Demo prep | Confirm integration demo scenario: new AD user appearing in ServiceNow, SSO login test, CMDB CI with SCCM data. |

# 3.  Decision Pre-Fills — ECS Recommendations

## Decision 1 — Integration Scope

| ECS Recommendation | Rationale | Common Pushback | ECS Response |
| --- | --- | --- | --- |
| Go-live integrations: AD/Entra user sync, SSO, and one data-source connector (SCCM or Intune). All others Phase 2. | Each additional integration adds testing burden, credential management overhead, and failure mode complexity. Three well-tested integrations are safer than seven partially tested ones. | 'We need the HR system integration at go-live for user provisioning.' | 'HR system integration for user provisioning is a Phase 2 project — it requires HR data model alignment that is outside Sprint 5 scope. At go-live, AD/Entra sync handles user provisioning. HR system integration adds automated lifecycle management (hire, transfer, terminate) which we scope in Phase 2.' |

# 4.  Common Pitfalls

## Pitfall 1 — SSO Configuration Delay

The customer's Identity team is not available during Sprint 5 to provide the IdP metadata. SSO cannot be configured. Prevention: the IdP metadata requirement should be in the Sprint 0 customer readiness checklist. If the Identity team is unavailable in Sprint 5, the platform launches with username/password authentication and SSO is a Week 1 post-go-live configuration — document this as a governed exception.

## Pitfall 2 — Integration Scope Expansion

A stakeholder adds a new integration requirement in Week 11 ('we just realized we need the monitoring tool connected for go-live'). Redirect: 'Any integration added after Sprint 5 Workshop 1 scope lock is a change request. We can scope it as a post-go-live hypercare item or defer to Phase 2. We cannot add untested integrations to the go-live platform.'

# 5.  Sprint Demo Discipline

## Pre-Demo Checklist

| # | Check | Owner | Status |
| --- | --- | --- | --- |
| 1 | AD/Entra user sync configured and validated — new users sync within 4 hours | ECS SA | ☐ |
| 2 | SSO configured and tested — corporate login working without ServiceNow password prompt | ECS SA | ☐ |
| 3 | SCCM or Intune connector validated — CMDB CIs showing software inventory data | ECS SA | ☐ |
| 4 | Integration health monitoring configured — alerts on integration failures | ECS SA | ☐ |
| 5 | Phase 2 integration backlog documented and reviewed with customer | ECS Lead | ☐ |

# 6.  Sprint Retro Template

| Category | Question | Capture Here |
| --- | --- | --- |
| What worked | Which integration was smoothest to configure and test? |  |
| What didn't work | Which credential or IdP issues caused delays? |  |
| Phase 2 scope | Which integrations are in the Phase 2 backlog? |  |
| Sprint 6 readiness | Is the platform stable enough for PA and reporting configuration? |  |
| ECS learning | What would we do differently? |  |