# 1.  UAT Philosophy — OOTB Model

UAT in an OOTB-first engagement is not about proving the software can do everything the legacy system did. It is about validating that the configured OOTB platform meets the business requirements agreed in the workshops. Legacy process parity is not an acceptance criterion. Business outcome delivery is.

Key rule: Any UAT failure that is caused by a feature that was explicitly accepted as OOTB during the workshop phase is NOT a defect — it is a scope confirmation. Document it and manage it separately from true defects.

# 2.  1. UAT Readiness Checklist

Complete before scheduling UAT sessions with the customer:

| Check | Owner | Status |
| --- | --- | --- |
| UAT environment (TEST instance) is a clean copy of DEV with all sprint configuration | ECS Lead |  |
| INT-UAT-01 Test Pack populated with scenarios for all in-scope module features | ECS Lead |  |
| Customer UAT testers identified, named, and confirmed available | ECS EM / Customer PM |  |
| UAT tester accounts created in TEST instance with correct roles | ECS Lead |  |
| Sample test data seeded: CIs, users, groups, catalog items | ECS Lead |  |
| UAT kickoff session scheduled (1 hour — ECS-facilitated) | ECS EM |  |
| Defect reporting process communicated to all testers | ECS EM |  |
| Defect severity definitions shared with customer PM and UAT lead | ECS EM |  |
| Go/no-go criteria confirmed with customer sponsor in writing | ECS EM |  |

# 3.  2. UAT Kickoff Session Agenda

| Time | Agenda Item | Facilitator | Notes |
| --- | --- | --- | --- |
| 0:00-0:10 | Welcome and UAT overview — what we are testing and why | ECS EM | Set the OOTB context — testers are validating business outcomes, not feature parity |
| 0:10-0:20 | Walk through the Test Pack — scenario structure, pass/fail criteria | ECS Lead | Use INT-UAT-01; show testers where to record results |
| 0:20-0:30 | Defect reporting process — how to log a defect, severity definitions | ECS EM | Reference INT-UAT-03 Defect Triage Guide; set expectation that some 'defects' are scope confirmations |
| 0:30-0:40 | Environment access — confirm all testers can log in and navigate | ECS Lead | Work through any access issues live; do not let access problems delay UAT start |
| 0:40-0:55 | Questions and open discussion | ECS EM | Address any concerns about scope or expectations before testing begins |
| 0:55-1:00 | UAT kick-off — testers begin with Scenario IDs 1-5 | ECS Lead | Consultants available for questions during first 30 minutes of testing |

# 4.  3. Daily UAT Standup Protocol

Run a 15-minute standup each morning of the UAT period:

| Question | Owner | Action |
| --- | --- | --- |
| How many scenarios completed vs. planned? | ECS Lead reviews execution log | Flag if >20% behind plan — escalate to EM |
| Any new FAIL results since yesterday? | ECS Lead reviews defect log | Triage new defects using INT-UAT-03; classify severity |
| Any BLOCKED scenarios? | ECS Lead | Unblock environment/data issues same day; do not let BLOCKED count accumulate |
| Any scope questions from testers? | ECS EM | Answer definitively — do not let ambiguity persist into the test day |
| Updated pass rate / go/no-go forecast? | ECS EM | Update customer sponsor daily on UAT health |

# 5.  4. UAT Defect Classification Quick Reference

| Severity | Definition | SLA to Fix | Go/No-Go Impact |
| --- | --- | --- | --- |
| Severity 1 — Critical | Core business process completely broken; no workaround exists | Fix before go-live — no exceptions | Blocks go-live |
| Severity 2 — High | Core feature impaired; workaround exists but is unacceptable for production | Fix before go-live or formal deferral approved by sponsor | Blocks go-live unless formally deferred |
| Severity 3 — Medium | Feature works but with minor inconsistency; acceptable workaround exists | Fix in first 2-week hypercare sprint | Does not block go-live |
| Severity 4 — Low | Cosmetic issue or very minor usability concern; no workflow impact | Schedule in backlog; target next upgrade cycle | Does not block go-live |
| Scope Confirmation | Feature behaves as OOTB — tester expected legacy behavior but OOTB was accepted in workshop | No fix — document and communicate to tester | Does not affect go/no-go |

# 6.  5. Go/No-Go Decision Protocol

ECS EM owns the go/no-go recommendation. Customer Project Sponsor owns the final go/no-go decision.

| Condition | ECS EM Recommendation | Action |
| --- | --- | --- |
| Pass rate 100%, 0 open Sev 1/2 defects | GO | Schedule production deployment; notify customer sponsor |
| Pass rate 95-99%, 0 open Sev 1 defects, all Sev 2 have approved deferral | CONDITIONAL GO | Proceed to production; Sev 2 items enter hypercare backlog immediately |
| Pass rate < 95% OR any open Sev 1 defect | NO-GO | Fix Sev 1 defects; re-run failed scenarios; schedule UAT cycle 2 |
| Pass rate < 90% OR more than 3 open Sev 2 defects | NO-GO — investigate root cause | Review whether sprint configuration is complete; may indicate rework of a sprint deliverable |