## Instructions
INT-TBV-03 · Customization Variance Tracker
ECS Federal · ServiceNow Practice · Internal Use Only
Purpose | System of record for every customization request raised during the engagement. Tracks each request from initial raise through Council decision and build disposition. Feeds the Customization Variance vector in the Engagement Health Dashboard (INT-TBV-02).
Who maintains this | Engagement Manager (primary). Solution Architect updates the OOTB Alternative Analysis column. Practice Lead reviews monthly in the cross-engagement roll-up.
Update cadence | Real-time as requests are raised. Reviewed every Friday during the weekly variance scan. Summarized at bi-weekly Sponsor Sync (INT-TBV-04) and monthly Practice Review (INT-TBV-07).
Key rule | Every customization that is council-approved and built adds to variance. Requests rejected by the Council do NOT add to variance. Customizations discovered post-build (unannounced) add to variance AND trigger the Red band.
Related artifacts | INT-TBV-01 (Manager Playbook) · INT-TBV-02 (Health Dashboard) · INT-TBV-04 (Sponsor Sync) · INT-TBV-05 (Council Pre-Read) · INT-TBV-08 (Course-Correction Playbook)
Deviation Lifecycle Stages
Stage | Description | Who Advances
1 – Raise | Customer or consultant identifies a need that appears non-OOTB. Logged in Variance Log immediately. | Consultant / EM
2 – Analyze | Solution Architect documents OOTB Alternative Analysis. Business outcome alignment assessed. | Solution Architect
3 – Classify | EM classifies: configuration (within OOTB), customization (code/custom table), or PCR. | Engagement Manager
4 – Recommend | SA prepares Council Pre-Read (INT-TBV-05). EM circulates 48 hrs before Council. | SA + EM
5 – Decide | Customization Council issues one of four decisions: approve-sprint, approve-backlog, reject, PCR. | Practice Lead + Sponsor
6 – Disposition | Decision executed: backlog item added, Council rejection documented, PCR drafted, or build planned. | EM / Architect

## Variance Log
Customization Variance Log — One Row Per Request
Add a row each time a customization request is raised. Yellow cells = customer input / Council decision
Req ID | Sprint Raised | Requester | Description of Request | OOTB Alternative (SA Analysis) | Classification (Config/Custom/PCR) | Council Decision | Decision Date | Sprint Built | Est. Effort (hrs) | Actual Effort (hrs) | Post-GoLive Owner
CVT-001 | [8 empty] | 0 | 0
CVT-002 | [8 empty] | 0 | 0
CVT-003 | [8 empty] | 0 | 0
CVT-004 | [8 empty] | 0 | 0
CVT-005 | [8 empty] | 0 | 0
CVT-006 | [8 empty] | 0 | 0
CVT-007 | [8 empty] | 0 | 0
CVT-008 | [8 empty] | 0 | 0
CVT-009 | [8 empty] | 0 | 0
CVT-010 | [8 empty] | 0 | 0
CVT-011 | [8 empty] | 0 | 0
CVT-012 | [8 empty] | 0 | 0
CVT-013 | [8 empty] | 0 | 0
CVT-014 | [8 empty] | 0 | 0
CVT-015 | [8 empty] | 0 | 0
Valid Classification Values
Configuration | Within OOTB — a setting, not a code change. Does NOT add to variance.
Customization | Code change or custom table. Council decision required. ADDS to variance if approved.
PCR | Scope change exceeding SOW. Pause sprint — PCR drafted before any commitment.

## Decision Log
Council Decision Log — Closed Requests
One row per request that has received a final Council decision. Reference for pattern-spotting.
Req ID | Sprint | Decision | Decision Date | Rationale | Deviation Approved? | Effort Added (hrs) | Notes
CVT-001 |  |  |  |  | No
CVT-002 |  |  |  |  | No
CVT-003 |  |  |  |  | No
CVT-004 |  |  |  |  | No
CVT-005 |  |  |  |  | No
CVT-006 |  |  |  |  | No
CVT-007 |  |  |  |  | No
CVT-008 |  |  |  |  | No
CVT-009 |  |  |  |  | No
CVT-010 |  |  |  |  | No
Decision Options Reference
Decision | Meaning | Variance Impact | Next Action
Approve – Sprint | Build in current or next sprint | Adds effort to variance | Add to sprint backlog · update Variance Log
Approve – Backlog | Defer to post-go-live | No current variance impact · tracked separately | Add to product backlog · inform sponsor
Reject | OOTB alternative sufficient | No variance impact | Document rationale · close ticket
PCR Required | Scope exceeds SOW | Pause build · commercial discussion | Draft PCR · Practice Lead + Sales lead discussion

## Sprint Capacity Reference
Sprint Capacity Reference — Variance Band Calculator
Enter team size and daily hours to auto-calculate sprint capacity and band thresholds
Inputs — Update these values for your engagement
Consultants on engagement (FTE) | 3
Billable hours per consultant per day | 6
Working days per sprint (2 weeks) | 10
Calculated Thresholds (auto-updates when inputs change)
Metric | Formula | Value | Notes
Sprint Capacity (hrs) | 180 | 180 | Total available consultant hours per sprint
Green ceiling (5%) | 9 | 9 | Max approved custom effort before Yellow
Yellow ceiling (10%) | 18 | 18 | Max before Orange band
Orange ceiling (15%) | 27 | 27 | Max before Red band
18-week total capacity (9 sprints) | 1620 | 1620 | Full engagement capacity for context
Per-Sprint Variance Tracker — Paste cumulative approved effort from Variance Log
Sprint | Capacity (hrs) | Cumulative Approved Custom Effort (hrs) | Variance % | Band | EM Action
Sprint 1 | 180 | 0 | 0.0% | Green | Continue weekly scan
Sprint 2 | 180 | 0 | 0.0% | Green | Continue weekly scan
Sprint 3 | 180 | 0 | 0.0% | Green | Continue weekly scan
Sprint 4 | 180 | 0 | 0.0% | Green | Continue weekly scan
Sprint 5 | 180 | 0 | 0.0% | Green | Continue weekly scan
Sprint 6 | 180 | 0 | 0.0% | Green | Continue weekly scan