## Project Plan
ECS DELIVERY INTELLIGENCE PLATFORM — BLUEPRINT A (FULL CUSTOM APP) ¦ PROJECT PLAN ¦ START: 01 JUN 2026 ¦ INTERNAL
ID | WBS | Task Name | Outline Level | Duration (Days) | Start Date | End Date | Predecessors | Resource | Planned Hours | Milestone | Phase | Notes
1 | 0 | PRE-BUILD & DECISION | 1 | 10 | 2026-06-01 | 2026-06-12 |  |  |  | Y | Phase 0 | Architecture decision, PDI provision, team assignment
2 | 0.1 | Architecture decision — Blueprint A or B | 2 | 5 | 2026-06-01 | 2026-06-05 |  | Senior Director; Shawn | 16 | N | Phase 0 | Review blueprints; confirm custom app approach
3 | 0.2 | Assign lead developer / app developer | 2 | 1 | 2026-06-08 | 2026-06-08 | 2 | Senior Director | 2 | N | Phase 0 | Dedicated developer resource confirmed
4 | 0.3 | Provision Personal Developer Instance (PDI) | 2 | 3 | 2026-06-09 | 2026-06-11 | 3 | Shawn; Lead Developer | 8 | N | Phase 0 | PDI request through ServiceNow partner portal
5 | 0.4 | ServiceNow ISV/Partner program — initiate | 2 | 5 | 2026-06-09 | 2026-06-15 | 3 | Senior Director; Practice Manager | 8 | N | Phase 0 | Begin ISV enrollment; runs parallel to build
6 | 0.5 | Phase 0 complete — PDI live, team confirmed | 2 | 1 | 2026-06-12 | 2026-06-12 | 4 | Senior Director | 2 | Y | Phase 0 | Milestone: all pre-conditions met
7 | 1 | PHASE 1 — APPLICATION FOUNDATION | 1 | 25 | 2026-06-15 | 2026-07-17 | 6 |  |  | Y | Phase 1 | Weeks 1–5: scoped app, custom tables, roles, update set
8 | 1.1 | Application Scope Setup | 2 | 5 | 2026-06-15 | 2026-06-19 | 6 | Lead Developer | 40 | N | Phase 1 | Create scoped app in Studio; set up GitHub source control
9 | 1.1.1 | Create scoped application in Studio | 3 | 1 | 2026-06-15 | 2026-06-15 | 6 | Lead Developer | 8 | N | Phase 1 | App scope: x_everforth_ecs_dip
10 | 1.1.2 | Define application identity and metadata | 3 | 1 | 2026-06-16 | 2026-06-16 | 9 | Lead Developer | 4 | N | Phase 1 | Version, vendor, description
11 | 1.1.3 | Configure source control (GitHub) | 3 | 2 | 2026-06-17 | 2026-06-18 | 10 | Lead Developer | 8 | N | Phase 1 | Studio GitHub integration
12 | 1.1.4 | Create application roles (5 internal + 4 customer) | 3 | 2 | 2026-06-17 | 2026-06-18 | 10 | Lead Developer; Delivery Manager | 8 | N | Phase 1 | ecs_practice_leader, ecs_delivery_mgr, ecs_architect, ecs_consultant, customer roles
13 | 1.2 | Custom Table Creation | 2 | 12 | 2026-06-19 | 2026-07-06 | 8 | Lead Developer | 120 | N | Phase 1 | All 5 core custom tables with fields and relationships
14 | 1.2.1 | Engagement table [x_ecs_dip_engagement] | 3 | 3 | 2026-06-19 | 2026-06-23 | 8 | Lead Developer | 20 | N | Phase 1 | 12 fields per blueprint data model
15 | 1.2.2 | Sprint Gate table [x_ecs_dip_sprint_gate] | 3 | 3 | 2026-06-24 | 2026-06-26 | 14 | Lead Developer | 20 | N | Phase 1 | 13 fields including calculated velocity fields
16 | 1.2.3 | Risk/Issue table [x_ecs_dip_risk] | 3 | 2 | 2026-06-29 | 2026-06-30 | 15 | Lead Developer | 16 | N | Phase 1 | 10 fields; workflow state
17 | 1.2.4 | Decision Record table [x_ecs_dip_decision] | 3 | 2 | 2026-07-01 | 2026-07-02 | 16 | Lead Developer | 16 | N | Phase 1 | 9 fields; approval workflow
18 | 1.2.5 | Methodology Content table [x_ecs_dip_content] | 3 | 2 | 2026-07-03 | 2026-07-06 | 17 | Lead Developer; Delivery Manager | 16 | N | Phase 1 | 9 fields including multi-value workstream/role/sprint tags
19 | 1.2.6 | Table relationships and cross-references | 3 | 2 | 2026-07-07 | 2026-07-08 | 18 | Lead Developer | 16 | N | Phase 1 | Reference fields, cascade deletes, related lists
20 | 1.3 | ACL Framework | 2 | 5 | 2026-07-01 | 2026-07-07 | 13 | Lead Developer; Delivery Manager | 40 | N | Phase 1 | ACLs for each table and field per role
21 | 1.3.1 | Define ACL matrix (table x role) | 3 | 2 | 2026-07-01 | 2026-07-02 | 13 | Lead Developer; Delivery Manager | 8 | N | Phase 1 | Document before coding
22 | 1.3.2 | Implement and test table-level ACLs | 3 | 3 | 2026-07-03 | 2026-07-07 | 21 | Lead Developer | 24 | N | Phase 1 | Create, read, write, delete per role per table
23 | 1.4 | Basic CRUD UI — Lists and Forms | 2 | 5 | 2026-07-01 | 2026-07-07 | 13 | Lead Developer | 40 | N | Phase 1 | Functional list/form views for all tables
24 | 1.4.1 | List views for all 5 custom tables | 3 | 2 | 2026-07-01 | 2026-07-02 | 13 | Lead Developer | 16 | N | Phase 1 | Column selection, filters, row colour coding
25 | 1.4.2 | Form views — all tables | 3 | 3 | 2026-07-03 | 2026-07-07 | 24 | Lead Developer | 24 | N | Phase 1 | Field layout, related lists, UI policies
26 | 1.5 | Update Set Packaging & Portability Test | 2 | 5 | 2026-07-10 | 2026-07-16 | 19;22;23 | Lead Developer; Shawn | 32 | N | Phase 1 | Package and test install on clean instance
27 | 1.5.1 | Configure update set scope | 3 | 1 | 2026-07-10 | 2026-07-10 | 19 | Lead Developer | 8 | N | Phase 1 | All components in x_everforth_ecs_dip scope
28 | 1.5.2 | Test install on clean PDI | 3 | 3 | 2026-07-13 | 2026-07-15 | 27 | Lead Developer; Shawn | 16 | N | Phase 1 | Verify clean install with no dependencies missing
29 | 1.5.3 | Document installation checklist v1 | 3 | 2 | 2026-07-16 | 2026-07-17 | 28 | Lead Developer | 8 | N | Phase 1 | Sprint 0 deployment guide
30 | 1.6 | Phase 1 Milestone — Foundation Complete | 2 | 1 | 2026-07-17 | 2026-07-17 | 29 | Senior Director; Shawn; Delivery Manager | 4 | Y | Phase 1 | Review: all tables, roles, ACLs, portable update set
31 | 2 | PHASE 2 — PORTAL & HEALTH ENGINE | 1 | 25 | 2026-07-20 | 2026-08-21 | 30 |  |  | Y | Phase 2 | Weeks 6–10: Service Portal, health score, notifications
32 | 2.1 | Service Portal Setup — ECS Theme | 2 | 5 | 2026-07-20 | 2026-07-24 | 30 | Lead Developer | 40 | N | Phase 2 | Everforth-branded portal; base theme applied
33 | 2.1.1 | Create ECS portal (separate from default) | 3 | 2 | 2026-07-20 | 2026-07-21 | 30 | Lead Developer | 16 | N | Phase 2 | Distinct portal URL; Everforth branding colours
34 | 2.1.2 | Base CSS — colours, fonts, logo | 3 | 3 | 2026-07-22 | 2026-07-24 | 33 | Lead Developer | 24 | N | Phase 2 | Navy/blue brand; Arial; responsive layout
35 | 2.2 | Internal Portal Pages | 2 | 10 | 2026-07-27 | 2026-08-07 | 34 | Lead Developer; Delivery Manager | 80 | N | Phase 2 | Consultant, Delivery Manager, Practice Leader pages
36 | 2.2.1 | Consultant landing page | 3 | 3 | 2026-07-27 | 2026-07-29 | 34 | Lead Developer; Delivery Manager | 24 | N | Phase 2 | My tasks, relevant content, open decisions for my workstream
37 | 2.2.2 | Delivery Manager dashboard | 3 | 4 | 2026-07-30 | 2026-08-04 | 36 | Lead Developer; Delivery Manager | 32 | N | Phase 2 | Engagement health card, sprint gate timeline, risk/decision summary
38 | 2.2.3 | Practice Leader roll-up page | 3 | 3 | 2026-08-05 | 2026-08-07 | 37 | Lead Developer | 24 | N | Phase 2 | All engagements aggregate view; portfolio health
39 | 2.3 | Customer Portal Pages | 2 | 12 | 2026-07-27 | 2026-08-11 | 34 | Lead Developer; Delivery Manager | 104 | N | Phase 2 | Sponsor, Project Owner, Process Owner, End User views
40 | 2.3.1 | Executive Sponsor view | 3 | 3 | 2026-07-27 | 2026-07-29 | 34 | Lead Developer; Delivery Manager | 24 | N | Phase 2 | Health summary, milestones, gate approvals, escalated items
41 | 2.3.2 | Project Owner view | 3 | 3 | 2026-07-30 | 2026-08-03 | 40 | Lead Developer; Delivery Manager | 24 | N | Phase 2 | Sprint detail, all decisions, risk log, commitments
42 | 2.3.3 | Process Owner view | 3 | 3 | 2026-08-04 | 2026-08-06 | 41 | Lead Developer | 24 | N | Phase 2 | Workstream-scoped content, decisions, workshop pre-reads
43 | 2.3.4 | End User view | 3 | 3 | 2026-08-07 | 2026-08-11 | 42 | Lead Developer | 24 | N | Phase 2 | Read-only: sprint schedule, knowledge articles by role
44 | 2.3.5 | Customer portal access testing — role validation | 3 | 3 | 2026-08-12 | 2026-08-14 | 43 | Lead Developer; Delivery Manager | 8 | N | Phase 2 | Verify each customer role sees ONLY appropriate data
45 | 2.4 | Health Score Engine | 2 | 8 | 2026-07-27 | 2026-08-05 | 34 | Lead Developer | 64 | N | Phase 2 | Scheduled job calculating 0-100 score from live data
46 | 2.4.1 | Health score script — velocity component | 3 | 2 | 2026-07-27 | 2026-07-28 | 34 | Lead Developer | 16 | N | Phase 2 | 40% weight: rm_story completed ÷ committed
47 | 2.4.2 | Health score script — risk component | 3 | 2 | 2026-07-29 | 2026-07-30 | 46 | Lead Developer | 16 | N | Phase 2 | 30% weight: open high/medium risk deductions
48 | 2.4.3 | Health score script — decision latency | 3 | 2 | 2026-07-31 | 2026-08-03 | 47 | Lead Developer | 16 | N | Phase 2 | 20% weight: overdue/escalated decision deductions
49 | 2.4.4 | Health score — milestone variance component | 3 | 2 | 2026-08-04 | 2026-08-05 | 48 | Lead Developer | 16 | N | Phase 2 | 10% weight: SPM milestone date variance
50 | 2.5 | Notification Framework | 2 | 5 | 2026-08-10 | 2026-08-14 | 44;45 | Lead Developer | 40 | N | Phase 2 | Overdue alerts, escalation triggers, gate sign-off requests
51 | 2.5.1 | Decision overdue notification (5-day rule) | 3 | 2 | 2026-08-10 | 2026-08-11 | 44 | Lead Developer | 16 | N | Phase 2 | Flow Designer: daily check; notify owner + DM
52 | 2.5.2 | Risk escalation trigger | 3 | 2 | 2026-08-12 | 2026-08-13 | 51 | Lead Developer | 12 | N | Phase 2 | High risk open > 7 days → escalate to DM
53 | 2.5.3 | Sprint gate sign-off request workflow | 3 | 2 | 2026-08-14 | 2026-08-17 | 52 | Lead Developer; Delivery Manager | 12 | N | Phase 2 | Flow: DM triggers → approval sent to sponsor
54 | 2.6 | Phase 2 Milestone — Portal & Health Live | 2 | 1 | 2026-08-21 | 2026-08-21 | 38;53 | Senior Director; Delivery Manager | 4 | Y | Phase 2 | Review: all portal pages, health score, notifications working
55 | 3 | PHASE 3 — NATIVE MODULE INTEGRATIONS | 1 | 20 | 2026-08-24 | 2026-09-18 | 54 |  |  | Y | Phase 3 | Weeks 11–14: Agile, SPM, PA widgets, Virtual Agent
56 | 3.1 | Agile Development Integration | 2 | 8 | 2026-08-24 | 2026-09-02 | 54 | Lead Developer | 64 | N | Phase 3 | Live story/sprint data flowing into Sprint Gate records
57 | 3.1.1 | Wire Sprint Gate to Agile backlog reference | 3 | 2 | 2026-08-24 | 2026-08-25 | 54 | Lead Developer | 16 | N | Phase 3 | Engagement → backlog reference; sprint gate → sprint
58 | 3.1.2 | Auto-populate committed stories on sprint start | 3 | 3 | 2026-08-26 | 2026-08-28 | 57 | Lead Developer | 24 | N | Phase 3 | Business rule or Flow: set committed count at sprint creation
59 | 3.1.3 | Live velocity calculation from rm_story | 3 | 3 | 2026-08-31 | 2026-09-02 | 58 | Lead Developer | 24 | N | Phase 3 | Calculated field: GlideRecord count completed stories
60 | 3.2 | SPM / PPM Integration | 2 | 6 | 2026-08-24 | 2026-08-31 | 54 | Lead Developer; Delivery Manager | 48 | N | Phase 3 | Milestone variance feeding health score; sponsor timeline
61 | 3.2.1 | Link Engagement to pm_project record | 3 | 2 | 2026-08-24 | 2026-08-25 | 54 | Lead Developer | 16 | N | Phase 3 | Reference field on Engagement table → pm_project
62 | 3.2.2 | Milestone variance calculation | 3 | 2 | 2026-08-26 | 2026-08-27 | 61 | Lead Developer | 16 | N | Phase 3 | Scheduled job: compare planned vs. actual milestone dates
63 | 3.2.3 | Sponsor portal milestone timeline widget | 3 | 2 | 2026-08-28 | 2026-08-31 | 62 | Lead Developer; Delivery Manager | 16 | N | Phase 3 | Visual milestone list on customer Sponsor portal page
64 | 3.3 | Performance Analytics (PA) Widgets | 2 | 6 | 2026-09-03 | 2026-09-10 | 59 | Lead Developer | 40 | N | Phase 3 | PA data sources, velocity chart, health trend — portal embedded
65 | 3.3.1 | PA data source — Agile story completion | 3 | 2 | 2026-09-03 | 2026-09-04 | 59 | Lead Developer | 16 | N | Phase 3 | PA indicator reading rm_story by sprint
66 | 3.3.2 | Velocity chart widget (sprint-by-sprint) | 3 | 2 | 2026-09-07 | 2026-09-08 | 65 | Lead Developer | 12 | N | Phase 3 | Bar chart: committed vs. completed per sprint
67 | 3.3.3 | Health score trend widget | 3 | 2 | 2026-09-09 | 2026-09-10 | 66 | Lead Developer | 12 | N | Phase 3 | Line chart: health score over engagement duration
68 | 3.4 | Virtual Agent Integration | 2 | 8 | 2026-08-24 | 2026-09-02 | 54 | Lead Developer; Delivery Manager | 56 | N | Phase 3 | 3 VA topics for consultant and customer guidance
69 | 3.4.1 | VA topic: What do I need this sprint? | 3 | 3 | 2026-08-24 | 2026-08-26 | 54 | Lead Developer | 20 | N | Phase 3 | Routes to consultant tasks + relevant content by sprint/role
70 | 3.4.2 | VA topic: Engagement health summary | 3 | 3 | 2026-08-27 | 2026-08-31 | 69 | Lead Developer | 20 | N | Phase 3 | Answers health status questions; shows RAG and key indicators
71 | 3.4.3 | VA topic: Find methodology content | 3 | 2 | 2026-09-01 | 2026-09-02 | 70 | Lead Developer; Delivery Manager | 16 | N | Phase 3 | Routes to KB articles/guides by workstream and sprint
72 | 3.5 | Phase 3 Milestone — All Integrations Live | 2 | 1 | 2026-09-11 | 2026-09-11 | 67;71 | Senior Director; Shawn; Delivery Manager | 4 | Y | Phase 3 | Review: Agile velocity, SPM milestones, PA charts, VA topics
73 | 4 | PHASE 4 — CONTENT, ATF & RELEASE | 1 | 20 | 2026-09-14 | 2026-10-09 | 72 |  |  | Y | Phase 4 | Weeks 15–18: content loading, ATF, Store prep, UAT
74 | 4.1 | Methodology Content Loading | 2 | 8 | 2026-09-14 | 2026-09-23 | 72 | Delivery Manager; Content Owner | 88 | N | Phase 4 | All existing ECS collateral loaded into Content table
75 | 4.1.1 | Tag existing KB articles with ECS metadata | 3 | 3 | 2026-09-14 | 2026-09-16 | 72 | Content Owner | 24 | N | Phase 4 | Apply content_type, role, sprint, workstream, audience tags
76 | 4.1.2 | Import How-To Guides to Content table | 3 | 3 | 2026-09-17 | 2026-09-21 | 75 | Content Owner; Delivery Manager | 24 | N | Phase 4 | All INT-FG, INT-HTG, decision guides, cheatsheets
77 | 4.1.3 | Import Accelerator Pack READMEs and templates | 3 | 2 | 2026-09-22 | 2026-09-23 | 76 | Content Owner | 16 | N | Phase 4 | All 18 accelerator packs linked from Content records
78 | 4.1.4 | Test content surfacing by role/sprint on portal | 3 | 2 | 2026-09-24 | 2026-09-25 | 77 | Delivery Manager; Lead Developer | 24 | N | Phase 4 | Verify right content shows for each role at each sprint
79 | 4.2 | ATF Test Suite | 2 | 8 | 2026-09-14 | 2026-09-23 | 72 | QA Engineer; Lead Developer | 88 | N | Phase 4 | 80%+ coverage required for ServiceNow Store certification
80 | 4.2.1 | ATF tests: CRUD operations all tables | 3 | 3 | 2026-09-14 | 2026-09-16 | 72 | QA Engineer | 24 | N | Phase 4 | Create, read, update, delete per table per role
81 | 4.2.2 | ATF tests: health score calculation | 3 | 2 | 2026-09-17 | 2026-09-18 | 80 | QA Engineer | 16 | N | Phase 4 | Test all four scoring components with edge cases
82 | 4.2.3 | ATF tests: portal access by role | 3 | 2 | 2026-09-21 | 2026-09-22 | 81 | QA Engineer | 16 | N | Phase 4 | Each role sees only their permitted data
83 | 4.2.4 | ATF tests: notification workflows | 3 | 2 | 2026-09-23 | 2026-09-24 | 82 | QA Engineer | 16 | N | Phase 4 | Decision overdue, risk escalation, gate sign-off
84 | 4.2.5 | ATF coverage report — achieve ≥80% | 3 | 2 | 2026-09-25 | 2026-09-28 | 83 | QA Engineer; Lead Developer | 16 | N | Phase 4 | Fix gaps; rerun until 80% threshold met
85 | 4.3 | ServiceNow Store Preparation | 2 | 6 | 2026-09-14 | 2026-09-21 | 72 | Lead Developer; Shawn | 48 | N | Phase 4 | Security scan, remediation, Store listing draft
86 | 4.3.1 | Security review self-assessment | 3 | 2 | 2026-09-14 | 2026-09-15 | 72 | Lead Developer; Shawn | 16 | N | Phase 4 | Check: no hardcoded creds, scoped ACLs, no global writes
87 | 4.3.2 | Run ServiceNow automated scanner | 3 | 2 | 2026-09-16 | 2026-09-17 | 86 | Lead Developer | 8 | N | Phase 4 | Fix all flagged issues before submission
88 | 4.3.3 | Draft Store listing (description, screenshots) | 3 | 2 | 2026-09-18 | 2026-09-21 | 87 | Delivery Manager; Senior Director | 16 | N | Phase 4 | Product description, use case, pricing model placeholder
89 | 4.4 | Documentation Package | 2 | 5 | 2026-09-21 | 2026-09-25 | 79 | Lead Developer; Delivery Manager | 48 | N | Phase 4 | Installation guide, admin guide, update set checklist
90 | 4.4.1 | Installation and deployment guide | 3 | 2 | 2026-09-21 | 2026-09-22 | 79 | Lead Developer | 16 | N | Phase 4 | Step-by-step Sprint 0 deployment instructions
91 | 4.4.2 | Admin configuration guide | 3 | 2 | 2026-09-23 | 2026-09-24 | 90 | Lead Developer; Delivery Manager | 24 | N | Phase 4 | How to configure engagement, assign roles, load content
92 | 4.4.3 | Update set versioning changelog | 3 | 1 | 2026-09-25 | 2026-09-25 | 91 | Lead Developer | 8 | N | Phase 4 | v1.0 release notes
93 | 4.5 | UAT & Pilot on First Engagement | 2 | 6 | 2026-09-28 | 2026-10-05 | 78;84;88 | Delivery Manager; Lead Developer | 32 | N | Phase 4 | Pilot on real engagement; gather feedback
94 | 4.5.1 | Internal UAT — all roles tested | 3 | 3 | 2026-09-28 | 2026-09-30 | 84 | Delivery Manager; Consultants | 24 | N | Phase 4 | Run through each portal view with real users
95 | 4.5.2 | Pilot deployment on first customer instance | 3 | 3 | 2026-10-01 | 2026-10-05 | 94;90 | Lead Developer; Delivery Manager | 8 | N | Phase 4 | Install update set on first real engagement instance
96 | 4.6 | v1.0 Release & Sign-Off | 2 | 1 | 2026-10-08 | 2026-10-08 | 92;95 | Senior Director; Shawn; Delivery Manager | 4 | Y | Phase 4 | Blueprint A v1.0 formally released; Store submission initiated

## Resource Summary
ECS DELIVERY INTELLIGENCE PLATFORM — BLUEPRINT A ¦ RESOURCE & EFFORT SUMMARY
Hours are estimated billable/working hours for each role. Internal overhead — not charged to client engagements.
Role | Engagement Type | Phase 0 (Hrs) | Phase 1 (Hrs) | Phase 2 (Hrs) | Phase 3 (Hrs) | Phase 4 (Hrs) | Total Hours | FTE Weeks (@40 hrs)
Lead Architect / App Developer | Everforth Internal | 8 | 200 | 200 | 160 | 80 | 648 | 16.2
Delivery Manager | Everforth Internal | 8 | 40 | 40 | 32 | 120 | 240 | 6
Content / Methodology Owner | Everforth Internal | 4 | 20 | 20 | 64 | 120 | 228 | 5.7
QA / ATF Engineer | Everforth Internal | 0 | 0 | 80 | 64 | 120 | 264 | 6.6
Practice Leader (reviews only) | Everforth Internal | 4 | 4 | 4 | 4 | 4 | 20 | 0.5
TOTAL — ALL ROLES |  | 24 | 264 | 344 | 324 | 444 | 1400 | 35
NOTES & ASSUMPTIONS
• Hours are estimates based on blueprint architecture complexity. Actual may vary ±20% based on developer experience with ServiceNow Studio and scoped app development.
• Lead Architect / App Developer assumed to be a dedicated resource. If shared across engagements, total calendar duration extends proportionally.
• Phase 4 Content Owner hours assume all existing ECS collateral (handbooks, guides, accelerator packs) is already authored — loading and tagging only.
• QA Engineer can be a senior developer performing peer QA. ATF test authoring requires ServiceNow ATF knowledge.
• Practice Leader hours are reviews and approvals at phase milestones only — 4 hours per milestone review.
• Excludes ServiceNow PDI/instance costs and any ISV partner program fees.
• FTE Weeks = Total Hours ÷ 40. Does not account for calendar sequencing (phases overlap where resources allow).
• Blueprint A total is ~1,370–1,400 hours across all roles. Compare to Blueprint B (~960 hours) in the companion spreadsheet.

## Import Instructions
HOW TO IMPORT THIS PLAN — MS PROJECT & SERVICENOW PPM
MICROSOFT PROJECT
Step 1 | Open Microsoft Project → File → Open → Browse to this Excel file.
Step 2 | In the Import Wizard: select 'Project Excel Template' or 'Custom'. Map columns as follows: Task Name → 'Task Name' ¦ Duration (Days) → 'Duration' ¦ Start Date → 'Start' End Date → 'Finish' ¦ Predecessors → 'Predecessors' ¦ Resource → 'Resource Names' Planned Hours → 'Work' ¦ Milestone → 'Milestone' ¦ Outline Level → 'Outline Level'
Step 3 | Set duration units to 'Days' when prompted. Predecessors are Task ID numbers (column A).
Step 4 | Review imported Gantt chart. Adjust resource calendars and working days as needed for your team.
Step 5 | Save as .mpp. The WBS column (column B) provides the Work Breakdown Structure hierarchy.
SERVICENOW PPM
Step 1 | In ServiceNow, navigate to Strategic Portfolio Management → Projects → Import.
Step 2 | Use the 'Import Project Tasks from Excel' option (available in SPM Standard and above).
Step 3 | Map columns: Task Name → 'Short Description' ¦ Start Date → 'Planned Start Date' End Date → 'Planned End Date' ¦ Duration (Days) → 'Planned Duration' Resource → 'Assigned To' (must be valid usernames in your instance) Planned Hours → 'Planned Hours' ¦ Notes → 'Description' Phase → 'Category' (or create a custom field)
Step 4 | Create the parent project record first (engagement record). Then import tasks referencing that project.
Step 5 | Predecessors (column H) use row ID numbers. ServiceNow PPM task dependencies can be set post-import via the Dependency tab.
Step 6 | Hierarchy: use WBS column to manually set parent-child relationships in SPM task tree after import.
GENERAL NOTES
Dates | All dates assume a project start of Monday 01 June 2026. Adjust by filtering/replacing START date.
Milestones | Rows marked 'Y' in the Milestone column are phase gates — map to SPM milestones or MS Project milestones.
Resources | Resource names are role titles. Replace with actual team member names before importing.
Phases | Phase column is informational — use for grouping/filtering in PPM if needed.