## Project Plan
ECS DELIVERY INTELLIGENCE PLATFORM — BLUEPRINT B (TABLE EXTENDS) ¦ PROJECT PLAN ¦ START: 01 JUN 2026 ¦ INTERNAL
ID | WBS | Task Name | Outline Level | Duration (Days) | Start Date | End Date | Predecessors | Resource | Planned Hours | Milestone | Phase | Notes
1 | 0 | PRE-BUILD & DECISION | 1 | 10 | 2026-06-01 | 2026-06-12 |  |  |  | Y | Phase 0 | Architecture decision, PDI provision, Extension Registry
2 | 0.1 | Architecture decision — Blueprint A or B | 2 | 5 | 2026-06-01 | 2026-06-05 |  | Senior Director; Shawn | 16 | N | Phase 0 | Review blueprints; confirm table extends approach
3 | 0.2 | Assign lead developer / configurator | 2 | 1 | 2026-06-08 | 2026-06-08 | 2 | Senior Director | 2 | N | Phase 0 | Configurator-level SNow experience sufficient
4 | 0.3 | Provision Personal Developer Instance (PDI) | 2 | 3 | 2026-06-09 | 2026-06-11 | 3 | Shawn; Lead Developer | 8 | N | Phase 0 | PDI request — SNow partner portal or existing PDI
5 | 0.4 | Create Extension Registry document | 2 | 2 | 2026-06-09 | 2026-06-10 | 3 | Lead Developer; Shawn | 8 | N | Phase 0 | Master list of all u_ecs_ fields planned — review before coding
6 | 0.5 | Phase 0 complete — team ready, PDI live | 2 | 1 | 2026-06-12 | 2026-06-12 | 4;5 | Senior Director | 2 | Y | Phase 0 | Milestone: Extension Registry approved; PDI ready
7 | 1 | PHASE 1 — TABLE EXTENSIONS & ROLES | 1 | 15 | 2026-06-15 | 2026-07-03 | 6 |  |  | Y | Phase 1 | Weeks 1–3: all u_ecs_ field additions, scoped roles, ACLs
8 | 1.1 | Extension Planning & Field Mapping | 2 | 3 | 2026-06-15 | 2026-06-17 | 6 | Lead Developer; Shawn | 24 | N | Phase 1 | Validate all field names against Extension Registry; confirm table targets
9 | 1.1.1 | Validate pm_project fields vs upgrade risk | 3 | 1 | 2026-06-15 | 2026-06-15 | 6 | Lead Developer | 8 | N | Phase 1 | Stable table — confirm field names do not conflict with SNow reserved names
10 | 1.1.2 | Validate pm_project_task field plan | 3 | 1 | 2026-06-16 | 2026-06-16 | 9 | Lead Developer | 8 | N | Phase 1 | Sprint gate fields — stable table, low upgrade risk
11 | 1.1.3 | Confirm GRC licensing — risk table decision | 3 | 1 | 2026-06-17 | 2026-06-17 | 10 | Delivery Manager | 8 | N | Phase 1 | If GRC licensed: extend sn_risk_risk. If not: extend task
12 | 1.2 | pm_project Extensions — Engagement Fields | 2 | 3 | 2026-06-18 | 2026-06-22 | 8 | Lead Developer | 24 | N | Phase 1 | 9 u_ecs_ fields on pm_project for engagement intelligence
13 | 1.2.1 | Add u_ecs_ fields to pm_project | 3 | 2 | 2026-06-18 | 2026-06-19 | 8 | Lead Developer | 16 | N | Phase 1 | health_score, health_indicator, current_sprint, delivery_mgr, lead_arch, sponsor, agile_backlog, portal_active, engagement_type
14 | 1.2.2 | Configure engagement form view in SPM | 3 | 1 | 2026-06-22 | 2026-06-22 | 13 | Lead Developer | 8 | N | Phase 1 | ECS section on pm_project form — grouped u_ecs_ fields
15 | 1.3 | pm_project_task Extensions — Sprint Gates | 2 | 3 | 2026-06-23 | 2026-06-25 | 12 | Lead Developer | 24 | N | Phase 1 | 10 u_ecs_ fields turning project tasks into sprint gate records
16 | 1.3.1 | Add u_ecs_ sprint gate fields to pm_project_task | 3 | 2 | 2026-06-23 | 2026-06-24 | 12 | Lead Developer | 16 | N | Phase 1 | sprint_number, stories_committed, gate_status, signoff_user, open_risks, open_decisions, velocity_pct
17 | 1.3.2 | Create sprint gate task type filter | 3 | 1 | 2026-06-25 | 2026-06-25 | 16 | Lead Developer | 8 | N | Phase 1 | List view: pm_project_task where u_ecs_task_type = Sprint Gate
18 | 1.4 | Risk & Issue Extensions | 2 | 3 | 2026-06-26 | 2026-06-30 | 11 | Lead Developer | 20 | N | Phase 1 | Extend sn_risk_risk OR task table based on GRC decision
19 | 1.4.1 | Add ECS delivery fields to risk table | 3 | 2 | 2026-06-26 | 2026-06-29 | 11 | Lead Developer | 12 | N | Phase 1 | u_ecs_risk_type, engagement ref, sprint gate ref, workstream, health_impact
20 | 1.4.2 | Configure risk record form for ECS use | 3 | 1 | 2026-06-30 | 2026-06-30 | 19 | Lead Developer | 8 | N | Phase 1 | ECS section on risk form; hide irrelevant GRC fields
21 | 1.5 | kb_knowledge Extensions — Content Tagging | 2 | 2 | 2026-06-26 | 2026-06-29 | 11 | Lead Developer | 16 | N | Phase 1 | 6 u_ecs_ fields enabling role/sprint/workstream content filtering
22 | 1.5.1 | Add u_ecs_ content fields to kb_knowledge | 3 | 1 | 2026-06-26 | 2026-06-26 | 11 | Lead Developer | 8 | N | Phase 1 | content_type, target_role, applicable_sprint, workstream, audience, ecs_content flag
23 | 1.5.2 | Create ECS Knowledge category in KB | 3 | 1 | 2026-06-29 | 2026-06-29 | 22 | Lead Developer; Delivery Manager | 8 | N | Phase 1 | ECS Delivery Methodology category — all tagged articles grouped here
24 | 1.6 | sc_task Extensions — Decision Records | 2 | 2 | 2026-06-30 | 2026-07-01 | 11 | Lead Developer | 16 | N | Phase 1 | 7 u_ecs_ fields turning catalog tasks into decision records
25 | 1.6.1 | Add u_ecs_ decision fields to sc_task | 3 | 1 | 2026-06-30 | 2026-06-30 | 11 | Lead Developer | 8 | N | Phase 1 | decision_type flag, engagement ref, sprint gate ref, workstream, options, outcome, impact_if_deferred
26 | 1.6.2 | Configure decision task form view | 3 | 1 | 2026-07-01 | 2026-07-01 | 25 | Lead Developer | 8 | N | Phase 1 | ECS Decision section; hide standard catalog fields not needed
27 | 1.7 | Scoped Application — Roles & ACLs Only | 2 | 4 | 2026-07-02 | 2026-07-07 | 14;20;23;26 | Lead Developer | 32 | N | Phase 1 | Scoped app contains roles and ACLs only (no custom tables)
28 | 1.7.1 | Create minimal scoped app scope | 3 | 1 | 2026-07-02 | 2026-07-02 | 14 | Lead Developer | 8 | N | Phase 1 | x_everforth_ecs_dip scope — for roles and ACLs only
29 | 1.7.2 | Define and implement ACLs per u_ecs_ field | 3 | 2 | 2026-07-03 | 2026-07-06 | 28 | Lead Developer | 16 | N | Phase 1 | ACL per field per role — critical to prevent data leakage
30 | 1.7.3 | Test role-based field visibility | 3 | 1 | 2026-07-07 | 2026-07-07 | 29 | Lead Developer; Delivery Manager | 8 | N | Phase 1 | Each role sees only their permitted fields and records
31 | 1.8 | Update Set Packaging & Portability Test | 2 | 3 | 2026-07-01 | 2026-07-03 | 17;20;23;26 | Lead Developer; Shawn | 20 | N | Phase 1 | Package all extensions in a deployable update set
32 | 1.8.1 | Capture all extensions in update set | 3 | 1 | 2026-07-01 | 2026-07-01 | 17 | Lead Developer | 8 | N | Phase 1 | Scoped update set containing all u_ecs_ field additions
33 | 1.8.2 | Test install on clean PDI | 3 | 2 | 2026-07-02 | 2026-07-03 | 32 | Lead Developer; Shawn | 12 | N | Phase 1 | Clean PDI install — verify no conflicts with native tables
34 | 1.9 | Phase 1 Milestone — Extensions Live | 2 | 1 | 2026-07-08 | 2026-07-08 | 30;33 | Senior Director; Shawn | 4 | Y | Phase 1 | Review: all extensions on native tables, roles, ACLs, portable update set
35 | 2 | PHASE 2 — PORTAL & HEALTH ENGINE | 1 | 20 | 2026-07-09 | 2026-08-05 | 34 |  |  | Y | Phase 2 | Weeks 4–7: Service Portal, health score engine, notifications
36 | 2.1 | Service Portal Setup — ECS Theme | 2 | 3 | 2026-07-09 | 2026-07-13 | 34 | Lead Developer | 24 | N | Phase 2 | Everforth-branded portal — same visual approach as Blueprint A
37 | 2.1.1 | Create ECS portal (separate from default) | 3 | 1 | 2026-07-09 | 2026-07-09 | 34 | Lead Developer | 8 | N | Phase 2 | Distinct portal URL; navy/blue/teal brand colours
38 | 2.1.2 | Base CSS — colours, fonts, responsive | 3 | 2 | 2026-07-10 | 2026-07-13 | 37 | Lead Developer | 16 | N | Phase 2 | Same branding standards as Blueprint A portal
39 | 2.2 | Internal Portal Pages | 2 | 8 | 2026-07-14 | 2026-07-23 | 38 | Lead Developer; Delivery Manager | 64 | N | Phase 2 | Consultant and Delivery Manager landing pages
40 | 2.2.1 | Consultant landing page | 3 | 3 | 2026-07-14 | 2026-07-16 | 38 | Lead Developer; Delivery Manager | 24 | N | Phase 2 | rm_story widget filtered to user + sprint; KB content by role/sprint
41 | 2.2.2 | Delivery Manager dashboard | 3 | 3 | 2026-07-17 | 2026-07-21 | 40 | Lead Developer; Delivery Manager | 32 | N | Phase 2 | pm_project health card, sprint gate timeline, risk/decision widgets
42 | 2.2.3 | Practice Leader portfolio roll-up | 3 | 2 | 2026-07-22 | 2026-07-23 | 41 | Lead Developer | 16 | N | Phase 2 | Aggregate across all pm_projects flagged u_ecs_portal_active=true
43 | 2.3 | Customer Portal Pages | 2 | 10 | 2026-07-09 | 2026-07-22 | 38 | Lead Developer; Delivery Manager | 80 | N | Phase 2 | Sponsor, Project Owner, Process Owner, End User views
44 | 2.3.1 | Executive Sponsor view | 3 | 3 | 2026-07-09 | 2026-07-13 | 38 | Lead Developer; Delivery Manager | 24 | N | Phase 2 | Health card from pm_project; milestone list; gate approval button
45 | 2.3.2 | Project Owner view | 3 | 3 | 2026-07-14 | 2026-07-16 | 44 | Lead Developer; Delivery Manager | 24 | N | Phase 2 | Sprint gate tasks; decision sc_task list; risk sn_risk_risk list
46 | 2.3.3 | Process Owner view | 3 | 2 | 2026-07-17 | 2026-07-20 | 45 | Lead Developer | 16 | N | Phase 2 | KB articles filtered by u_ecs_workstream + u_ecs_audience=Customer
47 | 2.3.4 | End User view | 3 | 2 | 2026-07-21 | 2026-07-22 | 46 | Lead Developer | 16 | N | Phase 2 | Read-only: sprint schedule, relevant KB articles by role
48 | 2.3.5 | Portal ACL audit — customer access scope | 3 | 2 | 2026-07-23 | 2026-07-24 | 47 | Lead Developer; Delivery Manager | 8 | N | Phase 2 | Critical: verify customers cannot access internal ECS fields or records
49 | 2.4 | Health Score Scheduled Job | 2 | 6 | 2026-07-09 | 2026-07-16 | 38 | Lead Developer | 48 | N | Phase 2 | Same 4-component score as Blueprint A; writes to u_ecs_health_score on pm_project
50 | 2.4.1 | Velocity component — rm_story query | 3 | 2 | 2026-07-09 | 2026-07-10 | 38 | Lead Developer | 12 | N | Phase 2 | GlideRecord: rm_story filtered by u_ecs_agile_backlog on pm_project
51 | 2.4.2 | Risk component — sn_risk_risk query | 3 | 2 | 2026-07-13 | 2026-07-14 | 50 | Lead Developer | 12 | N | Phase 2 | Count open high/medium risks for this pm_project
52 | 2.4.3 | Decision latency component — sc_task query | 3 | 2 | 2026-07-15 | 2026-07-16 | 51 | Lead Developer | 12 | N | Phase 2 | Count overdue/escalated sc_task decisions for this engagement
53 | 2.4.4 | Milestone variance — pm_milestone query | 3 | 2 | 2026-07-17 | 2026-07-20 | 52 | Lead Developer | 12 | N | Phase 2 | SPM milestone date variance for this pm_project
54 | 2.5 | Notification Framework | 2 | 4 | 2026-07-29 | 2026-08-03 | 48;49 | Lead Developer | 32 | N | Phase 2 | Decision overdue, risk escalation, gate sign-off request
55 | 2.5.1 | Decision overdue notification | 3 | 2 | 2026-07-29 | 2026-07-30 | 48 | Lead Developer | 12 | N | Phase 2 | Flow Designer: daily check on sc_task; notify decision owner
56 | 2.5.2 | Risk escalation trigger | 3 | 1 | 2026-07-31 | 2026-07-31 | 55 | Lead Developer | 8 | N | Phase 2 | High risk open > 7 days → notify Delivery Manager
57 | 2.5.3 | Sprint gate sign-off workflow | 3 | 1 | 2026-08-03 | 2026-08-03 | 56 | Lead Developer; Delivery Manager | 8 | N | Phase 2 | Flow: DM requests sign-off → approval to customer sponsor
58 | 2.6 | Phase 2 Milestone — Portal & Health Live | 2 | 1 | 2026-08-05 | 2026-08-05 | 42;57 | Senior Director; Delivery Manager | 4 | Y | Phase 2 | Review: all portal views, health score, customer portal access confirmed
59 | 3 | PHASE 3 — INTEGRATIONS & CONTENT | 1 | 15 | 2026-08-06 | 2026-08-26 | 58 |  |  | Y | Phase 3 | Weeks 8–10: Agile/SPM wiring, KB tagging, Virtual Agent
60 | 3.1 | Agile Development Integration | 2 | 5 | 2026-08-06 | 2026-08-12 | 58 | Lead Developer | 40 | N | Phase 3 | Velocity data flowing from rm_story into sprint gate velocity fields
61 | 3.1.1 | Wire u_ecs_agile_backlog on pm_project to sprint gates | 3 | 2 | 2026-08-06 | 2026-08-07 | 58 | Lead Developer | 16 | N | Phase 3 | Sprint gate query uses pm_project.u_ecs_agile_backlog to find sprint
62 | 3.1.2 | Stories committed auto-population | 3 | 2 | 2026-08-10 | 2026-08-11 | 61 | Lead Developer | 12 | N | Phase 3 | Business Rule: on sprint gate creation, snapshot rm_story count
63 | 3.1.3 | Test velocity calculation end-to-end | 3 | 1 | 2026-08-12 | 2026-08-12 | 62 | Lead Developer; Delivery Manager | 12 | N | Phase 3 | Create test stories, mark complete, verify velocity % updates
64 | 3.2 | SPM Milestone Integration | 2 | 4 | 2026-08-06 | 2026-08-11 | 58 | Lead Developer; Delivery Manager | 32 | N | Phase 3 | Milestone timeline widget + variance feeding health score
65 | 3.2.1 | Milestone timeline widget on Sponsor portal | 3 | 2 | 2026-08-06 | 2026-08-07 | 58 | Lead Developer; Delivery Manager | 16 | N | Phase 3 | pm_milestone list view on portal — native table, no extension needed
66 | 3.2.2 | Verify milestone variance in health score | 3 | 2 | 2026-08-10 | 2026-08-11 | 65 | Lead Developer | 16 | N | Phase 3 | Test: move milestone date past due → health score drops
67 | 3.3 | Knowledge Base Content Tagging | 2 | 6 | 2026-08-06 | 2026-08-13 | 58 | Content Owner; Delivery Manager | 64 | N | Phase 3 | Tag all existing ECS methodology content with u_ecs_ fields
68 | 3.3.1 | Tag How-To Guides in KB | 3 | 2 | 2026-08-06 | 2026-08-07 | 58 | Content Owner | 16 | N | Phase 3 | Apply content_type, role, sprint, workstream tags to all guide articles
69 | 3.3.2 | Tag Workshop Pre-Read articles | 3 | 2 | 2026-08-10 | 2026-08-11 | 68 | Content Owner | 16 | N | Phase 3 | 16 workshop pre-reads — tag by sprint and process owner role
70 | 3.3.3 | Tag Decision Guides and Cheatsheets | 3 | 2 | 2026-08-12 | 2026-08-13 | 69 | Content Owner; Delivery Manager | 16 | N | Phase 3 | All decision guides, adopt vs. reengineer cheatsheets
71 | 3.3.4 | Test content surfacing on portal by role | 3 | 2 | 2026-08-14 | 2026-08-17 | 70 | Delivery Manager; Lead Developer | 16 | N | Phase 3 | Verify each role on portal sees correct, filtered methodology content
72 | 3.4 | Virtual Agent Topics (if VA licensed) | 2 | 5 | 2026-08-06 | 2026-08-12 | 58 | Lead Developer; Delivery Manager | 40 | N | Phase 3 | Optional: 3 VA topics using extended table data sources
73 | 3.4.1 | VA topic: What do I need this sprint? | 3 | 2 | 2026-08-06 | 2026-08-07 | 58 | Lead Developer | 16 | N | Phase 3 | Queries rm_story + kb_knowledge for user's sprint and workstream
74 | 3.4.2 | VA topic: Engagement health summary | 3 | 2 | 2026-08-10 | 2026-08-11 | 73 | Lead Developer | 12 | N | Phase 3 | Reads u_ecs_health_score and u_ecs_health_indicator from pm_project
75 | 3.4.3 | VA topic: Find methodology content | 3 | 1 | 2026-08-12 | 2026-08-12 | 74 | Lead Developer; Delivery Manager | 12 | N | Phase 3 | Routes to kb_knowledge filtered by u_ecs_ tags
76 | 3.5 | Phase 3 Milestone — Integrations Complete | 2 | 1 | 2026-08-18 | 2026-08-18 | 63;66;71;75 | Senior Director; Delivery Manager | 4 | Y | Phase 3 | Review: velocity live, milestones wired, content surfacing, VA working
77 | 4 | PHASE 4 — HARDENING & RELEASE | 1 | 15 | 2026-08-19 | 2026-09-08 | 76 |  |  | Y | Phase 4 | Weeks 11–12: upgrade risk audit, ACL review, docs, UAT
78 | 4.1 | Upgrade Risk Audit | 2 | 4 | 2026-08-19 | 2026-08-24 | 76 | Lead Developer; Shawn | 32 | N | Phase 4 | Review all u_ecs_ extensions for upgrade exposure; finalize registry
79 | 4.1.1 | Complete Extension Registry — all fields | 3 | 2 | 2026-08-19 | 2026-08-20 | 76 | Lead Developer | 16 | N | Phase 4 | Every u_ecs_ field documented: table, type, purpose, upgrade risk rating
80 | 4.1.2 | Define upgrade regression test checklist | 3 | 1 | 2026-08-21 | 2026-08-21 | 79 | Lead Developer; Shawn | 8 | N | Phase 4 | Tests to run after every SNow upgrade before customer is affected
81 | 4.1.3 | Run regression suite on current PDI version | 3 | 1 | 2026-08-24 | 2026-08-24 | 80 | Lead Developer | 8 | N | Phase 4 | Baseline: all portal pages and health score pass on today's version
82 | 4.2 | ACL Comprehensive Audit | 2 | 3 | 2026-08-19 | 2026-08-21 | 76 | Lead Developer; Shawn | 24 | N | Phase 4 | Review all ACLs — confirm no unintended native table access granted
83 | 4.2.1 | Audit ACLs on all extended native tables | 3 | 2 | 2026-08-19 | 2026-08-20 | 76 | Lead Developer | 16 | N | Phase 4 | pm_project, pm_project_task, kb_knowledge, sc_task, sn_risk_risk
84 | 4.2.2 | Customer portal access penetration test | 3 | 1 | 2026-08-21 | 2026-08-21 | 83 | Lead Developer; Shawn | 8 | N | Phase 4 | Log in as each customer role — verify no internal data exposed
85 | 4.3 | Documentation Package | 2 | 4 | 2026-08-19 | 2026-08-24 | 76 | Lead Developer; Delivery Manager | 32 | N | Phase 4 | Extension guide, admin guide, upgrade checklist
86 | 4.3.1 | Extension installation guide | 3 | 2 | 2026-08-19 | 2026-08-20 | 76 | Lead Developer | 16 | N | Phase 4 | Step-by-step: import update set, verify extensions, assign roles
87 | 4.3.2 | Admin configuration guide | 3 | 2 | 2026-08-21 | 2026-08-24 | 86 | Delivery Manager; Lead Developer | 16 | N | Phase 4 | How to create engagement project, configure sprint gates, load KB content
88 | 4.4 | Content Completion & Final Tagging | 2 | 4 | 2026-08-19 | 2026-08-24 | 76 | Content Owner; Delivery Manager | 40 | N | Phase 4 | Complete any remaining KB content tagging; verify all 18 accelerator packs linked
89 | 4.4.1 | Final KB tagging sweep — all ECS content | 3 | 2 | 2026-08-19 | 2026-08-20 | 76 | Content Owner | 24 | N | Phase 4 | Confirm all existing accelerator packs, guides, pre-reads are tagged
90 | 4.4.2 | Verify content completeness on portal | 3 | 2 | 2026-08-21 | 2026-08-24 | 89 | Delivery Manager | 16 | N | Phase 4 | Spot-check each portal role sees complete, relevant methodology content
91 | 4.5 | UAT & Pilot on First Engagement | 2 | 5 | 2026-08-25 | 2026-08-31 | 81;84;87;90 | Delivery Manager; Lead Developer | 32 | N | Phase 4 | Internal UAT then pilot deploy on real customer instance
92 | 4.5.1 | Internal UAT — all portal roles tested | 3 | 3 | 2026-08-25 | 2026-08-27 | 84 | Delivery Manager; Consultants | 24 | N | Phase 4 | Real users test each view; document feedback; fix critical issues
93 | 4.5.2 | Pilot deployment on first customer instance | 3 | 2 | 2026-08-28 | 2026-08-31 | 92;86 | Lead Developer; Delivery Manager | 8 | N | Phase 4 | Deploy update set on real engagement instance; go live
94 | 4.6 | v1.0 Release & Sign-Off | 2 | 1 | 2026-09-01 | 2026-09-01 | 90;93 | Senior Director; Shawn; Delivery Manager | 4 | Y | Phase 4 | Blueprint B v1.0 released; engagement delivery begins

## Resource Summary
ECS DELIVERY INTELLIGENCE PLATFORM — BLUEPRINT B ¦ RESOURCE & EFFORT SUMMARY
Hours are estimated billable/working hours for each role. Internal overhead — not charged to client engagements.
Role | Engagement Type | Phase 0 (Hrs) | Phase 1 (Hrs) | Phase 2 (Hrs) | Phase 3 (Hrs) | Phase 4 (Hrs) | Total Hours | FTE Weeks (@40 hrs)
Lead Developer / Configurator | Everforth Internal | 8 | 120 | 160 | 120 | 60 | 468 | 11.7
Delivery Manager | Everforth Internal | 8 | 24 | 32 | 24 | 90 | 178 | 4.45
Content / Methodology Owner | Everforth Internal | 4 | 0 | 0 | 64 | 88 | 156 | 3.9
QA / Senior Developer (peer QA) | Everforth Internal | 0 | 0 | 40 | 48 | 60 | 148 | 3.7
Practice Leader (reviews only) | Everforth Internal | 4 | 4 | 4 | 4 | 4 | 20 | 0.5
TOTAL — ALL ROLES |  | 24 | 148 | 236 | 260 | 302 | 970 | 24.25
BLUEPRINT A vs BLUEPRINT B — INVESTMENT COMPARISON
Role | Blueprint A Total Hrs | Blueprint B Total Hrs | Hrs Saved (B vs A) | % Reduction
Lead Architect / App Developer vs Lead Developer | 640 | 468 | 172 | 26.88%
Delivery Manager | 232 | 178 | 54 | 23.28%
Content / Methodology Owner | 228 | 156 | 72 | 31.58%
QA / ATF Engineer | 264 | 148 | 116 | 43.94%
Practice Leader | 16 | 16 | 0 | 0%
TOTAL | 1380 | 966 | 414 | 125.7%
NOTES & ASSUMPTIONS
• Blueprint B requires a ServiceNow configurator-level developer rather than a full app developer. Lower cost per hour and easier to resource.
• No ATF test suite required in Blueprint B (no Store certification path). Quality assurance is peer review and manual UAT.
• Content Owner hours (Phase 3) assume the same volume of existing ECS collateral as Blueprint A — KB tagging vs. Content table import.
• QA in Blueprint B is a senior developer performing peer review, not a dedicated QA engineer. ACL audit is the primary quality gate.
• Blueprint B total is approx. 960–980 hours vs. Blueprint A approx. 1,380–1,400 hours — roughly 30% fewer total hours.
• Calendar duration savings are proportionally larger: 10–12 weeks (B) vs. 16–18 weeks (A) — ~40% faster to first deployment.
• FTE Weeks = Total Hours ÷ 40. Does not account for calendar sequencing.

## Import Instructions
HOW TO IMPORT THIS PLAN — MS PROJECT & SERVICENOW PPM
MICROSOFT PROJECT
Step 1 | Open Microsoft Project → File → Open → Browse to this Excel file.
Step 2 | In the Import Wizard: map columns as follows: Task Name → 'Task Name' ¦ Duration (Days) → 'Duration' ¦ Start Date → 'Start' End Date → 'Finish' ¦ Predecessors → 'Predecessors' ¦ Resource → 'Resource Names' Planned Hours → 'Work' ¦ Milestone → 'Milestone' ¦ Outline Level → 'Outline Level'
Step 3 | Set duration units to 'Days'. Predecessors reference the ID column (column A).
Step 4 | Review imported Gantt. Blueprint B is 12 weeks — confirm calendar start matches your engagement date.
Step 5 | Save as .mpp. WBS column (B) provides the Work Breakdown Structure hierarchy.
SERVICENOW PPM
Step 1 | Navigate to Strategic Portfolio Management → Projects → Import.
Step 2 | Map columns: Task Name → 'Short Description' ¦ Start Date → 'Planned Start Date' End Date → 'Planned End Date' ¦ Resource → 'Assigned To' Planned Hours → 'Planned Hours' ¦ Notes → 'Description'
Step 3 | Create the parent engagement project record in SPM first (using pm_project with u_ecs_ extensions from Blueprint B).
Step 4 | Import tasks. Set parent-child hierarchy manually in SPM task tree using WBS column as reference.
Step 5 | Predecessors (column H) are row ID numbers — set task dependencies post-import via the Dependency tab.
GENERAL NOTES
Dates | All dates assume project start Monday 01 June 2026. Adjust to match your actual engagement start.
Milestones | Rows marked 'Y' in Milestone column are phase gates — important sign-off points with the Senior Director.
Resources | Role names in Resource column — replace with actual team member names before importing.
Phases | Phase column maps to Blueprint B's four phases. Use for filtering/grouping in PPM.
vs. Blueprint A | Blueprint B is ~40% shorter duration. Resource Summary sheet has a side-by-side comparison of total hours.