# 1.  Purpose

Use this document to communicate to department managers and SMEs exactly when their participation is required. Complete the [Scheduled Date] and [SME Name] fields based on your actual project calendar. This should be distributed to all participating managers at Sprint 0 kickoff.

Important for managers: Your team members are not passive attendees in these sessions. They are the decision-makers who configure how ServiceNow will work for your organization. If they cannot attend, their decision authority must be delegated in writing to a named substitute before the session.

# 2.  Sprint-by-Sprint SME Schedule

| Sprint | Weeks | Workshop / Session | SMEs Required | Duration | Scheduled Date | SME Name(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 0 | 1-2 | Engagement Kickoff | All Sponsors + PM + IT Lead | 2 hrs |  |  |
| Sprint 0 | 1-2 | Customization Council Charter Review | Project Sponsor + IT Lead | 1 hr |  |  |
| Sprint 1 | 3-4 | Platform Foundation Workshop | IT Lead + System Admin | 3 hrs |  |  |
| Sprint 1 | 3-4 | Incident Management Workshop | ITSM Process Owner + IT Lead | 3 hrs |  |  |
| Sprint 1 | 3-4 | Sprint 1 Demo | Project Sponsor + ITSM Process Owner | 1.5 hrs |  |  |
| Sprint 2 | 5-6 | Service Catalog Workshop | Catalog Owner + Department Reps | 4 hrs |  |  |
| Sprint 2 | 5-6 | Employee Center Workshop | HR Lead (if HR in scope) + IT Lead | 2 hrs |  |  |
| Sprint 2 | 5-6 | Sprint 2 Demo | Project Sponsor + Catalog Owner | 1.5 hrs |  |  |
| Sprint 3 | 7-8 | Knowledge Management Workshop | Knowledge Base Owner + ITSM Lead | 2 hrs |  |  |
| Sprint 3 | 7-8 | Virtual Agent Workshop | IT Lead + Service Desk Manager | 2 hrs |  |  |
| Sprint 3 | 7-8 | Sprint 3 Demo | Project Sponsor + Service Desk Manager | 1.5 hrs |  |  |
| Sprint 4 | 9-12 | Change Management Workshop | Change Manager + IT Director | 3 hrs |  |  |
| Sprint 4 | 9-12 | CSDM / Service Model Workshop | IT Architect + Application Owners | 3 hrs |  |  |
| Sprint 4 | 9-12 | CMDB & Discovery Workshop | IT Architect + Network Lead | 3 hrs |  |  |
| Sprint 4 | 9-12 | Sprint 4 Demo | Project Sponsor + IT Director | 2 hrs |  |  |
| Sprint 5 | 13-15 | HAM/SAM Workshop | Asset Manager + Procurement Lead | 3 hrs |  |  |
| Sprint 5 | 13-15 | Integrations Workshop | IT Architect + Integration Leads | 2 hrs |  |  |
| Sprint 5 | 13-15 | Sprint 5 Demo | Project Sponsor + Asset Manager | 1.5 hrs |  |  |
| Sprint 6 | 16-17 | Performance Analytics Workshop | IT Director + Service Desk Manager | 2 hrs |  |  |
| Sprint 6 | 16-17 | UAT Kickoff | UAT Lead + All Process Owners | 1 hr |  |  |
| Sprint 6 | 16-17 | UAT Execution | UAT Lead + Business Testers | Full sprint availability |  |  |
| Sprint 6 | 16-17 | Go/No-Go Review | Project Sponsor + UAT Lead | 1 hr |  |  |
| Sprint 6 | 17-18 | Production Deployment | IT Lead + System Admin | Deployment window |  |  |
| Hypercare | 18+ | Hypercare Standup (daily, first week) | UAT Lead + Service Desk Manager | 15 min/day |  |  |

# 3.  Total SME Time Commitment by Role

| SME Role | Estimated Total Hours (18 weeks) | Peak Sprint(s) |
| --- | --- | --- |
| Project Sponsor | 20-25 hours (approx. 1.5 hrs/week) | Sprint 6 (UAT and Go/No-Go) |
| IT Lead / Architect | 30-40 hours (approx. 2.5 hrs/week) | Sprint 4 (CMDB, CSDM, Change) |
| ITSM Process Owner (Incident, Change) | 15-20 hours | Sprint 1 and Sprint 4 |
| Catalog / Service Request Owner | 10-15 hours | Sprint 2 |
| Asset Manager | 10-12 hours | Sprint 5 |
| UAT Lead | 20-30 hours | Sprint 6 (full sprint) |
| Service Desk Manager | 8-12 hours | Sprint 1 and Sprint 6 |