# 1.  What Is This Document?

This pack is your team's orientation to the ECS Federal ServiceNow OOTB-first delivery model. Read this before the kickoff meeting. Each section is short and direct. By the end, you will know what to expect, what is expected of you, and how to make the most of the next 18 weeks.

# 2.  The OOTB Commitment — Plain Language

ServiceNow is a mature enterprise platform. It was designed to handle the full spectrum of IT service, asset, and operations management — out of the box. When organizations customize it heavily, they create expensive maintenance burdens and lose the ability to benefit from the upgrades they are paying for.

ECS Federal's job is to configure ServiceNow the right way — not the familiar way. Some of what you see will look different from your current system. That is intentional. If something is different from what you expected, ask why before asking us to change it. There is almost always a good reason.

# 3.  The 18-Week Sprint Model — What to Expect Each Sprint

| Sprint | What Gets Built | What Your Team Does |
| --- | --- | --- |
| Sprint 0 (Weeks 1-2) | Setup: governance, environment, Sprint 1 preparation | Sign the Council Charter; confirm SME availability; complete the Readiness Checklist |
| Sprint 1 (Weeks 3-4) | Platform foundation + Incident Management go-live | Attend Incident Management workshop; make configuration decisions; attend sprint demo |
| Sprint 2 (Weeks 5-6) | Service Catalog + Employee Center go-live | Attend Catalog workshops; provide top 20 catalog item list; attend sprint demo |
| Sprint 3 (Weeks 7-8) | Knowledge Base + Virtual Agent configured | Attend Knowledge and VA workshops; provide article content; attend sprint demo |
| Sprint 4 (Weeks 9-12) | Change Management + CMDB + CSDM + Discovery | Attend all 4 workshops; provide service inventory; attend sprint demo |
| Sprint 5 (Weeks 13-15) | HAM/SAM + Service Graph + Integrations | Attend Asset and Integration workshops; provide asset data; attend sprint demo |
| Sprint 6 (Weeks 16-18) | Performance Analytics + UAT + Go-Live | Lead UAT; make go/no-go decision; participate in production deployment |
| Hypercare (Weeks 18+) | Post-go-live stabilization and knowledge transfer | Use the system; report issues; attend daily standup for first week post-go-live |

# 4.  The Three Most Important Habits for Your Team

| Habit | Why It Matters |
| --- | --- |
| Read the Pre-Read before every workshop | Workshops are decision sessions — your team needs background before they can decide. Without the Pre-Read, workshops run over time and decisions get deferred. |
| Make decisions in the room | Every deferred decision pushes its sprint deliverable back. Decisions made in the workshop take 5 minutes. Decisions deferred to follow-up emails take 5 days. |
| Bring customization requests to the Council — not to ECS consultants informally | Informal requests do not get scheduled, do not get documented, and create misunderstandings about scope. The Council process protects you as much as it protects ECS. |

# 5.  Key Documents in Your Engagement Pack

| Document | What It Is | Who Should Read It |
| --- | --- | --- |
| CLT-EO-02 Roles & Expectations | Who does what on both sides of the engagement | All stakeholders |
| CLT-EO-03 Decision Rights | Who decides what, and what happens when decisions are delayed | Sponsors, PM, IT Lead |
| CLT-EO-05 Engagement FAQ | Answers to the most common questions | All stakeholders |
| CLT-S0-01 Customer Readiness Checklist | What your team needs to have in place before Sprint 1 | Project Manager, IT Lead |
| CLT-S0-04 SME Time-Commitment Calendar | When each SME is needed and for how long | PM, Department Managers |
| Decision Topic Guides (CLT-DT series) | Background on each configuration decision area | Relevant SME before each workshop |
| Workshop Pre-Reads (CLT-WP series) | Deeper background on each module to prepare for workshops | Relevant SME before each workshop |