## Instructions
02 — CI Class Selection
CMDB-CSDM Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines which OOTB CMDB CI classes the customer will activate at MVP, what data quality standards apply to each class, and which classes are explicitly out of scope. Keeping CI class scope narrow at MVP is the single most important CMDB governance decision — it determines whether the CMDB becomes a trusted asset or a noise source.
Who fills this out | Customer-side: IT Operations Manager and the team responsible for the infrastructure environment (server, endpoint, network). ECS SA facilitates the scoping discussion and recommends the MVP class list based on Discovery data availability.
Sprint window | Sprint 1 Week 2 — Sprint 2 Week 1
Estimated effort | 3–4 hours (one scoping workshop + customer review of recommended class list)
Related workbooks | 01 CSDM Service Taxonomy · 05 Service-CI Relationships · 06 CMDB Governance Baseline · Foundation Data Pack
Success criteria
• | MVP CI class list is agreed and documented — typically 5–8 classes for a mid-market engagement.
• | Each in-scope CI class has a named data steward responsible for quality.
• | Out-of-scope CI classes are explicitly listed and the rationale recorded.
• | Minimum mandatory attributes for each in-scope CI class are defined.
• | Discovery source for each CI class (SCCM, Intune, Agent, manual) is confirmed.

## Process Decisions
02 — CI Class Selection — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which CI classes are in scope at MVP? | Recommended MVP class set: cmdb_ci_computer (workstations/laptops), cmdb_ci_server (on-prem servers), cmdb_ci_appl (installed applications), cmdb_ci_service / cmdb_ci_service_technical (CSDM services from Workbook 01), cmdb_ci_network_adapter (populated by Discovery automatically). Add only if Discovery data confirms reliable population. |  | Every CI class you activate is a data quality commitment. A CMDB with 6 clean classes is more valuable than one with 30 partially-populated classes. Start with what Discovery can reliably populate and expand sprint-by-sprint.
2 | Should we include network devices (switches, routers, firewalls) at MVP? | Exclude from MVP unless a Network Discovery licence and SNMP credentials are ready. Network devices can be added in Phase 2 without restructuring the MVP CMDB. |  | Network devices require SNMP community strings, device credentials, and a pattern library. Without these, Discovery creates stub records with no meaningful attributes — which is worse than no record.
3 | Should we track virtual machines separately from physical servers? | Yes. Use cmdb_ci_vm_instance for VMs and cmdb_ci_server for physical. Both classes are OOTB and Discovery populates them correctly when VMware/Hyper-V credentials are available. |  | Mixing VMs and physical servers in a single class breaks capacity reporting and service impact analysis. The OOTB separation is the right model.
4 | Should we include cloud resources (AWS EC2, Azure VMs) at MVP? | Include only if the Cloud Provisioning and Governance plugin is licensed. Use cmdb_ci_vm_instance with the cloud_service_account relationship. If not licensed, defer to Phase 2. |  | Manually maintained cloud CIs become stale within weeks. The OOTB Cloud Management integration is the only reliable source for cloud CI data. Without the licence, do not attempt cloud CIs at MVP.
5 | How do we handle legacy CI records from the previous ITSM tool? | Do not migrate legacy CI records. Run Discovery first; then reconcile what Discovery found against the legacy export. Retire any CI not confirmed by Discovery within 90 days. |  | Legacy CI data is typically 30–60% stale. Migrating it pollutes the CMDB before Discovery has a chance to establish a clean baseline. Discovery-first is the only way to start with trusted data.
6 | What is the minimum set of attributes required on every CI record? | Mandatory for all CI classes: Name, Class, Operational Status, Managed By (assignment group), and the relationship to at least one CSDM service (from Workbook 05). Class-specific mandatories: see Configuration Data tab. |  | CI records with no service relationship are invisible to service impact analysis. Records with no managed-by group are orphaned. These two attributes are the minimum for a CMDB that actually works in incident management.

## Dependencies
02 — CI Class Selection — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CSDM Service Taxonomy (Workbook 01) completed | Required | ECS SA + Customer EA | Sprint 1 Wk 2 | CI classes must be mappable to CSDM services. Without the service taxonomy, relationships cannot be defined.
2 | Discovery scope confirmed — IP ranges, credentials, MID Server location | Required | Customer IT Ops + ECS Architect | Sprint 1 Wk 2 | CI class selection drives Discovery pattern requirements. Unconfirmed scope means some classes cannot be reliably populated.
3 | SCCM/Intune Service Graph Connector credentials and instance access | Required | Customer IT Ops | Sprint 2 Wk 1 | SGC is the primary source for cmdb_ci_computer and installed applications (cmdb_ci_appl).
4 | VMware vCenter credentials (if virtualised environment) | Recommended | Customer Infrastructure Lead | Sprint 2 Wk 1 | Required to populate cmdb_ci_vm_instance and host relationships.
5 | Legacy CMDB or asset register export (for reconciliation reference) | Recommended | Customer IT Ops | Sprint 1 Wk 2 | Used to cross-check Discovery results, not to migrate into ServiceNow.

## Configuration Data
02 — CI Class Selection — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. MVP CI Class List
cmdb_ci_computer | In scope | Workstations, laptops. Primary source: SCCM/Intune SGC.
cmdb_ci_server | In scope | On-prem physical servers. Primary source: Discovery (agent or agentless).
cmdb_ci_vm_instance | In scope if VMware/Hyper-V credentials available | Virtual machines. Primary source: Discovery VMware extension.
cmdb_ci_appl | In scope (limited to managed applications) | Installed software. Populated by SCCM SGC. Scope to managed apps only — not every detected binary.
cmdb_ci_network_adapter | In scope (auto-populated by Discovery) | Network interfaces. Discovery creates these automatically as part of computer/server discovery.
cmdb_ci_network_gear | Out of scope at MVP | Network devices. Defer until SNMP credentials and Network Discovery are confirmed.
cmdb_ci_cloud_* | Out of scope at MVP unless Cloud Provisioning licensed | Cloud resources. Defer unless the licence is confirmed.
cmdb_ci_database | Out of scope at MVP | Database instances. Add in Phase 2 with Application Discovery patterns.
2. Mandatory CI Attributes (all classes)
name | Required — populated by Discovery | Must be unique within class.
sys_class_name | Required — set by Discovery automatically | Must match OOTB class hierarchy.
operational_status | Required — default to 1 (Operational) | Stale/retired CIs must be set to Retired within 90 days of confirmation.
assignment_group | Required — data steward group | Every CI must have a managed-by group. Use assignment groups from Foundation Data Pack.
Service relationship (cmdb_rel_ci) | Required — at least one CSDM service | Link to a Business Service, Technical Service, or Application Service from Workbook 01.
3. Mandatory Attributes — cmdb_ci_computer
serial_number | Required — from SCCM/Intune | Must match physical label or BIOS serial.
os | Required — from Discovery | Operating System name and version.
last_discovered | Required — auto-populated | Must be within 30 days to be considered current.
u_asset_tag or asset_tag | Required — from Foundation Data Pack | Link to HAM asset record if HAM is in scope.
4. Mandatory Attributes — cmdb_ci_server
serial_number | Required | From Discovery or manual entry for physical servers.
os | Required — from Discovery
ip_address / ip_addresses | Required — from Discovery | Primary IP; multiple IPs via related list.
location | Required | Must match a Location record from Foundation Data Pack.

## R&R
02 — CI Class Selection — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Facilitate CI class scoping workshop | R/A | C | ECS SA runs the workshop; customer confirms environment details.
Confirm Discovery scope (IP ranges, credentials) | C | R/A | Customer IT Ops owns network access; ECS advises on Discovery configuration.
Define mandatory attributes per CI class | R/A | C | ECS SA defines the OOTB-aligned mandatory set; customer confirms.
Assign CI data stewards per class | I | R/A | Customer IT Ops assigns stewards by class.
Configure Discovery patterns for in-scope classes | R/A | I | ECS Architect configures Discovery; IT Ops provides credentials.
Configure SCCM/Intune Service Graph Connectors | R/A | C | ECS Architect configures; customer provides connector credentials.
Validate first Discovery run results vs. in-scope class list | R | C | ECS validates class coverage; customer confirms asset counts are plausible.
Document out-of-scope class rationale | R/A | I | ECS SA documents rationale for the project record.

## Consultant Guide
02 — CI Class Selection — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The scoping conversation
The CI class scoping workshop is the highest-leverage CMDB conversation in the engagement. The goal is to get the customer to commit to a narrow, clean scope rather than a broad, aspirational one. Open with: 'Every CI class you include is a data quality commitment. I'd rather have you start with 5 classes that are 95% accurate than 20 classes that are 60% accurate. We can add classes in Phase 2. What can we not go live without?' This reframe usually cuts the initial class list by half.
Discovery credential dependency
The single biggest CMDB sprint risk is credential delays. In Sprint 1 Week 2, confirm: (1) MID Server is deployed and reaching the target subnets, (2) admin credentials for Windows/Linux discovery are in the credential store, (3) SCCM/Intune API credentials for the SGC are available. If any of these are missing at the start of Sprint 2, escalate immediately — this is a project risk, not a configuration problem.
Handling the 'we need everything' response
Customers frequently ask to track everything from printers to coffee machines in the CMDB. The counter-argument is not 'the platform can't do it' — it can. The counter-argument is: 'Every CI class requires a data steward who keeps it accurate. Who is the steward for printers, and how will they know when a printer is retired?' This question usually resolves the scope inflation.
Legacy data migration anti-pattern
Do not agree to migrate legacy CI data even if the customer insists it will 'save time'. Legacy CMDB data is almost always inaccurate and creates false positives in Discovery reconciliation. The correct sequence is: Discovery runs and creates authoritative records; then the customer compares to the legacy export and confirms what Discovery missed. Anything Discovery can't find within 90 days is out of scope.

## Adoption vs Re-engineering
02 — CI Class Selection — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We have 200 CI classes in our legacy CMDB and need them all | Activate only the OOTB MVP class set. Legacy class specialisations belong in CI attributes, not separate classes. | Custom CI classes require upgrade maintenance and break Discovery reconciliation rules. OOTB CI classes cover the meaningful distinctions. Use attributes for sub-types. | 'Your legacy system may have needed separate classes to compensate for limited attribute support. ServiceNow handles sub-types through attributes and CI relationships — you get the same reporting without the maintenance overhead of custom class tables.' | Only if the customer has a unique CI type with no OOTB class equivalent AND a named data steward. Escalate to Practice Lead before agreeing.
We want to migrate our existing 50,000 CI records on day one | Run Discovery first. Use the legacy export for reconciliation reference only. Do not load stale data. | Discovery-first ensures the CMDB starts with verified, current data. Loading 50,000 stale records creates noise that undermines trust in the CMDB from day one. | 'Imagine going live with a CMDB where every record is accurate because Discovery verified it. That's more valuable than a CMDB with 50,000 records where 30% are out of date. We'll run Discovery first, then use your legacy export to catch anything Discovery missed — you get the best of both.' | Never for bulk migration. Manual entry of a small set of strategic CIs (critical servers not reachable by Discovery) is acceptable.
We want to track every software installation, not just managed applications | Scope cmdb_ci_appl to managed applications (those with a maintenance or licence obligation). All detections are available via the Software Asset Management module without polluting the CMDB. | Tracking every detected binary in the CMDB creates millions of CI records that nobody maintains. SAM has its own normalised software library for this purpose. | 'Discovery will find every installed binary — that data lives in the SAM software normalisation layer where it belongs. The CMDB Application CI should represent managed applications your team is responsible for, not every utility that's ever been installed on a laptop.' | Only if the customer has a specific compliance requirement to audit every binary installation. Rare and should be managed in SAM, not CMDB.

## ServiceNow Mapping
02 — CI Class Selection — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Core CI Tables
cmdb_ci_computer | Computer CI | Workstations, laptops — populated via SCCM/Intune SGC.
cmdb_ci_server | Server CI | Physical on-prem servers — populated via Discovery.
cmdb_ci_vm_instance | Virtual Machine Instance | VMs — populated via Discovery with vCenter credentials.
cmdb_ci_appl | Application | Managed software installations — populated via SCCM SGC.
cmdb_ci_network_adapter | Network Adapter | Auto-populated by Discovery as part of computer/server patterns.
2. Key OOTB Identification Rules
IRE — Computer | Serial number + OS + CPU | OOTB identification rule. Do not modify without Discovery Architect review.
IRE — Server | Serial number + name | Fallback to IP if serial unavailable (physical only).
IRE — VM | VM UUID (from hypervisor) | VM UUID is the authoritative identifier. Never use hostname alone.
3. Discovery Sources
Service Graph Connector — SCCM | IntegrationHub > SCCM SGC | Populates computer CIs and installed application CIs.
Service Graph Connector — Intune | IntegrationHub > Intune SGC | Populates modern-managed endpoint CIs. Complements SCCM SGC.
Discovery (agentless) | Discovery > Discovery Schedules | Populates server CIs, VM instances, network adapters.