## Instructions
03 — Business Service Definitions
CMDB-CSDM Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Captures the full definition of each Business Service the customer will register in ServiceNow, including service name, owner, support group, SLA targets, user population, and the upstream Technical Services that support it. This is the customer-completed record set that ECS uses to load Business Service CIs in Sprint 1.
Who fills this out | Customer-side: IT Service Management Owner or Service Portfolio Manager, with sign-off from IT Director or CIO. One row per Business Service. ECS provides the template; customer populates. ECS SA reviews for CSDM compliance before loading.
Sprint window | Sprint 1 Weeks 1–2 (draft), confirmed by end of Sprint 1
Estimated effort | 2–4 hours for a typical 10–20 Business Service portfolio
Related workbooks | 01 CSDM Service Taxonomy · 04 Technical Services & Apps · 05 Service-CI Relationships · Foundation Data Pack — Groups
Success criteria
• | Every Business Service has a name, owner (named individual), support group, and operational status.
• | SLA targets (availability % and response time) are defined or confirmed as TBD for Phase 2.
• | Each Business Service is linked to at least one Technical Service (can be draft).
• | The IT Director or CIO has reviewed and signed off the list.
• | No duplicate Business Service names exist in the list.

## Process Decisions
03 — Business Service Definitions — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How do we handle services that are partially outsourced? | Define the Business Service from the user's perspective (what IT delivers) regardless of who delivers it. The support group can be an external vendor group. Mark the service as 'External Provider' in the service classification. |  | The user experiences a Business Service outage whether IT or a vendor caused it. The service record must exist to track incidents and SLAs end-to-end.
2 | Should Business Services have SLAs defined at this stage or deferred? | Capture SLA targets now even if aspirational — 99.9% availability, 4-hour response for P2. SLAs can be refined in Sprint 3 when the SLA module is configured. Having a placeholder prevents the field from being skipped entirely. |  | SLA fields left blank at Sprint 1 are rarely filled in later. A placeholder forces the service owner conversation about what 'good' looks like before configuration begins.
3 | What if we don't know the user population size? | Estimate in tiers: <100 users, 100-500 users, 500-2000 users, >2000 users. Exact counts are not required at this stage. |  | User population drives incident priority matrix, capacity planning, and service health alerting. Even a rough tier is better than no data.
4 | How should we handle services that are being decommissioned in the next 12 months? | Create the Business Service record with operational_status = 'Retiring'. This ensures incidents during the retirement period are tracked correctly and the service is excluded from new SLA commitments. |  | Omitting retiring services means incidents against them are uncategorised. OOTB operational_status = Retiring handles this cleanly without requiring a custom field.

## Dependencies
03 — Business Service Definitions — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CSDM Service Taxonomy (Workbook 01) approved | Required | Customer IT Director | Sprint 1 Wk 1 | Business Service names must align with the agreed taxonomy.
2 | Foundation Data Pack — Groups (assignment groups) loaded | Required | ECS SA | Sprint 0 | Support groups must exist in ServiceNow before Business Service CIs are created.
3 | Foundation Data Pack — Users (for service owners) loaded | Required | ECS SA | Sprint 0 | Service owners must be active user records in ServiceNow.
4 | SLA targets reviewed by IT Director | Recommended | Customer IT Director | Sprint 1 Wk 2 | Even draft SLA targets require business stakeholder input.

## Configuration Data
03 — Business Service Definitions — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Business Service Template Fields
Service Name | [Customer to complete] | Follow naming convention from Workbook 01.
Service Description | [Customer to complete — 1-2 sentences] | What does this service deliver to the business? Not how.
Service Owner (named individual) | [Customer to complete] | Must be an active user in ServiceNow.
Support Group | [Customer to complete] | Must be an existing assignment group.
Operational Status | 1 — Operational (default) / 5 — Retiring | Set Retiring for services being decommissioned.
SLA — Availability Target (%) | [Customer to complete or TBD] | e.g., 99.9%. Leave TBD if not yet agreed.
SLA — P2 Response Time | [Customer to complete or TBD] | e.g., 4 hours. Used in Sprint 3 SLA configuration.
User Population Tier | [<100 / 100-500 / 500-2000 / >2000] | Rough estimate is acceptable.
Service Classification | Business Service (OOTB) | Do not change. Set by ECS during CI load.
Primary Technical Service(s) supporting this | [Customer to complete — link to Workbook 04 rows] | Can be draft — confirm in Sprint 2.

## R&R
03 — Business Service Definitions — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Provide Business Service template and instructions | R/A | I | ECS SA distributes this workbook.
Complete Business Service definitions (one row per service) | I | R/A | Customer ITSM Owner fills; IT Director approves.
Review definitions for CSDM compliance | R/A | C | ECS SA validates names, classifications, and relationships.
Load Business Service CIs into ServiceNow | R/A | I | ECS SA performs the CI load after customer sign-off.
Validate loaded CIs in ServiceNow | R | A | ECS validates technically; customer confirms data is correct.
Obtain IT Director sign-off on final Business Service list | I | R/A | Customer-side governance step.

## Consultant Guide
03 — Business Service Definitions — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The service definition interview
If the customer is struggling to complete Workbook 03 independently, run a 60-minute service definition interview. Ask for each service: (1) Who calls the helpdesk when this is down? (2) What does 'down' mean for this service? (3) Who do you call at 2am if it's down? (4) How long can the business tolerate it being down? These four questions populate service owner, definition, support group, and SLA target respectively.
Service owner resistance
The most common blocker is naming a service owner. IT directors sometimes resist because they don't want to make managers 'accountable' for service health. Frame it as: 'We need someone who gets the first call from the business when this service is impacted. That's the owner — not someone who fixes it, just someone who orchestrates the response.' This usually resolves the resistance.
Validation before CI load
Before loading Business Service CIs, validate: (1) no duplicate names, (2) all support groups exist in ServiceNow, (3) all service owners are active users, (4) operational_status is explicitly set (not blank). A missing operational_status defaults to null, which breaks the CMDB Health dashboard filter for active services.

## Adoption vs Re-engineering
03 — Business Service Definitions — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Our service definitions from the old ITSM tool are fine — can we just import them? | Review the legacy definitions against CSDM compliance criteria, then load only compliant records as new Business Service CIs. | Legacy service definitions are often formatted as categories or queues, not CSDM Business Services. Importing them without review creates misclassified CIs that break service health and PI. | 'We'll start from your legacy list as a reference — it's much faster than starting from scratch. The review step just ensures each record is structured the way ServiceNow expects so that service health, Virtual Agent, and reporting all work correctly from day one.' | If the legacy system is ServiceNow and the definitions are already CSDM-compliant, a direct import is acceptable after validation.

## ServiceNow Mapping
03 — Business Service Definitions — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Target Table
Business Service CI | cmdb_ci_service | One record per Business Service. Loaded via import set or direct creation.
Service Relationship | cmdb_rel_ci | Links Business Service to Technical Service CIs.
SLA Definition (reference) | contract_sla | SLA records configured in Sprint 3; reference the service name from this workbook.
2. Key Fields
name | Service name from this workbook
service_classification | Business Service | Set by ECS during load.
owned_by | Service owner sys_user record
support_group | Assignment group sys_id
operational_status | 1 = Operational, 5 = Retiring
u_sla_availability_target | Custom field or notes field | If not using formal SLA module in Sprint 1, capture in notes.