## Instructions
02 — Topic Taxonomy
Employee Center Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Employee Center Topic structure — the browsable topic groups on the EC homepage and topic pages. Topics in EC are the user-facing equivalent of Service Catalog categories, but they also surface Knowledge articles and Virtual Agent topics. Aligning the EC topic taxonomy with the Catalog and KB category structures is the key configuration decision for Employee Center.
Who fills this out | ECS SA designs the topic taxonomy based on Catalog and KB categories; customer ITSM Process Owner approves.
Sprint window | Sprint 5 Week 1
Estimated effort | 1–2 hours
Related workbooks | 01 EC Design Decisions · Service Catalog Pack — Category Rationalization · Knowledge Pack — KB Structure
Success criteria
• | EC Topic taxonomy mirrors the Service Catalog category structure.
• | Each Topic has a named icon and short description.
• | Topic pages show the correct catalog items and KB articles.
• | No more than 6 top-level topics for the IT catalog.

## Process Decisions
02 — Topic Taxonomy — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should EC Topics exactly mirror Catalog categories or have a different structure? | EC Topics should mirror the Catalog category names exactly. Deviating creates a disconnect: a user who browses the Catalog sees 'IT Equipment'; the same user on the EC homepage sees 'Hardware' and doesn't recognise the connection. |  | Consistent taxonomy across EC, Catalog, and Knowledge is the OOTB Employee Center design intent. Virtual Agent also uses topic names for intent matching — inconsistency creates intent recognition failures.
2 | What content appears on each EC Topic page? | OOTB Topic page shows: popular catalog items in that topic, featured knowledge articles in that topic's KB category, and a search bar scoped to that topic. Configure using OOTB EC Topic page settings — no custom widgets required. |  | The OOTB Topic page content is driven by catalog item popularity (view count) and knowledge article featured flag. Both are configurable without customisation.

## Dependencies
02 — Topic Taxonomy — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Catalog category structure approved (Sprint 4) | Required | ECS SA | Sprint 4 | Topics must match categories.
2 | KB categories configured (Knowledge Pack) | Required | ECS SA | Sprint 5 Wk 1

## Configuration Data
02 — Topic Taxonomy — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. EC Topic Definitions
Topic 1 — Name | IT Equipment | Matches Catalog category name exactly.
Topic 1 — Icon | [Customer: select from OOTB icon library]
Topic 1 — Short description | [Customer: 1 sentence describing what users find here]
Topic 2 — Name | Software & Licensing
Topic 2 — Icon | [Customer: select from OOTB icon library]
Topic 3 — Name | Access & Security
Topic 3 — Icon | [Customer: select from OOTB icon library]
Topic 4 — Name | Infrastructure Services
Topic 4 — Icon | [Customer: select from OOTB icon library]
Topic 5 — Name | HR & Onboarding
Topic 5 — Icon | [Customer: select from OOTB icon library]
Topic 6 — Name | General Requests
Topic 6 — Icon | [Customer: select from OOTB icon library]
2. Topic Page Content
Popular items source | OOTB: most-viewed catalog items in that category (auto) | No configuration required.
Featured articles | Flag articles as 'Featured' in each KB category | Featured flag on kb_knowledge record.
Topic search scope | OOTB: scoped to topic's catalog category + KB category | No configuration required.

## R&R
02 — Topic Taxonomy — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Design EC topic taxonomy | R/A | C | ECS SA; customer approves.
Select icons and write topic descriptions | C | R/A | Customer ITSM PO selects icons; ECS SA configures.
Configure EC topics in ServiceNow | R/A | I | ECS SA.
Flag featured KB articles per topic | C | R/A | Customer KMs flag articles; ECS SA validates display.

## Consultant Guide
02 — Topic Taxonomy — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Topic icon selection
OOTB EC has a large icon library. Let the customer choose icons — it takes 20 minutes and gives them ownership of the portal. More importantly, icons chosen by the customer tend to make more intuitive sense to their employees than icons chosen by the consultant. Schedule this as a 20-minute screen-share session in Sprint 5 Week 1.

## Adoption vs Re-engineering
02 — Topic Taxonomy — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want different topic names than our catalog categories | Use identical names. Taxonomy consistency across EC, Catalog, and Knowledge is non-negotiable for search and VA. | Inconsistent names fragment user mental models and break Virtual Agent intent matching. | 'If your catalog says IT Equipment and your EC homepage says Hardware, users who navigate from EC to the catalog are in unfamiliar territory. Consistency is the single biggest usability win in portal design — it costs nothing and improves every user interaction.' | Never. If the customer wants different names, change both catalog and EC simultaneously.

## ServiceNow Mapping
02 — Topic Taxonomy — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. EC Topic Tables
EC Topic | sn_hr_sp_topic | Employee Center topic record.
Topic Category Link | sn_hr_sp_topic_category | Links EC topic to catalog category and KB category.
Featured Article | kb_knowledge.featured | Flag to surface articles on EC topic page.