## Instructions
01 — Event Sources
Event Management Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines every monitoring tool that will send events into ServiceNow Event Management at MVP. The event source list is the foundation of the entire Event Management program — every downstream rule, alert, and incident traces back to a source.
Who fills this out | Customer-side: IT Operations lead working with the monitoring/tooling team. ECS facilitates the source prioritisation workshop in Sprint 0.
Sprint window | Sprint 0, Week 1–2
Estimated effort | 4–6 hours including source inventory and connector validation
Related workbooks | 02 Event Rules Baseline · 05 MID Server Configuration · Foundation Data Pack — CIs
Success criteria
• | Every active monitoring tool sending event data is listed with a named owner and the data volume estimate.
• | Source priority (P1 = feeds alerts that could become P1 incidents, P2 = operational, P3 = informational) is assigned to all sources.
• | MID Server connector type is confirmed for each source (REST, JDBC, Email, custom connector).
• | Sources with duplicate coverage (e.g., two tools monitoring the same CI) are flagged for consolidation discussion.
• | Out-of-scope sources (decommission planned within 12 months) are excluded with a note.

## Process Decisions
01 — Event Sources — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which monitoring tools are in scope at MVP? | Start with the tools that generate P1/P2 alert noise today — typically 2–4 tools covering infrastructure, network, and application tiers. Add others in Phase 2. |  | Customers who onboard every monitoring tool at once overwhelm the event rules build and produce an alert flood that operators ignore. Focus on the tools that matter most for SLA compliance first.
2 | How will each source authenticate to ServiceNow? | Use REST API (sys_import_set or em_event table endpoint) with a dedicated service account per source. OAuth where the tool supports it. |  | Shared credentials across sources make audit trails useless and create a single point of credential failure. One service account per source is the OOTB best practice and a security baseline requirement.
3 | Will sources send raw events or pre-correlated alerts? | Send raw events. ServiceNow Event Management's correlation engine produces the alert layer — pre-correlating in the monitoring tool duplicates logic and prevents ServiceNow from applying its own correlation rules. |  | Pre-correlated input bypasses the em_event table entirely and arrives as an alert, which means the source's correlation logic overrides ServiceNow's. This breaks the unified operator view and makes the CMDB correlation step meaningless.
4 | What event volume (events/minute) is expected per source at peak? | Document peak volume per source. Any source exceeding 1,000 events/minute requires dedicated MID Server capacity planning. |  | Under-provisioned MID Servers are the most common cause of event lag, which delays alert creation, which delays incident creation, which triggers SLA breaches. Volume numbers must be captured now.
5 | How are out-of-hours events handled — same rules or suppressed? | Use OOTB Event Management maintenance windows (em_maintenance_schedule) to suppress known maintenance events. All other events follow standard rules regardless of time of day. |  | Time-based suppression at the source level is a trap — it hides real incidents during maintenance windows. Suppress selectively by CI + window, not globally by time.
6 | What is the retention policy for raw events in the em_event table? | OOTB default is 7 days for raw events and 30 days for alerts. Accept the defaults at MVP; revisit after observing actual volume. |  | Custom retention is frequently requested but rarely necessary at MVP. The em_event table growth is manageable at default settings for most customers.
7 | Will the monitoring tools be integrated via MID Server or direct REST? | MID Server for on-premises monitoring tools; direct REST for cloud-native tools that can reach the ServiceNow instance. Hybrid is common and OOTB-supported. |  | Forcing all sources through MID Server when direct REST is available adds unnecessary latency and a single MID Server becomes a bottleneck. Use the right connector for the source topology.
8 | Are there SIEM or log aggregation tools (e.g., Splunk) that should also feed events? | Include SIEM/log aggregation tools that generate actionable operational alerts. Exclude log streams that are informational only — these inflate event volume without actionable signal. |  | Splunk and similar tools can send thousands of informational events per minute. Without pre-filtering at the source, the em_event table fills with noise and operator confidence collapses.

## Dependencies
01 — Event Sources — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | MID Server installed and registered to ServiceNow instance | Pending | ECS | Sprint 0, Wk 1 | Required before any monitoring tool can send events via MID Server connector
2 | Event Management plugin (com.glideapp.itom.snac) activated | Pending | ECS | Sprint 0, Wk 1 | Foundation for all Event Management tables and rules
3 | Monitoring tool admin credentials provided for connector configuration | Pending | Customer | Sprint 0, Wk 2 | One set of read-only credentials per tool; ECS will configure the connector
4 | Network firewall rules opened: monitoring tool → MID Server → ServiceNow | Pending | Customer | Sprint 0, Wk 1 | ECS to provide port requirements; Customer networking team to execute
5 | CMDB CI baseline loaded (Foundation Data Pack) | Pending | ECS + Customer | Sprint 0, Wk 1 | CI correlation requires CIs to exist in the CMDB; cannot correlate events to phantom CIs
6 | Peak event volume estimate provided per monitoring tool | Pending | Customer | Sprint 0, Wk 2 | Required for MID Server sizing; ask the monitoring team's ops lead

## Configuration Data
01 — Event Sources — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Event Source Registry
Total event sources at MVP | TBD | Customer to confirm after source inventory workshop
Source naming convention | TOOL_TIER (e.g., DYNATRACE_APP, SOLARWINDS_NET) | Consistent naming required — used as source field in em_event and in alert grouping
Primary event table | em_event | OOTB; do not redirect to custom table
Source classification field | source (string) | Populated by the monitoring tool connector; drives rule filtering
2. Connector Types
Dynatrace | REST API (OOTB Dynatrace connector) | Supported natively in Event Management; configure in MID Server Extensions
SolarWinds | REST API via MID Server | Use the OOTB SolarWinds connector from the ServiceNow Store
Nagios / Icinga | JDBC or REST via MID Server | Legacy Nagios uses JDBC polling; Icinga 2 supports REST push
Splunk | REST push (Splunk Add-on for ServiceNow) | Customer installs the Splunk add-on; ECS configures the ServiceNow-side receiver
Prometheus / Alertmanager | REST push via Alertmanager webhook | Alertmanager sends JSON to em_event REST endpoint; no MID Server required if cloud-to-cloud
Custom / proprietary tool | JDBC polling or REST via MID Server | ECS builds a custom connector using the Event Management scripted connector framework
3. Service Account Configuration
Service account naming convention | svc_em_[tool] (e.g., svc_em_dynatrace) | One dedicated account per source for audit traceability
Required ServiceNow role | evt_mgmt_integration | OOTB role; do not grant admin or itil to event integration accounts
Password rotation policy | 90-day rotation; ECS notified 2 weeks before rotation | Customer to confirm rotation schedule aligns with connector reconfiguration window
4. Volume and Capacity Baseline
Expected peak events/minute — all sources combined | TBD | Customer to provide; drives MID Server sizing and event retention planning
MID Server CPU/memory recommendation (< 5k events/min) | 4 vCPU / 8 GB RAM | OOTB recommendation for standard deployments
MID Server CPU/memory recommendation (5k–20k events/min) | 8 vCPU / 16 GB RAM | Scale MID Server before going live; cannot resize mid-sprint without downtime
High-availability MID Server (> 20k events/min or SLA-critical) | Clustered MID Servers (2+ nodes) | Requires MID Server cluster configuration; plan for this in Sprint 0 if volume warrants

## R&R
01 — Event Sources — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Event source inventory (which tools are in scope) | C | R | Customer IT Ops lead owns the list; ECS validates for connector feasibility
Source priority classification (P1/P2/P3) | R | C | ECS facilitates; customer confirms based on SLA exposure per tier
Monitoring tool credential provisioning | I | R | Customer security team provisions; ECS receives and configures
Network firewall rule changes (tool → MID Server → SN) | I | R | Customer networking team owns; ECS provides port specs
MID Server connector configuration | R | I | ECS configures each connector; customer validates data flow in the event log
Service account creation in ServiceNow | R | I | ECS creates; customer IT security to approve/audit
Volume estimation and MID Server sizing sign-off | R | C | ECS sizes based on customer data; customer confirms acceptable risk
Out-of-scope source documentation (decommission list) | C | R | Customer owns decommission timeline; ECS documents exclusion rationale

## Consultant Guide
01 — Event Sources — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Event Management Architecture Overview
ServiceNow Event Management sits between monitoring tools and ITSM. The flow is: monitoring tool → em_event (raw event) → event rules (dedup/filter/classify) → em_alert (correlated alert) → alert promotion → incident. Every decision in this workbook affects every stage of that flow. Do not skip the source inventory — trying to build event rules without knowing the sources is like building assignment rules without knowing the groups.
MID Server Sizing — The Number Customers Get Wrong
Ask for peak events/minute from the monitoring team, not average. Events are not evenly distributed — a network storm, a failed patch, or a cloud region failure can generate 10× the normal volume in under 60 seconds. MID Server queue depth is finite; if it fills, events are dropped silently. There is no dead-letter queue in the OOTB architecture. Size for peak + 20% headroom.
Common Source Inventory Mistakes
Three patterns that create downstream problems: (1) listing monitoring tools that are decommissioning within 6 months as in-scope — wastes connector build time and creates rule tech debt; (2) including informational log streams alongside operational monitoring — floods the em_event table and destroys operator confidence; (3) missing the SIEM because 'Splunk is log management, not monitoring' — if Splunk generates actionable alerts, it belongs in scope.
Sprint 0 Sequencing Note
Get the source list locked by end of Sprint 0 Week 1. The event rules workbook (02) cannot be built without a confirmed source list because rules are keyed to the source field. One week of source inventory slippage equals one week of rule-building slippage equals one week of alert configuration slippage. This is the critical path item in Event Management Foundations.
Connector Validation Checkpoint
Before Sprint 1: validate each connector by sending a test event and confirming it appears in the em_event table. Use the Event Management > Events list view. If a test event does not appear within 60 seconds, the connector is misconfigured — do not proceed to event rules until all sources are validated. A misconfigured source discovered during alert testing costs 3× as long to diagnose.

## Adoption vs Re-engineering
01 — Event Sources — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We already have alert management in our monitoring tool — why do we need ServiceNow to do it again?' | ServiceNow correlates alerts from all tools into a single operator view, links them to CMDB CIs, and drives automated incident creation — none of which the individual monitoring tool can do across the full stack. | Unified operator experience, CMDB-backed correlation, and SLA-linked incident automation are impossible from a single monitoring tool silo. | 'Your monitoring tool is excellent at detecting issues in its domain. ServiceNow is where all those domains meet — it's the single pane of glass your operators use to see the full picture and drive incidents.' | Never for the core flow. Custom dashboards in the monitoring tool for tier-specific views are fine alongside ServiceNow, not instead of it.
'We want to keep incidents in our legacy ITSM tool and just use ServiceNow for events.' | Event Management's alert promotion creates incidents natively in ServiceNow. Sending promoted alerts to an external ITSM requires custom integration and breaks the OOTB SLA, assignment, and notification chain. | OOTB alert promotion to ServiceNow Incident is a first-class feature. External integration is a custom build that introduces latency and breaks the closed-loop workflow. | 'The alert-to-incident promotion is where the ROI lives — automated creation, CMDB-backed assignment, SLA clock starts on promotion. Routing to an external tool means building all of that again outside the platform.' | Only if contractually required and the external ITSM has a ServiceNow-certified integration. Even then, plan for significant limitations.
'Can we customize the em_event table to add fields specific to our monitoring tools?' | Use the OOTB additional_info (JSON) field on em_event for tool-specific metadata. Do not add columns to em_event — it is a high-volume staging table and schema changes affect indexing and performance. | em_event is a transient staging table, not a record of system. Custom columns on a high-volume transient table create index bloat and performance risk. | 'The additional_info field is purpose-built for exactly this — tool-specific metadata that the correlation rules and alert tabs can surface without touching the core schema.' | Never add columns to em_event. If metadata must persist beyond the event, promote it to the alert or incident record via a transform rule.
'We want event rules to auto-close incidents when the monitoring tool sends a recovery event.' | Use OOTB Alert Closure Rules (em_alert_state_rule) to close alerts on recovery, which then triggers incident resolution via the alert-incident binding. This is fully OOTB. | Auto-resolution is a high-ROI OOTB feature that reduces MTTR and operator burden. It is explicitly in scope for Foundations. | 'Good news — this is exactly what OOTB alert closure rules are designed for. We configure the recovery event pattern and the resolution state together in workbook 03.' | No customisation needed. This is a configuration exercise, not a development exercise.

## ServiceNow Mapping
01 — Event Sources — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Core Tables
Raw event table | em_event | High-volume transient table; 7-day default retention
Alert table | em_alert | Correlated alerts; 30-day default retention; drives the operator workspace
Event source table | em_source | Registry of configured event sources
Maintenance schedule table | em_maintenance_schedule | Suppression windows tied to CIs and sources
Alert state rule table | em_alert_state_rule | Drives alert lifecycle (open → flapping → closed → resolved)
2. Key Fields — em_event
source | String — monitoring tool identifier | Must match the registered em_source name; drives all event rules
node | String — hostname or IP of affected CI | Used for CMDB CI lookup/correlation; must match ci_identifier strategy
type | String — event category from the tool | e.g., 'CPU', 'Disk', 'Network'; used in event rule matching
severity | Integer 1–5 (1=Critical) | OOTB severity scale; monitoring tool severity must be mapped to this scale
description | String | Alert and incident short description is derived from this field
additional_info | JSON string | Tool-specific metadata; surfaced in alert tabs via transform; no schema change needed
message_key | String | Deduplication key; events with the same message_key update the existing alert rather than creating a new one
3. OOTB Features Used
Event Management Workspace | Operator-facing unified alert view | OOTB; no configuration required beyond alert rules
Event Correlation Rules | Groups related alerts into a parent alert | OOTB scripted rules engine; configured in workbook 02
Alert Promotion to Incident | Auto-creates incident from alert on threshold breach | Configured in workbook 03; OOTB promotion template
MID Server Event Connectors | Tool-specific data adapters (Dynatrace, SolarWinds, etc.) | Installed from ServiceNow Store or MID Server Extensions
CI Correlation (CMDB lookup) | Links em_event.node to cmdb_ci.name/ip_address | Configured via CI Identifier Rules; requires clean CMDB