## Instructions
03 — Alert Promotion Rules
Event Management Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines when and how alerts automatically promote to incidents. Alert promotion is the ROI moment of Event Management — it replaces manual operator triage with a rules-driven, CMDB-backed incident creation workflow.
Who fills this out | ECS Solution Architect with the Service Desk Manager and IT Operations lead. Promotion thresholds must be jointly agreed — over-promoting creates noise, under-promoting defeats the purpose.
Sprint window | Sprint 1, Week 1–2
Estimated effort | 6–8 hours including threshold design, ITSM field mapping, and test promotion runs
Related workbooks | 02 Event Rules Baseline · 04 CI Correlation Mapping
Success criteria
• | Promotion criteria (severity level + duration + CI tier) are agreed and documented for all alert types.
• | Incident field mapping from alert to incident is confirmed (category, subcategory, assignment group, priority).
• | Auto-resolution rules (recovery event closes alert and resolves incident) are configured and tested.
• | Incident deduplication (do not create a second incident if one is already open for the same CI + alert) is configured.
• | Non-promotion scenarios (informational alerts, non-production CIs) are explicitly documented.
• | Promotion rules are tested end-to-end with synthetic events before go-live.

## Process Decisions
03 — Alert Promotion Rules — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What severity level triggers automatic incident promotion? | Severity 1 (Critical) and Severity 2 (Major) alerts auto-promote. Severity 3 (Minor) promotes only if the alert is open for more than 15 minutes without operator acknowledgement. Severity 4–5 never auto-promote. |  | Promoting only Severity 1–2 at MVP keeps the incident queue clean. Adding the 15-minute rule for Severity 3 catches unattended medium alerts without flooding the queue with every minor event.
2 | Should non-production CI alerts ever auto-promote to incidents? | No. Non-production alerts route to a dedicated 'Event Triage' assignment group for manual review. They do not auto-create incidents. |  | Auto-promoting non-production alerts is the fastest path to operator fatigue. Non-production systems can generate high event volumes during deployments, testing, and patch cycles.
3 | What incident fields are populated by the promotion rule? | OOTB promotion populates: short_description (from alert.name), description (from alert.description + event details), category/subcategory (from CI class), assignment_group (from CI support group via CMDB), priority (from alert severity), cmdb_ci (from alert.cmdb_ci). |  | Mapping assignment_group from the CMDB support group is the highest-value promotion field — it routes the incident to the right team automatically without dispatcher intervention.
4 | What happens when the monitoring tool sends a recovery event? | Recovery event closes the alert. If the incident is still open (not yet resolved by the team), an auto-resolution work note is added and the incident is moved to 'Resolved' with resolution code 'Auto-Resolved by Event Management'. |  | Auto-resolution is the OOTB feature that closes the loop and reduces MTTR. Do not disable it — it is the most visible ROI metric for Event Management.
5 | How should duplicate incidents be handled (same CI alerts multiple times before resolution)? | Use OOTB alert-incident binding: if an open incident already exists for the alert's CI, the new alert is linked to the existing incident as a related alert, not promoted to a new incident. |  | Without duplicate detection, a network storm can create hundreds of incidents for the same CI in minutes. The OOTB binding table (em_alert_task_alert) manages this natively.
6 | What is the escalation path if an auto-promoted incident is not acknowledged within SLA? | Use standard Incident Management SLA with escalation rules. Event Management promotion does not change the incident SLA workflow — the promoted incident is a standard incident from that point forward. |  | Do not build a separate escalation path for Event Management incidents. The Incident SLA module handles this correctly for all incidents regardless of origin.

## Dependencies
03 — Alert Promotion Rules — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Event rules baseline configured (workbook 02) | Pending | ECS | Sprint 0, Wk 2 | Promotion rules require alerts to exist; alerts require event rules to be configured first
2 | CI support group mapping in CMDB confirmed | Pending | Customer + ECS | Sprint 0, Wk 2 | Assignment group on promoted incidents derives from CMDB CI support_group; must be populated before promotion testing
3 | Incident category/subcategory taxonomy agreed (from Incident Management workstream) | Pending | Customer | Sprint 0, Wk 2 | Event Management promotion must map to the agreed incident taxonomy; cannot differ from manually created incidents
4 | Non-production CI list confirmed (for non-promotion rule) | Pending | Customer | Sprint 0, Wk 2 | ECS needs the list or CMDB attribute to identify non-production CIs accurately
5 | Recovery event type identified per monitoring tool | Pending | Customer | Sprint 0, Wk 2 | Each tool sends recovery differently (Nagios: OK state, Dynatrace: RESOLVED event type); must be confirmed per source

## Configuration Data
03 — Alert Promotion Rules — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Promotion Thresholds
Severity 1 (Critical) — auto-promote? | Yes — immediate on alert creation | No delay for Critical alerts; the monitoring tool has already determined this is critical
Severity 2 (Major) — auto-promote? | Yes — immediate on alert creation | Same logic as Severity 1; Major events have a material service impact
Severity 3 (Minor) — auto-promote? | Yes — after 15 minutes without acknowledgement | 15-minute window gives operators a chance to review before the system promotes
Severity 4–5 — auto-promote? | No | Informational and low-severity alerts do not auto-create incidents at MVP
Non-production CI — auto-promote? | No — route to Event Triage group for manual review | Customer to confirm non-production identification attribute (e.g., cmdb_ci.environment = 'Development')
2. Incident Field Mapping
short_description | Derived from alert.name (auto-populated by OOTB promotion template) | ECS to validate the resulting format matches incident standards
category | Derived from CI class (cmdb_ci.sys_class_name → category mapping) | Customer to confirm category taxonomy aligns with Incident Management configuration
subcategory | Derived from alert event type | Customer to confirm subcategory mapping per event type
assignment_group | Derived from CMDB CI support_group field | Requires support_group to be populated on all in-scope CIs; ECS to validate coverage during CI correlation workbook
priority | Derived from alert.severity (1=Critical → Priority 1, etc.) | Consistent with OOTB priority matrix; customer to confirm alignment with Incident Management SLA tiers
cmdb_ci | Direct link from alert.cmdb_ci (set during CI correlation) | Requires CI correlation to be working correctly; auto-populates CMDB field on the incident
3. Auto-Resolution Configuration
Recovery event type — Nagios/Icinga | OK | When Nagios sends OK severity event, OOTB closure rule closes the alert
Recovery event type — Dynatrace | Event type = RESOLVED (or severity drops to INFO) | Customer to confirm Dynatrace recovery signal; varies by monitor type
Recovery event type — SolarWinds | Status = Up or severity = Clear | Customer to confirm SolarWinds clear/recovery event type name
Incident auto-resolution state | Resolved (state = 6) with resolution code 'Auto-Resolved' | Work note added to incident before resolution so the team can see the auto-resolution event
Auto-resolution suppression (critical incidents) | Do not auto-resolve if incident priority = 1 and caller is VIP group | Customer to confirm if any incident class should be excluded from auto-resolution
4. Duplicate Detection
Alert-incident binding | OOTB em_alert_task_alert table | If an open incident exists for the CI, new alert is linked as a related alert, not promoted to a new incident
Open incident lookback window | Any incident in 'New' or 'In Progress' state for the same CI | OOTB logic; does not consider incidents in 'Resolved' or 'Closed' state as active
Storm deduplication (>10 alerts from same source in 5 min) | Route to a single parent 'Event Storm' incident via correlation rule | Configured in workbook 02 (storm detection rule); referenced here for promotion linkage

## R&R
03 — Alert Promotion Rules — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Promotion threshold decisions (severity levels, delays) | R | C | ECS facilitates threshold workshop; customer Service Desk Manager and IT Ops lead approve
Incident field mapping to agreed ITSM taxonomy | R | C | ECS maps; customer confirms alignment with Incident Management configuration
Non-production CI identification and non-promotion rule | C | R | Customer defines non-production boundary; ECS configures the rule
Recovery event type confirmation per monitoring tool | I | R | Customer monitoring team confirms; ECS configures the closure rule
Auto-resolution configuration and exclusion list | R | C | ECS configures; customer approves exclusion criteria (e.g., P1 VIP incidents)
End-to-end promotion testing (synthetic events → incidents) | R | C | ECS executes test runs; customer validates incident quality and assignment accuracy
Promotion rule documentation | R | I | ECS documents in this workbook; customer retains for operational runbook

## Consultant Guide
03 — Alert Promotion Rules — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Why Promotion Rules Are the Hardest Conversation
Every customer wants to auto-promote everything and auto-resolve everything. The tension is: over-promotion trains operators to ignore the incident queue; under-promotion means the team is still manually triaging events. The right threshold is almost always narrower than the customer initially wants. Use production data from the monitoring tools to show current alert volume by severity — that conversation resets expectations faster than any presentation.
CMDB Support Group Coverage Is the Hidden Dependency
Alert promotion maps the assignment_group from the CMDB CI's support_group field. If support_group is empty on a CI, the promoted incident has no assignment group — it lands in the unassigned queue and defeats the whole purpose. Before Sprint 1 promotion testing, run a report: how many in-scope CIs have an empty support_group? That gap must be closed before go-live.
Auto-Resolution Is the Metric Customers Will Measure
Track: (1) how many incidents were auto-resolved via Event Management, (2) what percentage of those were legitimate resolutions vs. false positives (monitoring tool said OK but the issue wasn't really fixed). This ratio is what you show in the Sprint demo. A 90%+ legitimate auto-resolution rate is the benchmark for a well-tuned system. Early on, expect 70–80% — it improves as the event rules tighten.
Testing Sequence
Before go-live: (1) synthetic critical event → confirm alert created → confirm incident created with correct assignment group and category; (2) synthetic recovery event → confirm alert closes → confirm incident resolves with auto-resolution note; (3) second critical event for same CI while incident is open → confirm new alert links to existing incident, not a new one; (4) non-production CI event → confirm no incident is created.

## Adoption vs Re-engineering
03 — Alert Promotion Rules — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want every alert to create an incident — even informational ones.' | Use the OOTB operator workspace for informational alerts; only Critical/Major auto-create incidents. Operators review informational alerts manually and promote if warranted. | Auto-promoting informational alerts fills the incident queue with non-actionable records within hours. Operator confidence collapses and the team starts closing incidents without reading them. | 'Let's show you the operator workspace — informational alerts are visible there and a single click promotes to an incident if the operator decides it warrants one. You get full visibility without the queue flood.' | Only if a regulatory requirement mandates an incident record for every event. Even then, use a separate low-priority incident queue with a dedicated assignment group.
'We want the auto-resolved incident to be Closed, not Resolved.' | Use Resolved (state = 6) for auto-resolution. Closed (state = 7) requires a closure code and caller confirmation in most Incident Management configurations. | OOTB incident workflow requires closure confirmation before reaching Closed state. Bypassing this breaks the Incident SLA closure metric and creates audit gaps. | 'Resolved is the right landing state — it signals the monitoring tool confirmed the issue is cleared, the team can review and formally close after confirming there is no follow-up action. Closed without that review step is a governance risk.' | Only if the customer has explicitly removed the closure confirmation step from their Incident workflow AND has a named owner for the audit gap.

## ServiceNow Mapping
03 — Alert Promotion Rules — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Core Promotion Tables
Alert promotion rule table | em_alert_task_rule | Defines conditions for alert-to-incident promotion
Alert-incident binding table | em_alert_task_alert | Links alerts to their promoted incidents; drives deduplication
Promotion template table | em_alert_task_template | Defines default field values for promoted incidents
Alert closure rule table | em_alert_state_rule | Drives auto-resolution when recovery event arrives
2. Key Promotion Fields
em_alert.cmdb_ci | CI linked to the alert (from CI correlation) | Drives assignment_group, category, and location on the promoted incident
em_alert.severity | 1–5 scale (from event rules) | Primary promotion threshold condition
em_alert.state | Open / Flapping / Closed / Resolved | Promotion only fires when state = Open; closed/resolved alerts do not re-promote
em_alert.task | Reference to promoted incident (task table) | Set by the promotion engine; used for deduplication lookup
3. OOTB Features Used
Alert Promotion Rules | Conditions and templates for incident creation | Configured via Event Management > Alert Management > Promotion Rules
Alert-Incident Binding | Deduplication and related-alert linking | OOTB em_alert_task_alert; no custom code required
Alert Closure Rules | Auto-resolution on recovery event | Configured via Event Management > Alert Management > Alert State Rules
CI Support Group Lookup | Auto-assignment via CMDB | Requires CMDB support_group field to be populated on all in-scope CIs