## Instructions
04 — CI Correlation Mapping
Event Management Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Documents how events from monitoring tools are correlated to CMDB Configuration Items. CI correlation is the bridge between the monitoring world (hostnames, IPs, DNS names) and the ServiceNow CMDB. Without it, alert promotion, auto-assignment, and service impact analysis all fail.
Who fills this out | ECS Solution Architect (primary), with customer CMDB owner validating CI naming conventions and coverage.
Sprint window | Sprint 0, Week 2 — Sprint 1, Week 1
Estimated effort | 6–10 hours including CI identifier rule design, CMDB gap analysis, and correlation testing
Related workbooks | 01 Event Sources · 02 Event Rules Baseline · Foundation Data Pack — CIs
Success criteria
• | CI identifier rules are configured for each event source's naming convention (hostname, IP, FQDN, custom tag).
• | Coverage report shows CI correlation rate ≥ 85% for in-scope monitoring sources at go-live.
• | Uncorrelated event handling is defined (route to triage queue, not discard).
• | Business Service maps are either built or explicitly deferred to Phase 2 with a named owner.
• | CMDB gap analysis (CIs monitored but not in CMDB) is completed and remediation is planned.

## Process Decisions
04 — CI Correlation Mapping — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How does each monitoring tool identify the affected CI — hostname, IP, FQDN, or custom tag? | Document the node field value format per source. Map to the corresponding CMDB attribute (name, ip_address, fqdn, asset_tag). |  | CI identifier rules match the em_event.node value to a CMDB CI attribute. If the format does not match, correlation fails silently — events are recorded but no CI is linked, which breaks promotion and assignment.
2 | What is the target CI correlation coverage rate at go-live? | 85% or higher. Events without a CI correlation are routed to an 'Uncorrelated Events' assignment group, not discarded. |  | 100% correlation at go-live is rarely achievable because monitoring tools often know about CIs that are not yet in the CMDB. 85% is a realistic MVP target; drive toward 95%+ by end of Phase 2.
3 | What happens to events that cannot be correlated to a CI? | Route to a designated 'Event Triage' assignment group. Do not discard — uncorrelated events may represent CIs that should be in the CMDB but are not. |  | Discarding uncorrelated events hides CMDB gaps and means real incidents are never raised for those CIs. The triage queue is the safety net and the CMDB improvement driver.
4 | Are Business Service maps in scope for Foundations? | Defer Business Service maps to Phase 2 unless a service map already exists in the CMDB. CI-level correlation is the MVP foundation. |  | Building accurate Business Service maps requires a mature CMDB and stakeholder investment in service topology documentation. Forcing it in Foundations delays go-live without commensurate value.
5 | How will dynamic infrastructure CIs (cloud VMs, containers, auto-scaled instances) be handled? | Use ServiceNow Discovery or a cloud connector to keep dynamic CI records current. Event Management CI correlation depends on CMDB accuracy for dynamic infrastructure. |  | Dynamic infrastructure is where CI correlation most commonly fails — a VM spun up after the last Discovery run does not exist in the CMDB. The Discovery workstream must be coordinated with Event Management if cloud or containerised infrastructure is in scope.

## Dependencies
04 — CI Correlation Mapping — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CMDB CI baseline loaded with name, ip_address, and fqdn attributes populated | Pending | ECS + Customer | Sprint 0, Wk 1 | CI correlation requires CI records to exist and have populated identifier attributes
2 | Event sources confirmed with node field format documented (workbook 01) | Pending | ECS | Sprint 0, Wk 2 | Cannot configure CI identifier rules without knowing how each tool identifies CIs
3 | Business Service map decision made (in scope vs. deferred) | Pending | Customer | Sprint 0, Wk 2 | Service map scope affects correlation rule design; must be decided before Sprint 1
4 | Discovery / cloud connector scope confirmed (for dynamic CIs) | Pending | Customer + ECS | Sprint 0, Wk 2 | Dynamic CI coverage must be understood before go-live; gaps mean uncorrelated events for cloud workloads

## Configuration Data
04 — CI Correlation Mapping — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. CI Identifier Rules
Primary identifier — hostname | em_event.node → cmdb_ci.name (case-insensitive) | Works for most on-premises servers; hostname must match exactly
Secondary identifier — IP address | em_event.node → cmdb_ci.ip_address | Fallback if hostname match fails; requires IP to be populated on the CI record
Tertiary identifier — FQDN | em_event.node → cmdb_ci.fqdn | Used by tools that send fully qualified domain names; common for network devices
Tool-specific tag mapping | Customer to document | Some tools (e.g., Dynatrace entity IDs) require a custom attribute on the CI; ECS configures the lookup
Match failure behaviour | Route to Event Triage assignment group; do not discard | Uncorrelated events are logged and visible for CMDB remediation
2. CMDB Coverage Baseline
In-scope CI count (monitored by at least one source) | TBD | Customer to provide or ECS to derive from monitoring tool export
CI records with name populated | TBD% | ECS to run CMDB report; target 100% for in-scope CIs
CI records with ip_address populated | TBD% | Target 90%+ for servers; lower acceptable for non-IP-addressable CIs
CI records with fqdn populated | TBD% | Required for sources that send FQDN; ECS to report coverage
CI records with support_group populated | TBD% | Required for auto-assignment on promoted incidents; target 95%+
Target correlation rate at go-live | ≥ 85% | Track weekly after go-live; drive toward 95%+ by end of Phase 2
3. Business Service Map (Phase 2 Target)
Business Service map scope | Deferred to Phase 2 (unless existing map available) | If a service map exists, ECS will validate and link to Event Management correlation rules
Phase 2 target service count | TBD | Customer to identify top 5–10 services for Phase 2 mapping
Service map source | Manual mapping or Discovery-derived | Discovery-derived maps are more accurate but require Discovery to be mature first

## R&R
04 — CI Correlation Mapping — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Node field format documentation per monitoring tool | C | R | Customer monitoring team documents; ECS uses for identifier rule design
CI identifier rule configuration | R | I | ECS configures all CI identifier rules; customer validates in testing
CMDB CI coverage gap analysis | R | C | ECS runs the report; customer CMDB owner reviews and confirms remediation plan
CMDB attribute population (name, ip, fqdn, support_group) | C | R | Customer CMDB team populates; ECS validates coverage rate
Event Triage group creation and staffing | I | R | Customer defines the triage group and assigns members; ECS configures the routing rule
Business Service map scope decision (Foundations vs. Phase 2) | C | R | Customer decides; ECS documents the decision and Phase 2 plan
CI correlation rate validation (≥ 85% checkpoint) | R | C | ECS measures from em_event data; customer reviews and approves go-live readiness

## Consultant Guide
04 — CI Correlation Mapping — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
CI Correlation Is the Hidden Critical Path Item
CI identifier rules sound simple, but the reality is that monitoring tools and the CMDB evolved independently and use different naming conventions. Dynatrace uses its own entity IDs. SolarWinds uses Node Names that may or may not match the CMDB hostname. Network devices are often in the CMDB by their management IP, not their hostname. Spend an hour with both the monitoring team and the CMDB team together in the same room — it surfaces the naming gaps faster than any analysis.
The 85% Target and What to Do About the Other 15%
The uncorrelated 15% at go-live is not a failure — it is a CMDB improvement backlog. Every uncorrelated event is evidence of a CI that should be in the CMDB. Track uncorrelated events in the triage queue for 4 weeks, then run a report: what are the top 20 uncorrelated node values? Those become the CMDB remediation list for Phase 2. Show this to the customer as the virtuous cycle: better events → better CMDB → better correlation → better events.
Dynamic Infrastructure Warning
If the customer runs significant cloud or containerised workloads, CI correlation for those assets requires a real-time Discovery or cloud connector — not a periodic CMDB snapshot. A VM that spins up after the last Discovery run does not exist in the CMDB. Events from that VM are uncorrelated. If the VM hosts a critical service, that means Event Management is blind to it. Flag this explicitly with the customer and ensure the Discovery workstream is coordinated.
Support Group Coverage Is Mandatory, Not Optional
At least 95% of in-scope CIs must have a support_group populated before go-live. This is not a nice-to-have. An incident promoted from an Event Management alert with no assignment group lands in an unassigned queue and is indistinguishable from a manually created incident with a data entry error. Run the coverage report early in Sprint 0 and give the customer time to remediate.

## Adoption vs Re-engineering
04 — CI Correlation Mapping — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'Our monitoring tool knows about CIs that are not in the CMDB — can Event Management create CIs automatically?' | No. Event Management correlates events to existing CMDB CIs; it does not create new CI records. Use Discovery or manual import to add missing CIs to the CMDB. | Auto-creating CIs from event data produces low-quality CMDB records with no ownership, no relationships, and no lifecycle data. The CMDB degrades faster than it grows. | 'What Event Management can do is show you exactly which node values are failing correlation — that is your missing CI list. Discovery or a quick import fills those gaps properly with full CMDB attributes.' | Never. This is an architectural boundary.
'Can we skip CI correlation and just use event metadata for incident assignment?' | Use CI correlation and derive assignment from the CMDB. Event metadata routing requires custom scripting and produces brittle assignment logic that breaks when tool configurations change. | CMDB-based assignment is maintainable by the customer's CMDB team without ECS involvement. Metadata-based routing requires a developer to update scripts every time the monitoring tool changes its event format. | 'The CMDB approach is self-maintaining — update the support_group on the CI record and the assignment changes everywhere automatically. Let me show you why that is worth the upfront CI coverage work.' | Only if the CMDB is genuinely too immature to populate support_group in time for go-live. Even then, plan to migrate to CMDB-based routing in Phase 2.

## ServiceNow Mapping
04 — CI Correlation Mapping — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. CI Identifier Tables
CI identifier rule table | em_ci_identifier_rule | Defines how em_event.node maps to a CMDB CI; evaluated in priority order
CI identifier type table | em_ci_identifier_type | Defines the CMDB attribute used for lookup (name, ip_address, fqdn, etc.)
Uncorrelated event log | em_event (where cmdb_ci is empty) | Used for CMDB gap analysis; query this table weekly in the first 30 days
2. Key CI Attributes Required for Correlation
cmdb_ci.name | Primary identifier; must match em_event.node for hostname-based sources | Case-insensitive match; partial match not supported in OOTB rules
cmdb_ci.ip_address | Secondary identifier for IP-based sources | IPv4 only in base OOTB; IPv6 requires custom rule
cmdb_ci.fqdn | Tertiary identifier for FQDN-based sources | Must be fully qualified (e.g., server01.domain.com, not server01)
cmdb_ci.support_group | Required for auto-assignment on promoted incidents | Must be a valid sys_user_group reference; free-text not supported
cmdb_ci.environment | Used for non-production suppression rule | Values: Production, Development, Test, Staging; customer to confirm taxonomy
3. OOTB Features Used
CI Identifier Rules | Core CI correlation engine | Configured via Event Management > Administration > CI Identifier Rules
Event Triage Assignment Group | Routing destination for uncorrelated events | Standard assignment group; created via User Administration > Groups
Business Service Map (Phase 2) | Service-level alert grouping | Configured via Service Mapping or manual map builder; deferred from Foundations